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The 2023 Annual Action Plan of the Bibiani-Anhwiaso-Bekwai Municipal Assembly outlines the programmes and projects which the Municipal Assembly has planned to implement in 2023 with the collaboration and support of the Central Government, Donors, NGOs, CSOs, communities, etc. They are programmes and projects earmarked in the 2022-2025 DMTDP that are in line the Medium-Term National Development Policy Framework (MTNDPF 2022-2025) christened “An Agenda for Jobs: Creating Prosperity and Equal Opportunity for All II” and also enshrined with the Long Term National Development Policy Framework “a just, free, and prosperous nation with high levels of national income and broad-based social development’’ and the Medium-Term National Development Policy Framework, 2022-2025, with seven main goals: build a prosperous society; create equal opportunities for all;  safeguard the natural  environment and ensure a resilient built environment; Maintain a stable, united and safe society; Mainstream Emergency Response Activities into District Development Planning and Improve percentage implementation of Development Programme.

The 2021 Population and Housing Census (PHC) put the Municipal population at 167,971 which is made up of 82,798 males and 85,173 females, with a population growth rate of 1.8%.  

1.1 DATE OF ESTABLISHMENT
The Bibiani-Anhwiaso-Bekwai Municipal Assembly was established in 1988 by the Local Government (Bibiani-Anhwiaso-Bekwai Municipal Assembly) (Establishment) Instrument, L.I 1387 under the then Local Government Law, 1988 PNDCL 207. The District was elevated into a Municipal status in 2018 and inaugurated on Thursday, 15th March, 2018 with LI 2284. Bibiani is the Municipal capital of the Bibiani Anhwiaso Bekwai Municipal.

1.2 VISION
The vision of the Assembly is to be an efficient and effective municipality with continuous enhanced living standards of its people.

1.3 MISSION STATEMENT
The Municipal Assembly exists ‘to facilitate the overall development of the municipality by effectively formulating and implementing plans and programmesof the Assembly, Ministries, Departments, Agencies and Non-Governmental Organisations in order to improve the quality of life of the people in the District. 





1.4 LOCATION AND SIZE
The municipality is located in the north-western part of the Western Region of Ghana and between latitude 6o N, 3o N and longitude 2o W, 3o W. It is bordered to the North by the Atwima Mponua District in the Ashanti Region, South by the Wassa Amenfi West in the Western Region, West by the Sefwi Wiawso Municipal Assembly in the Western North Region and East by the Upper Denkyira West and Amannsie West in the Ashanti Region respectively. The municipal has a total land area of 873 km square.

Table 1 below provides a summary of the plan under various Development Dimesions 

	THEMATIC AREAS

	ECONOMIC DEVELOPMENT
	SOCIAL DEVELOPMENT
	ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENTS
	GOVERNANCE, CORRUPTION AND ACCOUNTABILITY
	Emergency Planning & Response (Inclusding Covid-19)
	Implementation, Coordinating, Monitoring & Evaluation

	
GOAL
	
Build a prosperous society
	
Create equal opportunity for all
	
Ensure resilient built environment while safeguarding the natural environment
	
Maintain a stable, safe and united society
	Mainstream Emergency Response Activities into district development Planning
	Improve percentage implementation of development programme

	
SECTORS
	
Trade, Agriculture, Markets, Tourism, Private Sector Development
	Education, Health, Child dev’t & Protection, HIV/AIDS, Persons with Disability, Portable Water, Women Empowerment & Gender
	
Transportation, Energy, Waste & Sanitation, ICT, Human Settlement & Dev’t Planning, Natural Resource.
	
Revenue Mobilization, Local Governance, Security
	Health care, disaster prevention and pandemics
	Development planning, Budgeting and local governance

	TOTAL NO. OF PROGRAMS AND PROJECTS

	35
	73
	30
	17
	

6
	

8

	LEAD IMPLEMENTING AGENCY

	BAC, MOFA, DWD / Central Administration
	SWCD, GHS, GES, DWD, ILO, TA/ Central Administration
	MEHU, DWD,TCPD, FSD, GES/ Central Administration
	NADMO, GNFS/ Central Administration
	GHS, NADMO and Central Administration
	Central Administration
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	Programme (PBB)
	Sub- Programme (PBB)
	Broad Activities
	Location
	Time Frame
	Cost
	Programme Status
	Implementing Institution

	
	
	
	
	Q1
	Q2
	Q3
	Q4
	GoG
(GH¢)
	IGF
(GH¢)
	Others
(GH¢)
	New
	On-going
	Lead
	Collaborating

	DEVELOPMENT DIMENSION 1: ECONOMIC DEVELOPMENT

	Focus Area: Strong and Resilient Economy

	Management and Administration
	Finance
	1. Train revenue collectors and key staff on revenue collection strategies
	Bibiani
	
	
	
	
	-
	15,000.00
	5,000.00
	· 
	-
	Finance
	CA, GIZ

	Management
	Finance
	2. Update the list of ratable properties and businesses to enhance revenue mobilization
	Municipal
Wide
	
	
	
	
	-
	30,000.00
	-
	· 
	-
	Finance Dept./

	CA

	Focus Area: Private Sector Development

	Economic Development 

























	Trade, Industry and Tourism























	3.Training and provision of start-up kits for 60 people in Gari processing, bee keeping, Soap making, Baking &confessionary 
	Municipal wide
	
	
	
	
	20,000
	30,000.00
	10,000.00
	· 
	-
	BAC
	CA

	
	
	4.Facilitate linkages among 5 local SMEs to Large Contractors on Subcontract base on GoG/MA projects
	Municipal
wide
	
	
	
	
	20,000.00
	15,000.00
	-
	· 
	-
	BAC
	CA, Donors

	
	
	5.Provide apprenticeship and start -ups for 30 youth in carpentry, Masonry, Auto-Mechanics, Welding& Fabrication
	Municipal wide
	
	
	
	
	20,000.00
	20,000.00
	10,000.00
	· 
	-
	BAC
	CA, RTF, Donors

	
	
	6.Organise management training for 120 SMEs and Entrepreneurs
	Municipal wide
	
	
	
	
	30,000.00
	35,000.00
	-
	· 
	-
	BAC
	CA

	
	
	7.Support Agriculture value chain Actors & SMEs with Revolving Funds
	Municipal wide
	
	
	
	
	-
	-
	500,000.00
	· 
	-
	BAC
	EU, Sefwiman Rural Bank

	
	
	8.Partner with financial institutions to provide loans to SMEs
	Municipality- wide
	
	
	
	
	-
	30,000.00
	-
	· 
	-
	BAC
	Financial Institutions,

	Focus Area: Agriculture and Rural Development
	

	Economic Development 

























	Agricultural Services and Management























	9. Update and intensify the use of mass communication systems and electronic media weekly for extension delivery by 8 scheduled officers
	Municipality- wide
	
	
	
	
	
2,400.00
	-
	-
	· 
	-
	MDA
	CA

	
	
	10. Disseminate Extension Information through 15 AEAs fortnightly home and farm visits including Vet AEAs.
	Municipality- wide
	
	
	
	
	18,000.00
	-
	-
	· 
	-
	MDA
	CA

	
	
	11. Conduct quarterly monitoring by 8 MAOs and MDA
	Municipality- wide
	
	
	
	
	
24,000.00
	-
	-
	· 
	-
	MDA
	CA

	
	
	12. Train 30 farmers on nursery management, GAPs
	Bibiani
	
	
	
	
	2,495.00
	-
	-
	· 
	-
	MDA
	CA

	
	
	13. Follow up visit to 30 rice farmers PWD, Aged and Youth by MDA, MIS.
	Municipality- wide
	
	
	
	
	1,800.00
	-
	-
	· 
	-
	MDA
	CA

	
	
	14. 1 demonstration set up by 15 AEAs by 2nd quarter, 2023 
	Municipality- wide
	
	
	
	
	4,500.00
	-
	-
	· 
	-
	MDA
	CA

	
	
	15. 2 Field days by 15 AEAs for 30 farmers by 2nd quarter, 2023
	Municipality- wide
	
	
	
	
	2,200.00
	-
	-
	· 
	-
	MDA
	CA

	
	
	16. Train and resource 25 DOA staff and 30 farmers in post-harvest management of cereal crops
	Municipality- wide
	
	
	
	
	4,560.00
	-
	-
	· 
	-
	MDA
	CA

	
	
	17. Create awareness and build capacity in extension delivery skills for 8 MAOs and 15 AEAs on  HIV/AIDS, Covid-19, Malaria prevention and Child labour elimination in agriculture
	Municipality- wide
	
	
	
	
	2,500.00
	-
	-
	· 
	-
	MDA
	CA

	
	
	18. Sensitize and Train 30 Ghana School feeding and free SHS caterers on the use of local food ingredients
	Selected Caterers
	
	
	
	
	6,000.00
	-
	-
	· 
	-
	MDA
	CA

	
	
	19. Support for Planting for Food and Jobs (PFJs) &Planting for Export and Rural Development (PERD) and other agricultural programme.
	Municipality- wide
	
	
	
	
	1,016,420.00
	-
	-
	· 
	-
	MDA
	CA

	
	
	20. Training of four (4) AEAs, 2 Market Enumerators, one (1) MIS Officer and MDA on market linkages, Networking and data collection.  Data
	Municipality- wide
	
	
	
	
	1,200.00
	-
	-
	· 
	
	MDA
	CA

	
	
	21. Sensitization of 100 livestock farmers (male, female, PWD, Youth) on vaccination of Pets against Rabies and PPR by December, 31st 2023
	Municipality- wide
	
	
	
	
	2,500.00
	-
	-
	· 
	
	MDA
	CA

	
	
	22. Organize training for 15 AEAs, 8 MAOs and 30 Farmers on GAPs in vegetable production
	Municipality- wide
	
	
	
	
	3,857.00
	-
	-
	· 
	
	MDA
	CA

	
	
	23. Organize training for 15 AEAs, 8 MAOs, 2 Market Enumerators on Web-Based Reporting Format by the MIS Officer by 31st March 2023 
	Municipality- wide
	
	
	
	
	2,240.00
	-
	-
	· 
	
	MDA
	CA

	
	
	24. Organize 4 Quarterly technical Review Meeting 
	Municipality- wide
	
	
	
	
	4,800.00
	-
	-
	· 
	
	MDA
	CA

	
	
	25. Organize 8 monthly Staff and 12 Management Meetings by  MIS Officer
	Municipality- wide
	
	
	
	
	9,000.00
	-
	-
	· 
	
	MDA
	CA

	
	
	26. Support the implementation of Rice improvement project with JICA
	Municipality- wide
	
	
	
	
	51,000.00
	-
	-
	· 
	
	MDA
	CA

	
	
	27. Organize 2 TEDMAG Trainings for 30 Technical staff.
	Municipality- wide
	
	
	
	
	9,000.00
	-
	-
	· 
	-
	MDA
	CA

	Economic Development 

	Agricultural Services and Management

	28. Train 3 tractor operators and 12 power tiller operators under DCAT establishment.
	Municipality- wide
	
	
	
	
	2,500.00
	-
	-
	· 
	-
	MDA
	CA

	Economic Development 

	Agricultural Services and Management

	29. Organize one day training workshop for 20 livestock farmers (male, female, PWD, Youth on FBO Formation, Farmer Database, and Value Addition by June, 2023.
	Municipality- wide
	
	
	
	
	1, 860.00
	-
	-
	· 
	
	MDA
	CA

	Economic Development 

	Agricultural Services and Management
	30. Organize Municipal RELC Planning Session by June , 2023
	Bibiani
	
	
	
	
	5,400.00
	-
	-
	· 
	
	MDA
	CA

	Economic Development 

	Agricultural Services and Management

	31. Organize quarterly training on climate smart agriculture for 15 AEAs, 8 MAOs, and 200 farmers (male, female, PWDs, Youth and Aged) by 31st December, 2023.
	Municipality- wide
	
	
	
	
	25,000.00
	-
	-
	· 
	
	MDA
	CA

	Focus Area: Tourism and Creative Arts Development

	Economic Development
	Trade, Industry and Tourism
	32. Project Independence Day celebration
	Municipal wide
	
	
	
	
	-
	20,000.00
	50,000.00
	· 
	-
	CA
	Private Sector

	
	
	33. Organize radio sensitizations to educate public on issues including marriage rites and puberty rights
	Bibiani & Bekwai
	
	
	
	
	-
	20, 000.00
	-
	· 
	-
	Dept. of Arts & Culture
	CA

	Economic Development
	Economic Development
	34. Establishment of an Arts center to promote local Arts & Culture
	Bibiani
	
	
	
	
	-
	20,000.00
	-
	· 
	-
	Dept. of Arts & Culture
	CA

	Economic Development
	Economic Development
	35. Organize 2023 Municipal Festival of Arts and Culture
	Bibiani
	
	
	
	
	-
	90,000.00
	-
	· 
	-
	Dept. of Arts & Culture
	CA

	DEVELOPMENT DIMENSION 2: SOCIAL DEVELOPMENT

	Focus Area: Education and Training

	39. 
	
	36. Rehabilitation of  Lineso JHS Block
	Lineso
	
	
	
	
	200,000.00
	-
	-
	· 
	-
	GES
	CA

	
	
	37. Construction of 1 No. 6-Unit Classroom Block with office, store and 5-seater WC toilet facility
	Bibiani community JHS
	
	
	
	
	350, 000.00
	-
	-
	· 
	-
	GES
	CA

	
	
	38. Construction of 1No. 2-Unit KG  Block with office, store and 5-seater W/C
	Bekwai Methodist
	
	
	
	
	380,000.00
	-
	-
	· 
	-
	GES
	Works

	
	
	39. Supply of 794 No. Dual Desks and 360 Mono Desks to Basic Schools  
	Municipality- wide
	
	
	
	
	328,200.00
	-
	-
	· 
	-
	GES
	Works

	
	
	40. Construction of 1 No. 6-Unit Classroom Block with office, Store and 5-Seater WC toilet facility at Queens SHS 
	Bekwai
	
	
	
	
	791,920.30
	-
	-
	· 
	-
	GES
	Works

	
	
	41. Construction of 1No. 3-Unit Classroom Block with office, store and 5-seater W/C
	Hwenampori
	
	
	
	
	350,000.00
	-
	-
	· 
	-
	GES
	Works

	
	
	42. STMIE for 30 students from selected schools 
	Municipal wide 
	
	
	
	
	-
	20,000.00
	27,000.00
	· 
	-
	GES 
	MA, Private sector 

	
	
	43. Mock exams for BECE candidates  
	Municipal wide 
	
	
	
	
	153,000.00
	-
	-
	· 
	-
	GES 
	CA

	
	
	44. Organize Inter-schools’ sports and athletic competition
	Municipal Wide
	
	
	
	
	-
	30,000.00
	-
	· 
	-
	GES
	CA

	
	
	45. Organise capacity building for Teachers
	Bibiani
	
	
	
	
	20,000.00
	-
	20,000.00
	· 
	-
	GES
	CA

	
	
	46. Supply of 1,000 Mono Desk & 1,000 Dual Desk for schools
	Selected Schools
	
	
	
	
	-
	-
	300,000.00
	· 
	-
	GES
	CA

	
	
	47. Construction of 1No. 3-Unit classroom Block
	Kumkumso
	
	
	
	
	350,000.00
	-
	-
	· 
	-
	GES
	CA

	Focus Area: Health and Health Services

	
	
	48. Construction of 1 No. CHPS compound with Borehole & 3-seater WC Toilet facility
	Aboabo
	
	
	
	
	325,000.00
	-
	-
	· 
	-
	GHS
	Works

	
	
	49. Procurement of 10 delivery sets for CHPS Compounds
	Selected CHPS Zones
	
	
	
	
	30,000.00
	-
	-
	· 
	-
	GHS
	CA

	
	
	50. Construction of 1 No. CHPS compound with 3-seater WC Toilet facility
	Adupri
	
	
	
	
	325,000.00
	-
	-
	· 
	-
	GHS
	CA

	
	
	51. Procurement of 5 delivery beds for CHPS compounds 
	Selected CHPS Zones
	
	
	
	
	50,000.00 
	-
	-
	· 
	-
	GHS 
	CA

	
	
	52. Construction of 2No mechanized borehole in existing CHPS Compounds
	Ampenkrom
Nkatieso
	
	
	
	
	90,000.00
	-
	-
	· 
	-
	GHS
	CA

	
	
	53. Construction and mechanization of 6 No. Boreholes for selected CHPS Compounds
	Mmerewa, Asawinso, Bassengele, Wenchi, Aboduabo & Chirano health Center
	
	
	
	
	246,000.00
	-
	-
	· 
	-
	GHS
	Works

	
	
	54. Renovation of  Mmerewa and Humijibre CHPS compounds
	Mmerewa, Humjibre
	
	
	
	
	-
	120,000.00
	-
	· 
	-
	GHS 
	CA

	
	
	55. Support training in malaria case management
	Municipal wide
	
	
	
	
	25,000.00
	10,000.00
	-
	· 
	-
	GHS
	CA, Private Sector, NGOs

	
	
	56. Support for national immunization campaigns and support for neglected tropical Disease control programme 
	Municipal wide 
	
	
	
	
	-
	30,000.00
	30,000.00
	· 
	-
	GHS 
	CA 

	
	
	57. Intensify education to reduce stigmatization on HIV/AIDs and other diseases
	Municipal wide
	
	
	
	
	16,000.00
	20,000.00
	-
	· 
	-
	GHS
	CA

	
	
	58. Intensify behavioural change strategies, especially for high risks groups for HIV/AIDS and TB
	Municipal wide 
	
	
	
	
	6,000.00
	10,000.00
	-
	· 
	-
	GHS
	CA

	
	
	59. Rehabilitation of malnourished children ward and support other Nutritional activities
	Bibiani
	
	
	
	
	50,000.00
	-
	-
	· 
	-
	GHS
	CA

	
	
	60. Organise quarterly Municipal health Committee meetings 
	Bibiani
	
	
	
	
	-
	35,000.00
	-
	· 
	-
	GHS 
	CA

	
	
	61. Support the management of Public Health emergencies i e. disease outbreak 
	Municipal wide 
	
	
	
	
	-
	-
	250,000.00
	· 
	-
	GHS 
	CA

	Focus Area: Food and Nutrition Security 

	Social Service Delivery
	Public Health Services and Management
	62. Promote nutritionally sensitive and cost-effective diet through education and sensitization through radio and community visits
	Municipal wide 
	
	
	
	
	28,000.00
	50,000.00
	2,000.00
	· 
	-
	GHS
	CA, Private Sector,

	
	
	63. Promote the production of diversified, nutrient-rich food and consumption of nutrition foods
	Municipal wide 
	
	
	
	
	-
	20,000.00
	30,000.00
	· 
	-
	GHS
	CA

	
	
	64. Sensitisation to reduce infant, adult malnutrition, and dietary non communicable diseases
	Municipal wide 
	
	
	
	
	15,000.00
	30,000.00
	-
	· 
	-
	GHS
	CA

	Social Service Delivery
	Public Health Services and Management
	65. Organise demonstrative training workshop for women on kitchen gardens and food basal in 10 communities 
	Selected
Communities
	
	
	
	
	-
	20,000.00
	30,000.00
	· 
	-
	SWCD
	CA

	Focus Area: Population Management and Migration for Development

	Social Services Delivery
	Public Health Services and management
	66. Organise sensitization programme on teenage pregnancy on radio
	Bibiani
	
	
	
	
	-
	22,000.00
	-
	· 
	-
	SWCD
	NCCE
UNICEF

	Social Services Delivery
	Population Management
	67. Collaboration with Immigration service on migration data within the Municipality
	Municipal
Wide
	
	
	
	
	10,000.00
	25,000.00
	-
	· 
	-
	Statistics Dept
	CA
GIS

	Focus Area: Reducing Poverty and Inequality

	Social Services Delivery
	Social Welfare and Community Services
	68. Monitor and coordinate Livelihood Empowerment Against Poverty (LEAP) programme
	Municipal Wide
	
	
	
	
	-
	-
	34,000.00
	· 
	-
	SW&CD
	CA

	
	
	69. Coordinate activities of School Feeding Programme
	Beneficiary schools
	
	
	
	
	30,000.00
	20,000.00
	-
	· 
	-
	SW&CD
	CA

	
	
	70. Provision of Medical Support to the vulnerable
	Municipal Wide
	
	
	
	
	70,000.00
	30,000.00
	-
	· 
	-
	SWCD
	CA

	
	
	71. Support 1,000 Vulnerable people to get NHIS Cards
	Municipal Wide
	
	
	
	
	30,000.00
	50,000.00
	15,000.00
	· 
	-
	SWCD
	CA

	Focus Area: Water and Environmental Sanitation

	Infrastructure Development and Management
	Public Works, Rural Housing and Water Management
	72. Construction and Mechanization of 7 No. Boreholes
	Fawokabra, Mota-yard, Bibiabi SHTS, Ntakam,  Anyinase, Ohiampeneka & Asempaneye
	
	
	
	
	287,000.00
	-
	-
	· 
	-
	Works Dept.
	LMC

	
	
	73. Formation and training of WATSANS members in 10 communities
	Selected Towns
	
	
	
	
	40,000.00
	20,000.00
	-
	· 
	-
	EHU
	MA

	Social Services Delivery
	Environmental Health and Sanitation Services
	74. Procure 2 No motorbikes for monitoring activities of sanitation service providers
	Bibiani
	
	
	
	
	86,000.00
	-
	-
	· 
	-
	EHU
	CA

	
	
	75. Procure 5 No. refuse containers and sanitary tools
	Municipal
Wide
	
	
	
	
	70,000.00
	-
	-
	· 
	-
	EHU
	CA

	
	
	76. Conduct medical  screening for 800 food vendors
	Municipal Wide
	
	
	
	
	20,000.00
	35,000.00
	-
	· 
	-
	EHU
	CA

	
	
	78. Promote household toilet construction in 10 communities (CLTS)
	Municipal
Wide
	
	
	
	
	5,500.00
	20,000.00
	-
	· 
	-
	EHU
	CA

	
	
	79. Conduct environmental health /hygiene education in 40 communities
	Municipal Wide
	
	
	
	
	32,000.00
	-
	-
	· 
	-
	EHU
	GES, NGOs

	
	
	80. Organize spraying to control Pests and vectors in the municipality
	Bibiani
	
	
	
	
	30,000.00
	20,000.00
	-
	· 
	-
	EHU
	MA

	
	
	81. Solid and liquid waste management, (Fumigation, manage wasteland fills Contract with Zoomlion)
	Municipal Wide
	
	
	
	
	300,000.00
	-
	-
	· 
	-
	EHU
	CA, Zoomlion

	
	
	82. Conduct quarterly Evaluation and Performance Review meetings with Environmental Health Zonal Heads
	Bibiani
	
	
	
	
	20,000.00
	25,000.00
	-
	· 
	-
	EHU
	CA

	
	
	83. Conduct monthly monitoring of Sanitation service providers
	Municipal
Wide
	
	
	
	
	15,000.00
	20,000.00
	-
	· 
	-
	EHU
	CA

	
	
	84. Conduct quarterly meeting of Sanitation Service providers
	Bibiani
	
	
	
	
	12,000.00
	12,000.00
	-
	· 
	-
	EHU
	CA

	
	
	85. Construction of Slaughterhouse in Bibiani
	Bibiani
	
	
	
	
	400,000.00
	-
	-
	· 
	-
	EHU
	CA

	
	
	86. Procurement of 1 ambient meter for controlling public noise
	Selected Communities
	
	
	
	
	15,000.00
	-
	-
	· 
	-
	EHU
	CA

	
	
	87. Support quarterly leaning exercises 
	Municipality-wide
	
	
	
	
	20,000.00
	-
	-
	· 
	-
	EHU
	CA

	
	
	88. Construction of Pour Flush Toilet Facility
	Bibiani
	
	
	
	
	400,000.00
	-
	-
	· 
	-
	EHU
	CA

	
	
	89. Provide public education on solid waste management
	Municipal wide 
	
	
	
	
	10,000.00
	4000.00
	4000.00
	· 
	-
	EHU
	CA

	
	
	90. Promote public health education and hygiene in basic schools
	Municipal wide 
	
	
	
	
	10,.000.00
	40,000.00
	5000.00
	· 
	-
	EHU
	CA

	
	
	91. Training of food vendors on safety and proper handling of food
	Municipal wide 
	
	
	
	
	-
	20,000.00
	15,000.00
	· 
	
	EHU
	CA

	Focus Area: Child Protection and Development
	

	Social Services Delivery

	Social Welfare and Community Services

	92. Formation of Community Child Protection Committees in 10 Child labour endemic communities and train them on child labour issues
	Selected Towns
	
	
	
	
	-
	
32,000.00
	10,000.00
	· 
	-
	SW&CD
	MCPC 

	
	
	93. Organize sensitization programmes on child labour
	Bibiani
	
	
	
	
	-
	20,000.00
	20,000.00
	· 
	-
	SW&CD
	MCPC

	
	
	94. Remediation support for children
	
	
	
	
	
	10,000.00
	20,000.00
	20,000.00
	· 
	-
	SWCD
	CA

	Focus Area: Gender Equality
	

	Social Services Delivery 


	Social Welfare and 
Community Services


	95. Organise sensitization programme on the need to involve women in decision making and local governance in 20 communities
	Municipal wide
	
	
	
	
	18,000.00
	7,000.00
	-
	· 
	-
	SW&CD
	CA, 
NGOs

	
	
	96. Organise sensitization programme on Persistent negative discriminatory socio-cultural and customary practices against women
	Bibiani
	
	
	
	
	25,000.00
	10,000.00
	5,000.00
	· 
	-
	SW&CD
	CA, 
NGOs

	
	
	97. Provide educational support to 10 female students pursuing science at the Tertiary level
	Municipal wide
	
	
	
	
	30,000.00
	30,000.00
	-
	· 
	-
	CA
	GES

	
	
	98. Organise skills training and income generating activities for 80 women and groups to improve their economic empowerment
	Municipal
Wide
	
	
	
	
	25,000.00
	10,000.00
	-
	· 
	-
	BAC
	CA

	Focus Area: Sports and Recreation

	Social Services Delivery
	Education, youth &sports and library services
	99. Organise community football galas

	Bibiani
	
	
	
	
	40,000.00
	20,000.00
	-
	· 
	-
	CA
	Community members

	Focus Area: Youth Development

	Social Services Delivery
	Education, youth &sports and library services
	100. Organise capacity building workshops for the youth to orient them on the need to venture into entrepreneurship
	Bibiani
	
	
	
	
	25,000.00
	-
	20,000.00
	· 
	-
	BAC
	CA, Private Sector, NABCO

	Focus Area: Social Protection

	Social Services Delivery
	Welfare and Community Services
	101. Organise radio programme on child right and child protection issue
	Bibiani
	
	
	
	
	12,000.00
	10,000.00
	5,000.00
	· 
	-
	SW&
CD
	CA, MCPC

	Focus Area: Disability-Inclusive Development

	Social Services Delivery
	Welfare and Community Services
	102. Provide medical /assistive devices to PWDs
	Municipal wide
	
	
	
	
	30,000.00
	20,000.00
	-
	· 
	-
	SW&
CD
	CA

	
	
	103. Organise Advocacy & awareness creation on the rights & responsibilities of PWDs
	Bibiani
	
	
	
	
	12,000.00
	20,000.00
	-
	· 
	-
	SW&
CD
	CA

	
	
	104. Provide educational/
apprenticeship support to PWDs
	Municipality-wide
	
	
	
	
	10,000.00
	10,000.00
	-
	· 
	-
	SW&
CD
	CA

	
	
	105. Procure items such as fridges, Tricycles, start-ups etc, to support PWDs to enter into income generation activities 
	Municipal wide
	
	
	
	
	60,000.00
	20,000.00
	-
	· 
	-
	SW&
CD
	CA

	
	
	106. Strengthening organization of Persons with Disability
	Bibiani
	
	
	
	
	18,000.00
	20,000.00
	-
	· 
	-
	SW&
CD
	CA

	Focus Area: Employment and Decent Work

	Social Services Delivery
	Social Welfare and Community Services
	107. Support government flagship programmes such as NABCO &YEA 
	Bibiani
	
	
	
	
	20,000.00
	-
	-
	· 
	-
	 YEA
	CA

	DEVELOPMENT DIMENSION 3: ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENTS

	Focus Area: Protected Areas

	Environmental Management
	Natural Resource Conservation and Management
	108. Facilitate alternative livelihoods including eco-tourism   support schemes for fringe communities along protected areas
	5 Selected Communities
	
	
	
	
	22,000.00
	20,000.00
	10,000.00
	· 
	-
	Forestry
Commission
	CA, Care International

	
	
	109. Sensitization of communities to prevent illegal activities in forest reserves
	Forest Reserves
	
	
	
	
	20,000.00
	30,000.00
	-
	· 
	-
	Forestry
Commission
	Chiefs, CA

	Focus Area: Mineral Extraction

	Environmental Management
	Natural Resource Conservation and Management
	110. Organise sensitization programme on illegal mining, deforestation and land reclamation
	Selected communities
	
	
	
	
	20,000.00
	22,000.00
	-
	· 
	-
	Minerals
Commission
	CA, NGOs, CSO, Chiefs Minerals Commission

	Infrastructure Maintenance

	Infrastructure Development and Management
	Public works, rural housing, and water management
	111. Rehabilitation and Furnishing of Assembly Hall complex
	Bibiani
	
	
	
	
	180,000.00
	-
	-
	· 
	-
	Works
	MLGDRD

	Infrastructure Development and Management
	Public works, rural housing and water management
	112. Rehabilitation of Bibiani and Bekwai Markets
	Bibiani & Bekwai
	
	
	
	
	400,000.00
	-
	-
	· 
	-
	Works
	MLGDRD

	Infrastructure Development and Management
	Public works, rural housing and water management
	113. Rehabilitation of Humijibre Market
	Humijibre
	
	
	
	
	30,000.00
	-
	-
	· 
	-
	Works
	MLGDRD

	Focus Area: Water Resources Management

	Environmental Management
	Natural Resource Conservation and Management
	114. Enforcement of development control on water bodies
	Municipal wide
	
	
	
	
	40,000.00
	30,000.00
	-
	· 
	-
	Forestry
Commission
	CA, NGOs, CSO,Chiefs, Minerals Commission

	Focus Area: Environmental Pollution

	Environmental Management
	Natural Resource Conservation and Management
	115. Enforce environmental laws and regulations to prevent noise and air pollution 
	Municipal Wide
	
	
	
	
	32,000.00
	-
	-
	· 
	-
	EHU
	CA, NGOs, CSO, MWST, 

	
	
	116. Promote the use of LPG as alternative sources of energy by households
	Municipal wide
	
	
	
	
	2,000.00
	-
	2,000.00
	· 
	-
	NADMO
	FC

	Focus Area: Deforestation, Desertification and Soil Erosion

	Environmental Management
	Natural Resource Conservation and Management
	117. Support the planting of 400,000 assorted tree seedlings under the green Ghana project
	Municipal wide
	
	
	
	
	120,000.00
	-
	-
	· 
	-
	Forestry Communities
	NADMO

	
	
	118. Establishment of forest plantations in degraded forest land through Modified Taungya and industrial plantation
	Anhwiaso, Aboduabo
	
	
	
	
	10,000.00
	-
	-
	· 
	-
	Forestry Commission
	CA

	Environmental Management
	Natural Resource Conservation and Mgt.
	119. Support the implementation of youth in afforestation programme
	Municipal wide
	
	
	
	
	-
	
	20,000.00
	· 
	-
	Forestry Commission
	CA

	Focus Area: Climate Variability and Change

	Environmental Management
	Natural Resource Conservation & Management
	120. Train 650 farmers on climate smart agriculture technologies
	Municipal Wide
	
	
	
	
	5,000.00
	30,000.00
	-
	· 
	-
	MDA
	CA, NGOs, CSO,MWST, FC

	
	
	121. Organise sensitization campaigns on climate change variability and adaption in 30 communities 
	Municipal
Wide
	
	
	
	
	15,000.00
	20,000.00
	-
	· 
	-
	NADOM
	CA
NGO’s, FC

	Environmental Management
	Natural Resource Conservation & Mgt
	122. Support the planting of 3,000 assorted tree seedlings 
	Selected towns
	
	
	
	
	2,000.00
	20,000.00
	-
	· 
	-
	NADMO
	CA, NGOs, CSO,
Mineral Commission, FC

	Focus Area: Disaster Management

	Environmental Management
	Disaster Prevention and management
	123. Formation of Disaster Risk Reduction clubs in 20 schools
	Selected Schools
	
	
	
	
	2,000.00
	-
	5,000.00
	· 
	-
	NADMO
	GES

	
	
	124. Organise community sensitization on hazards of fire
	Selected Towns
	
	
	
	
	3,000.00
	-
	3,000.00
	· 
	-
	NADMO
	GNFS, CA

	Environmental Management
	Disaster Prevention and management
	125. Sensitization of the general public on the prevention and management of domestic and bush fires
	Selected Communities
	
	
	
	
	-
	2,000.00
	-
	· 
	-
	GNFS
	CA

	Environmental Management
	Disaster Prevention and management
	126. Training of fuel stations, markets and other public places on management of fire outbreaks
	Selected Communities
	
	
	
	
	-
	2,000.00
	-
	· 
	-
	GNFS
	CA

	Focus Area: Transportation: Road & Road Safety

	Infrastructure Development and Management  
	Urban roads and transport services
	127. Reshape 100km of feeder roads and building of culvert
	Municipal Wide
	
	
	
	
	300,000.00
	100,000.00
	-
	· 
	-
	Works
	CA

	
	
	128. De-silting of 10km of drains, grass cutting and patching of potholes
	Municipality-wide
	
	
	
	
	420,000.00
	-
	-
	· 
	-
	Works
	CA, Urban Roads

	
	
	129. Grading of 5km Town Roads
	Municipality-wide
	
	
	
	
	140,000.00
	-
	-
	· 
	-
	Works
	CA, Urban Roads

	
	
	130. Traffic Management
	Municipality-wide
	
	
	
	
	105,000.00
	-
	-
	· 
	-
	Works
	CA, RSC

	
	Urban roads and transport services
	131. Sensitization on Road Safety policy for drivers and user
	Municipal
Wide
	
	
	
	
	10,000.00
	5,000.00
	-
	· 
	-
	Works
	CA,
NRSC, NCCE

	Focus Area: Information Communication Technology Development

	Infrastructure Development and Management  
	ICT
	132. Organise ICT training for 150 youth
	Municipal
Wide
	
	
	
	
	5,000.00
	15,000.00
	-
	· 
	
	GES
	CA, NGOs

	Focus Area: Human Settlements Development and Housing

	Infrastructure Development and Management  
	Spatial Planning
	133. Continue the street naming and property addressing system
	Anhwiaso, Chirano
	
	
	
	
	100,000.00
	
	100,000.00
	· 
	-
	Physical Planning
	CA, 
TA
.SPC

	
	
	134. Support the extension of electricity in 8 communities in the Municipality
	Atronsu, Asempanaye, Bekwai old clinic, Maakrom,Kramokrom, Surano A Nambro, Kwartengkrom, 
	
	
	
	
	300,000.00
	-
	-
	· 
	-
	Works
	CA,TA 
SPC

	
	
	135. Preparation and revision of local settlement plans
	Sefwi Bekwai, Chirano, Ampenkrom
	
	
	
	
	100,000.00
	-
	-
	· 
	-
	Physical Planning
	CA, TA, 
SPC

	
	
	136. Landscaping and Gardening of principal streets in Bibiani
	Bibiani
	
	
	
	
	5,000.00
	10,000.00
	-
	· 
	-
	Physical Planning
	CA,TA
, SPC

	
	
	137. Undertake building inspections to ensure compliance with the national building code
	Municipal Wide
	
	
	
	
	-
	20,000.00
	-
	· 
	-
	Physical Planning
	CA, TA,
 SPC

	Focus Area: Drainage and Flood Control

	Infrastructure Development and Management  
	Public Works, Rural Housing and Water Management
	138. Construction of 6 No. culverts
	Kofikrom, Chira 
Nzema Nkwanta,Mframakrom, Abokyikrom
	
	
	
	
	40,000.00
	-
	-
	· 
	-
	NADMO
	CA

	DEVELOPMENT DIMENSION 4: GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY

	Focus Area: Local Governance and Decentralization

	Management and Administration
	General Administration
	139. Organize Statutory meetings (Management Meetings, Sub-Committee, Executive Committee & General Assembly Meetings, SAT Meetings etc)
	Bibiani
	
	
	
	
	-
	260,000.00
	-
	· 
	-
	CA
	MLGDRD

	
	
	140. Maintenance of office equipment
	Bibiani
	
	
	
	
	20,000.00
	30,000.00
	-
	· 
	-
	CA
	MLGDRD

	
	
	141. Procurement of 100kva generator for the Assembly and other offices
	Bibiani
	
	
	
	
	100,000.00
	-
	-
	· 
	-
	Works
	CA

	
	
	142. Maintenance of Assembly Vehicles/
General Equipment
	Bibiani
	
	
	
	
	30,000.00
	20,000.00
	-
	· 
	-
	CA
	MLGDRD

	
	
	143. Renovation of 4 Assembly Bungalows & Offices
	Bibiani
	
	
	
	
	50,000.00
	130,000.00
	-
	· 
	-
	CA
	MLGDRD

	
	
	144. Procurement of Office Equipment
/Logistics (6-No servers, 6-No laptops, UPS & Networking Equipment)
	Bibiani
	
	
	
	
	50,000.00
	20,000.00
	-
	· 
	-
	CA
	MLGDRD

	
	
	145. Gazetting of Assembly’s Bye-Laws
	Bibiani
	
	
	
	
	30,000.00
	-
	-
	· 
	-
	CA
	MLGDRD

	Management and Administration
	General Administration
	146. Support to Self Help Community Projects
	Municipal Wide
	
	
	
	
	200,000.00
	100,000.00
	-
	· 
	-
	CA
	MLGDRD

	
	
	147. Support the sub-structures in the Municipality/Construction of 1 No. Zonal Council Office
	Sefwi Bekwai
	
	
	
	
	300,000.00
	-
	-
	· 
	-
	CA
	MLGDRD

	
	
	148. Supply, Installation and maintenance of streetlight and extension of electricity
	Selected communities
	
	
	
	
	150,000.00
	50,000.00
	-
	· 
	-
	Works
	CA

	
	
	149. Support Decentralized Dept. and WNRCC
	Bibiani
	
	
	
	
	50,000.00
	-
	-
	· 
	
	CA
	MLGDRD

	
	
	150. Implement Capacity building plan/Staff development
	Bibiani
	
	
	
	
	50,000.00
	30,000.00
	-
	· 
	-
	HR Dept.
	MLGDRD

	
	
	151. Provision for official day celebrations

	Selected Communities
	
	
	
	
	150,000.00
	-
	-
	· 
	-
	CA
	MLGDRD

	
	
	152. Internal Management of organization (Utility, fuel, call credit, Hotel Accommodation, NALAG Dues etc)
	Bibiani
	
	
	
	
	100,000.00
	100,000.00
	-
	· 
	-
	CA
	MLGDRD

	Focus Area: Public Accountability

	Management and Administration
	Planning, Budgeting,
Monitoring & Evaluation
	153. Organise Social Accountability Fora ie. 2 Town Hall meetings, Meet the Press & Social Audit 
	Bibiani & Bekwai
	
	
	
	
	40,000.00
	10,000,00
	-
	· 
	-
	CA
	MLGDRD

	Focus Area: Human Security and Public Safety

	Management and Administration
	General Administration
	154. Support for Security operations & MUSEC activities
	Bibiani
	
	
	
	
	80,000,00
	20,000.00
	-
	· 
	-
	CA
	MLGDRD

	Focus Area: Corruption and Economic Crimes

	Management and Administration
	General Administration
	155. Support Anti- Corruption Agencies /Implement NACAP 
	Municipal wide
	
	
	
	
	10,000.00
	20,000.00
	-
	· 
	-
	CA
	CHRAJ, Audit Service,
NCCE, NGOs

	DEVELOPMENT DIMENSION 5: EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19 RECOVERY PLAN)

	Focus Area: Hydro meteorological

	Social Services Delivery
	Public Health Services and management
	156. Organize community education programme on hydro meteorological disaster
	Selected Communities
	
	
	
	
	5,000.00
	30,000.00
	-
	· 
	-
	NADMO
	CA

	Focus Area: Biological
	

	Social Services Delivery
	Public Health Services and management
	157. Organise sensitization and education programmes on Covid-19 and other pandemics and enforcement of safety protocols
	Municipal wide
	
	
	
	
	20,000.00
	10,000.00
	-
	· 
	-
	GHS
	CA

	
	
	158. Support Municipal Public Health Emergency Management Committee & Municipal Public Health Emergency Rapid Response Team activities
	Bibiani
	
	
	
	
	20,000.00
	40,000.00
	-
	· 
	-
	GHS
	CA

	
	
	159. Vaccination against public health emergencies such as Covid-19 and other pandemics
	Municipality- wide
	
	
	
	
	10,000.00
	10,000.00
	-
	· 
	-
	GHS
	CA

	Focus Area: Anthropogenic

	Social Services Delivery
	Public Health Services and management
	160. Organise 4 quarterly disaster mitigation and public awareness programmes
	Selected communities
	
	
	
	
	5,000.00
	12,000.00
	-
	· 
	-
	NADMO
	CA

	Relief Assistance and Victim Welfare

	Environmental Management
	Disaster Prevention and management
	161. Support 200 disaster victims with relief items
	Municipal wide
	
	
	
	
	100,000.00
	-
	-
	· 
	-
	NADMO
	CA

	DEVELOPMENT DIMENSION 6: IMPLEMENTATION, COORDINATION, MONITORING AND EVALUATION

	Management and Administration
	Planning, Budgeting, Monitoring & Evaluation
	162. Organize 4 Quarterly MPCU and budget committee meetings
	Bibiani
	
	
	
	
	30,000.00
	10,000.00
	-
	· 
	-
	CA
	MLGDRD

	
	
	163. Preparation of 2024 composite Annual Action Plan and budget 
	Bibiani
	
	
	
	
	25,000.00
	-
	-
	· 
	-
	CA
	MLGDRD

	
	
	164. Conduct projects and programme evaluations and APR preparation sessions for HODs.
	Selected Towns
	
	
	
	
	50,000.00
	30,000.00
	-
	· 
	-
	CA
	MLGDRD

	
	
	165. Dissemination of 2023 approved composite and Gazetting of fee-fixing
	Bibiani
	
	
	
	
	15,000.00
	10,000.00
	-
	· 
	-
	CA
	MLGDRD

	
	
	166. Undertake consultative meetings and prepare 2024 Fee-Fixing Resolutions
	Bibiani
	
	
	
	
	
5,000.00
	20,000.00
	-
	· 
	-
	CA
	MLGDRD

	
	
	167. Undertake Mid-Year Review of the 2023 Composite Budget
	Bibiani
	
	
	
	
	14,000.00
	-
	-
	· 
	-
	CA
	MLGDRD

	Production and Utilization of Statistics

	Management and Administration
	Planning, Budgeting, Monitoring & Evaluation
	168. Conduct monthly market readings at Sefwi Bekwai and Bibiani
	Bekwai & Bibiani
	
	
	
	
	5,000.00
	-
	-
	· 
	-
	Statistics
	CA

	Management and Administration
	Planning, Budgeting, Monitoring & Evaluation
	169.  Build community register in 3 endemic communities of child labour using Ghana Child Labour Monitoring System
	Selected Communities
	
	
	
	
	10,000.00
	-
	-
	· 
	-
	Statistics
	CA

	Total

	
	
	
	
	
	
	
	9,950,372.00
	2,480,000.00
	1,577,000.00
	14,007,372.00
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