REPUBLIC OF GHANA

BIBIANI–ANWHIASO–BEKWAI MUNICIPAL ASSEMBLY

WESTERN NORTH REGION

FINAL 2022-2025 DMTDP

PREPARED BY MPCU

DECEMBER, 2022

# TABLE OF CONTENTS

Contents										               Page

TABLE OF CONTENTS	iii

LIST OF TABLES	v

LIST OF FIGURES	vi

LIST OF ABBREVIATIONS	vii

ACKNOWLEDGEMENT	ix

EXECUTIVE SUMMARY	x

CHAPTER ONE	1

PERFORMANCE REVIEW, ANALYSIS OF CURRENT SITUATION AND DEVELOPMENT ISSUES	1

1.1.	Introduction	1

1.2.	The Municipality’s Vision	1

1.3.	The Assembly’s Mission Statement	1

1.4 Municipal Core Values	1

1.5 The Performance Review of the Municipality in Implementing Programmes and Projects in the 2018-2021 DMTDP under the Agenda for jobs policy	1

1.6 Performance of the Assembly based on outcome indicators	2

1.7 Status of financial Performance from 2018-2021	5

1.8	Lessons Learnt which have Implication for the 2022-2025 DMTDP	6

1.9	Analysis of Existing Conditions of the Municipality	7

1.10 Summary of Key Development Issues of the Agenda for jobs policy (From Performance Review of 2018- 2021 DMTDP	26

CHAPTER TWO	28

KEY DEVELOPMENT PRORITIES	28

2.1.	Introduction	28

2.2 List of prioritized Development issues	28

CHAPTER THREE	31

DEVELOPMENT PROJECTIONS, GOALS, OBJECTIVES AND STRATEGIES	31

3.1.	Introduction	31

3.2.	Development Projections of the District for 2022 -2025	31

3.3 Revenue Projections from 2022-2025	32

3.3 Desired Future Map	35

3.4 Municipal Goals, Objectives and Strategies Linked with Medium-Term National Development Framework (MTNDPF)	38

3.5 Strategic Environmental Assessment (SEA) of MTDP – Compound Matrix Sustainability Tests	48

CHAPTER FOUR	50

COMPOSITE DEVELOPMENT PROGRAMMES	50

4.1.	Introduction	50

4.2	Assumptions and methodologies used for projects costing	50

4.3 Programmes of Action (PoA) for 2022-2025	51

4.4 Indicative Financial Plan (2022-2025)	56

4.5	Maintenance Plan	58

4.6 Spatial Development Framework/Structure Plan	58

CHAPTER FIVE	59

ANNUAL ACTION PLANS FOR 2022-2025	59

5.1 Introduction	59

CHAPTER SIX	138

MONITORING AND EVALUATION ARRANGEMENTS	138

6.1 Introduction	138

6.2 Stakeholders Analysis	138

6.3 Monitoring of Development Programmes/Projects	140

6.4 Development indicators and Targets	140

6.5 Evaluation Arrangements	154

6.6. Participatory Monitoring and Evaluation Arrangements	154

CHAPTER SEVEN	157

COMMUNICATION STRATEGY	157

7.1 Introduction	157

7.2 Strategies	157

7.3 Approaches/Channels for Communication	160

LIST OF APPENDICES	161

Appendix I – Report on Final Public Hearing	161

Appendix II - Assets Maintenance Plan (2022 – 2025)	168

Appendix III - Climate Change Mitigation and Vulnerability Analysis	169

# LIST OF TABLES

Table 1.1 Performance Review of the 2018-20121 DMTDP under “An Agenda for Jobs	3

Table1.2: Financial Performance from 2018-2021	5

Table 1.3 Age Distribution in the Bibiani-Anhwiaso-Bekwai Municipality based on 2021 Population figure	10

Figure 1.5: Population Pyramid of the Bibiani Anhwiaso Bekwai Municipality	11

Table1.4: Forest Reserves in the Municipality	12

Table 1.5: Public Educational Institutions in the Municipality	20

Table 1:6 Categories of Teachers in Public and Private Schools	21

Table 1.7: Health Facility by Provider	22

Table 2.1: Prioritized Development Issues	29

Table 3.1: Projected Total Population and Sex Composition of the Municipality 2022 – 2025	32

Table 3:2 Age Distribution and Projected Population in the Municipality, 2022-2025	32

Table 3.3: Revenue projection from 2022-2025	32

Table 3.4:  Development Projections under the Development Dimensions	33

Table 3.5:  District Goals, Objectives and Strategies Linked With Medium-Term National Development Framework (MTNDPF)	39

Table 4.1 Programme of Action for Bibiani-Anhwiaso-Bekwai Municipal Assembly (2022-2025)	52

Table 4.2 Programme Financing (2022 – 2025)	57

Table 5.1 Annual Action Plan for 2022	60

Table 5.2 Annual Action Plan for 2023	82

Table 5.3 Annual Action Plan for 2024	103

Table 5.4 Annual Action Plan for 2025	121

Table 6.1: Stakeholder Analysis	138

Table 6.2 Monitoring Matrix – Performance of District Core Indicators	141

Table 6.3 Monitoring Matrix – Performance of District Specific Indicators	149

Table 6.4 Summary of Evaluation Matrix	156

Table 7.1 2022 – 2025 DMTDP Communication Strategy Matrix	158

# LIST OF FIGURES

Figure 1.1:  Projects/programmes implementation level under the Development Dimensions	2

Figure 1.2 Proportion of the overall medium-term development plan implemented from 2018-2021	2

Figure1.3: Financial Performance from 2022-2025	6

Figure 1.4: Location of the Municipality with respect to National and Regional Context 		8

Figure 1.5: Population Pyramid of the Bibiani Anhwiaso Bekwai Municipality	11

Figure 1.6 Land Cover of Bibiani Anhwiaso Bekwai Municipal	13

Figure 1.7 Drainage System of Bibiani Anhwiaso Bekwai Municipal	15

Figure 1.8 Zonal Council of Bibiani Anhwiaso Bekwai Municipal	18

Figure 3.1 Proposed Health Facilities Map	35

Figure 3.2 Proposed Education Facilities Map	36

Figure 3.3 Proposed Water Facilities Map	37

# LIST OF ABBREVIATIONS

BABMA  	-  	Bibiani-Anhwiaso-Bekwai Municipal Assembly

BAC     	-  	Business Advisory Centre

CBOs        	-  	Community Based Organisations

CHPS      	-  	Community Based Health Planning and Services

CWSA    	-  	Community Water and Sanitation Agency

DA		-  	District Assembly

DAC		-  	District AIDS Committee

DACF		-      	District Assemblies Common Fund

DFID		-      	Department for International Development

DFR		-      	Department of Feeder Roads

DMTDP	-      	District Medium Term Development Plan

DSW/CDD      -     	District Social Welfare/Community Development Department

EDIF		-      	Export Development and Investment Fund

EPA		-      	Environmental Protection Agency

EHU         	 -     	Environmental Health Unit

EU		-      	European Union

F&A        	-   	Finance and Administration

FAO		-      	Food and Agriculture Organization

FBOs		-      	Farmer Based Organizations

FC              	 -    	Forestry Commission

FIDA		-      	Federation of International Women Lawyers

FM		-      	Frequency Modulation

FOAT/DDF 	 -       	Functional Organisational Assessment Tool/District Development Fund

GARFUND	-      	Ghana AIDs Response Fund

GES		-      	Ghana Education Service

GFS               -      	Ghana Fire Service

GETFund	-      	Ghana Education Trust Fund

GHA		-      	Ghana Highways Authority

GHS                -     	Ghana Health Service

GIZ		-      	German International Cooperation

GSS                -      	Ghana Statistical Service

GoG		-      	Government of Ghana

GPRTU	-      	Ghana Private Road Transport Union

GSGDA         -      	Ghana Shared Growth and Development Agenda

GIZ		-      	German International Co-operation

HIV/AIDS	-      	Human Immunodeficiency Virus

ICT                 -      	Information, Communication and Technology

IGF		-      	Internally Generated Fund

KVIP		-      	Kumasi Ventilated Improved Pit

LEAP        	-      	Livelihood Empowerment against Poverty

LCS          	-      	Local Government Service

LPG            	-      	Liquefied Petroleum Gas

LI		-      	Legislative Instrument

LTNDPF 	-      	Long Term National Development Policy Framework

MA            	-      	Municipal Assembly

MDA              -      	Municipal Director of Agriculture

MFO		-      	Municipal Finance Officer

MCD		-      	Municipal Co-ordinating Director

MCE		-      	Municipal Chief Executive

MHMT	-      	Municipal Health Management Team

MPO		-      	Municipal Planning Officer

MWST	-      	Municipal Water and Sanitation Team

MoC		-      	Ministry of Communication

MoGCSP        -      	Ministry of Gender, Children and Social Protection

MoE	      	 -       	Ministry of Education

MoEST         -        	Ministry of Environment, Science and Technology

MLGRD	-      	Ministry of Local Government, Rural Development

MLNR         	-     	Ministry of Lands and Natural Resources

MoTI        	-      	Ministry of Trade and Industry

MoT           	-      	Ministry of Transport

MoELR	-      	Ministry of Employment and Labour Relation

MoFEP      	-      	Ministry of Finance and Economic Planning

MoFA		-      	Ministry of Food and Agriculture

MoH		-      	Ministry of Health

MPCU        	-     	Municipal Planning Coordinating Unit

M-SHAP	-      	Multi-Sectoral HIV/AIDS Programme

NADMO	-      	National Disaster Management Organization

NBSSI		-      	National Board for Small Scale Industries

NCA		-      	National Communication Authority

NCCE		-      	National Commission for Civil Education

NCWD	-      	National Commission for Women and Development

NDPC		-      	National Development Planning Commission

NMTDPF 	-      	National Medium Term Development Policy Framework

NGOs		-      	Non-Governmental Organizations

NHIS		-      	National Health Insurance Scheme

NYEP		-      	National Youth Employment Programme

OPD		-      	Out -Patient Department

PHC		-      	Primary Health Care or Population and Housing Census

PLWHA	-      	People Living with HIV/AIDS

PM      		-      	Presiding Member

PNDCL	-      	Provisional National Defence Council

POCC		-      	Potential, Opportunities, Constraints and Challenges

PWDs		-      	People with Disabilities

RCC		-      Regional Co-ordinating Council

REP           	-     	Rural Enterprise Programme

SMCs		-      	Schools Management Committees

SHS		-      	Senior High School

SW&CD     	-      	Social Welfare and Community Development

TV		-      	Television

UC            	-      	Unit Committee

UNDP		-      	United Nation Development Programme

UNICEF	-      	United Nations International Children Education Fund

WATSAN	-      	Water and Sanitation Committee

WNRCC     	-      	Western North Regional Coordinating Council

ZC              	-     	Zonal Councils

# ACKNOWLEDGEMENT

An important document like the 2022-2025 DMTDP of the Bibiani-Anhwiaso-Bekwai Municipal Assembly could not have been prepared without the technical and logistical support from the stakeholders or development partners particularly, NDPC and WNRCC. The NDPC in collaboration with WNRCC organized series of workshops for the Assemblies by taking us through all the detailed steps in DMTDP preparation processes to further equip/build the capacity of the Assemblies.

The NDPC after the capacity building training also provided us with the necessary reference materials to enhance easy preparation of the plan.

The Municipal Assembly benefited from development partners like NGOs, Decentralized Departments, CBOs, Assembly sub-structures and communities who also assisted in diverse ways and provided us with the necessary inputs which were imputed into the plan.

The management of the Bibiani-Anhwiaso-Bekwai Municipal Assembly also did well by providing all the necessary financial and logistical support to facilitate the preparation of the document. The efforts and commitment of all MPCU Members specifically the preparation team are also acknowledged.

# EXECUTIVE SUMMARY

Introduction

In fulfilling the planning function of the Assembly, a Plan Preparation Team consisting Municipal Coordinating Director, team of Municipal Development Planners, Physical Planning Officer, Budget Analyst, Internal Auditor and the Works Engineer was formed and tasked to prepare the next Medium Term Development Plan to cover a period 2022 - 2025 and was based on the Medium-Term National Development Policy Framework (MTNDPF 2022-2025) christened “An Agenda for Jobs: Creating Prosperity and Equal Opportunity for All” to replace the first Agenda for Jobs policy II.  The preparation of the MTDP was based on the guidelines prepared by the National Development Planning Commission (NDPC). All the steps provided to guide the process of preparation were followed.

A participatory process was adopted in the preparation, stemming from the fact that the plan preparation team collaborated with other stakeholders’ including heads of departments, agencies, assembly members, chiefs’ opinion leaders, community members, municipal desk officer and other stakeholders for WASH, civic societies, NGOs among others.  This document had the following as the guiding principles especially during the prioritization of issues. The first is that, there should be an impact on a large proportion of the citizenry especially the poor, gender disparities and the vulnerable. The next is the significant linkage effect on meeting basic human needs and rights, and significant multiplier effects on the economy including social and environmental considerations. Equitable distribution of interventions among geographical locations, sustainability and reliable source of funding were also considered in the prioritization process.  It would also help promote WASH in the municipal through adequate interventions through the provision of adequate water and sanitation facilities as well as sensitization on hygiene issues. It is hoped that the current water coverage of 72% would be increased to an appreciable level when all WASH interventions in the plan are fully implemented.

In ensuring a participatory planning process, public engagements were organized for all the Nine Urban/Zonal Councils in the Municipality. They were taken through their Potentials, Opportunities, Constraints and Challenges (POCC) in a participatory manner after which prioritized needs were derived through ranking.  All the 15 main steps in the plan preparation process were followed in preparing a draft plan for 2022 -2025 MTDP. Two major Public forums were organized in the Municipality to solicit the general public inputs and validate the information gathered from the draft plan.

The MTNDPF has Four Broad Goals and their related thematic or development dimensions. The broad goals are; Build Prosperous Society, Create Opportunities for all Ghanaians, Safeguard the natural environment and ensure resilient built environment and maintain a stable, united and safe society. The development dimensions are Economic, Social Development, Environment, Infrastructure and Human Settlements, Governance, Corruption and Public Accountability and Ghana’s Role in International Affairs. However, this plan was prepared based on all the six (6) Development Dimensions of the Medium Term National Development Policy Framework (2022-2025). The total cost in implementing the programmes, projects and activities of the DMTDP within the planned period by the Development Dimensions is Fifty-Five Million, Four Hundred and Two thousand, Three hundred and Ninety- Five Ghana Cedis, Ninety-Seven Pesewas (GH¢ 55,402,395.97).

These amounts have been allocated to tackle the key development needs of the Municipality under the respective six (6) Development Dimensions. The plan has been structured into seven chapters. Chapter one is on performance review, analysis of current situation and development issues. Chapter two is on prioritization of development issues. This is followed by chapter three which focuses on the development goals, objectives and strategies to achieve them. Chapter four is on composite development programmes whiles the fifth chapter is on the annual action plans. The sixth chapter concentrates on Monitoring and Evaluation arrangements and the seventh Chapter focuses on the communication strategies of the plan.

# CHAPTER ONE

# PERFORMANCE REVIEW, ANALYSIS OF CURRENT SITUATION AND DEVELOPMENT ISSUES

## Introduction

Chapter one discusses the status of performance of the Municipality on the implementation of its Medium Term Development Plan (DMTDP) 2018-2021 based on the Medium-Term National Development Policy Framework (MTNDPF 2018-2021) christened “An Agenda for Jobs: Creating Prosperity and Equal Opportunity for All” with respect to outcomes/ impact indicators and financial performance. This chapter also highlights the vision, mission and core values of the Assembly as well as analysis of existing situation (Location and physical characteristics, Demographic characteristics, Social, Economic, Infrastructure, Environment, Governance, Hazards, Disaster and   Security as well as list of development issues in the Municipality.

The Bibiani-Anhwiaso-Bekwai Municipal Assembly was established in 1988 by the Local Government (Bibiani-Anhwiaso-Bekwai District Assembly) (Establishment) Instrument, L.I 1387 under the then Local Government Law, 1988 PNDCL 207 and elevated to Municipal status in 2018 by LI. 2284 and inaugurated on Thursday, 15th March, 2018.

## The Municipality’s Vision

The vision of the Assembly is to be an efficient and effective Municipality with continuous enhanced living standards of its people.

## The Assembly’s Mission Statement

The Municipal Assembly exists ‘to facilitate the overall development of the Municipality by effectively formulating and implementing plans and programmes of the Assembly, Ministries, Departments, Agencies and Non-Governmental Organizations in a participatory manner to improve the quality of life of the people in the Municipality’.

## 1.4 Municipal Core Values

The Bibiani Anhwiaso Bekwai Municipal Assembly cherishes the following values or guiding principles: Professionalism, Client Focus, Transparency, Accountability, and Efficient and Effective use of Resources, Sustainability of developmental gains, Participation and inclusiveness.

## 1.5 The Performance Review of the Municipality in Implementing Programmes and Projects in the 2018-2021 DMTDP under the Agenda for jobs policy

The review was undertaken to determine the extent of implementation of Programmes and projects outlined in the 2018 - 2021 DMTDP. It identifies challenges that militated against the implementation of the plan which would serve as inputs/lessons learnt towards the preparation of 2022-2025 DMTDP under the National Long Term Development (NLTDP) policy framework. The Agenda for Jobs (DMTDP 2018-2021) focused on five (5) development dimensions listed as follows; Economic Development, Social Development, Environment, Infrastructure and Human Settlement, Governance, Corruption and Public Accountability and Strengthening Ghana’s Role in international Affairs. The status of implementation of the 2018-2021 DMTDP is presented in Figure 1.1.

Figure 1.1:  Projects/programmes implementation level under the Development Dimensions

Source: MPCU, 2021

Figure 1.2 Proportion of the overall medium-term development plan implemented from 2018-2021

22%

46%

66.5%

22%

46%

66.5%

Source: MPCU, 2021

From figure 1.2 , it can be found that as at the end of 2021 the overall level of implementation of 2018-2021 DMTDP stood at 66.5% out of the targeted percentage of 75% which was as a result of the Assemblies inability to achieve its revenue target to implement all the projects/programmes  due to delays in the DACF, the Assembly inability to meet its revenue targets as well as the ripple effect of the Covid-19 pandemic which continues to be an albatross on the neck of the Assembly and the country as a whole.

## 1.6 Performance of the Assembly based on outcome indicators

The section analyses the performance of the Bibiani Anhwiaso Bekwai Municipality in implementing programmes and projects under the Agenda for jobs policy (2018-2021) based on a set of indicators and target for the plan period under the various development dimensions which were consistent with the mandate of the Assembly. They include Economic Development, Social Development, Environment, Infrastructure and Human Settlement and Governance, Corruption and Public Accountability. Table 1.1 shows the status of performance with respect to the indicators;

##### Table 1.1 Performance Review of the 2018-20121 DMTDP under “An Agenda for Jobs

| Development Dimension | Indicator |  |  | Baseline 2017 |  | 2018-2021 Medium -Term Target |  | Development Outcomes |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Year |  | D Data |  |
| Economic Development | % change improvement in yield of selected crops and livestock | Maize | 5,695 |  | 70% |  | 2020 |  | 65% |  |
|  |  | Rice | 1,392 |  | 75% |  | 2020 |  | 76% |  |
|  |  | Cassava | 97,889 |  | 70% |  | 2020 |  | 68% |  |
|  |  | Yam | 21,696 |  | 60% |  | 2020 |  | 52% |  |
|  |  | Cocoyam | 32,553 |  | 43% |  | 2020 |  | 38% |  |
|  |  | Plantain | 101,696 |  | 80% |  | 2020 |  | 82% |  |
|  |  | Cattle | 1,725 |  | 50% |  | 2020 |  | 40% |  |
|  |  | Goat | 24,298 |  | 65% |  | 2020 |  | 60% |  |
|  |  | Sheep | 24,153 |  | 60% |  | 2020 |  | 52% |  |
|  |  | Pig | 3,608 |  | 50% |  | 2020 |  | 40% |  |
|  |  | Poultry | 137,536 |  | 55% |  | 2020 |  | 51% |  |
|  | Percentage of arable land under cultivation |  |  | 73% |  | 75% |  | 2020 |  | 75% |  |
|  | Number of new industries established - Agriculture - Industry - Service |  |  | 3 50 27 |  | 25% 52% 10% |  | 2020 2020 2020 |  | 4 80 445 |  |
|  | Number of new jobs created - Agriculture - Industry - Service |  |  | 773 20 125 |  | 80% 90% 60% |  | 2020 2020 2020 |  | 3752 211 315 |  |
|  | Percentage of SMEs adopting improved technology |  |  | 15% |  | 40% |  | 2020 |  | 33% |  |
| Social Development | Net enrolment rate | Kindergarten | 94.2% |  | 96% |  | 2020 |  | 87.7% |  |
|  |  | Primary | 97.9 |  | 98% |  | 2020 |  | 89.7% |  |
|  |  | JHS | 55.2% |  | 60% |  | 2020 |  | 47.7% |  |
|  |  | SHS | 39.2% |  | 45% |  | 2020 |  | 39.4% |  |
|  | Gender Parity Index | Kindergarten | 1.02 |  | 1.00 |  | 2020 |  | 1.02 |  |
|  |  | Primary | 1.00 |  | 1.00 |  | 2020 |  | 1.02 |  |
|  |  | JHS | 0.98 |  | 0.99 |  | 2020 |  | 1.05 |  |
|  |  | SHS | 0.89 |  | 0.94 |  | 2020 |  | 0.90 |  |
|  | Completion rate | Kindergarten | 89.4% |  | 94.4% |  | 2020 |  | 89.4% |  |
|  |  | Primary | 114.7% |  | 100% |  | 2020 |  | 66.4% |  |
|  |  | JHS | 101.6% |  | 100% |  | 2020 |  | 92.9% |  |
|  |  | SHS | 71.6% |  | 90% |  | 2020 |  | 94.1% |  |
|  | BECE pass rate |  |  | 98.1% |  | 99.9% |  | 2020 |  | 99.64 |  |
|  | Percentage of schools benefitting from school feeding |  |  | 38.2% |  | 55% |  | 2020 |  | 53.1% |  |
|  | Doctor to population ratio |  |  | 1:38,412 |  | 1:15,000 |  | 2020 |  | 1:13,709 |  |
|  | Percentage of population with improved access to health care |  |  | 87% |  | 92% |  | 2020 |  | 91% |  |
|  | Maternal mortality ratio (Institutional) |  |  | 61:100,000 |  | 25/100,000LB |  | 2020 |  | 18/100,000LB |  |
|  | Malaria case fatality (Institutional) |  |  | 4 |  | 0 |  | 2020 |  | 0 |  |
|  | HIV prevalence rate |  |  | 2.7 |  | 2.00 |  | 2020 |  | 3.8 |  |
|  | Modern Contraceptive use |  |  | 26.8 |  |  |  |  |  | 15,100 |  |
|  | Under-five mortality ratio (number of deaths due to pregnancy and childbirth /1000 live births) |  |  | 0.40/1000 |  |  |  | 2020 |  | 4/1000 LB |  |
|  | The proportion of the population with a valid NHIS card |  |  | 54% |  | 70% |  | 2020 |  | 62.6% |  |
|  | Percentage of population with sustainable access to safe drinking water source | District | 68% |  | 90% |  | 2020 |  | 72% |  |
|  |  | Urban | 36% |  | 56% |  | 2020 |  | 42% |  |
|  |  | Rural | 32% |  | 34% |  | 2020 |  | 30% |  |
|  | The proportion of population with access to improved sanitation services (flushed toilets, KVIP, household latrine) | District | 70% |  | 88% |  | 2020 |  | 77 |  |
|  |  | Urban | 62% |  | 92% |  | 2020 |  | 78 |  |
|  |  | Rural | 44% |  | 76% |  | 2020 |  | 66 |  |
|  | Percentage of the road network in good condition | Total | 70% |  | 85% |  | 2020 |  | 83% |  |
|  |  | Urban | 90% |  | 90% |  | 2020 |  | 92% |  |
|  |  | Feeder | 50% |  | 80% |  | 2020 |  | 74% |  |
|  | Percentage of communities covered by electricity | Total | 72% |  | 92% |  | 2020 |  | 93% |  |
|  |  | Rural | 56% |  | 90% |  | 2020 |  | 82% |  |
|  |  | Urban | 90% |  | 96% |  | 2020 |  | 98% |  |
|  | Percentage change in income levels of PWDs |  |  | 16% |  | 40% |  | 2020 |  | 32% |  |
|  | Incidence of child labour |  |  | 85% |  | 60% |  | 2020 |  | 50% |  |
|  | Percentage change in reported case of abuse |  |  | 35% |  | 20% |  | 2020 |  | 30% |  |
| Environment, Infrastructure and Human Settlement | Percentage change in the activities of illegal chainsaw operation |  |  | 80% |  | 60% |  | 2020 |  | 71% |  |
|  | Percentage of road network in good condition |  |  | 70% |  | 90% |  | 88% |  | 83% |  |
|  | Percentage coverage of street naming and property addressing |  |  | 10% |  | 40% |  | 2020 |  | 35% |  |
| Governance, Corruption and Public Accountability | Police citizen ratio |  |  | 1:1,019 |  | 1:850 |  | 2020 |  | 1:905 |  |
|  | Percentage change of DMTDP implemented |  |  | 78.6% |  | 90% |  | 2020 |  | 66.5% |  |
|  | Percentage of Assembly’s Sub-structures functioning |  |  | 70% |  | 100% |  | 2020 |  | 100% |  |

## 1.7 Status of financial Performance from 2018-2021

A good plan is meaningless unless it is translated into fiscal implementation. This means that the amount of revenue (funds) that are generated both internally and externally and its expenditure patterns are critical in the development of any Municipality. Based on this important assumption the Bibiani-Anhwiaso-Bekwai Municipal Assembly in partnership with its development partners marshalled all efforts to mobilise adequate resources to finance its development programmes/projects within the last four years (2018-2021).

##### Table1.2: Financial Performance from 2018-2021

| Source of Funds | Total Estimated Cost of Plan (A) | Total Amount Received (B) | Variance (A-B) |
| --- | --- | --- | --- |
| IGF | 6,615,618.00 | 5,150,944.02 | 1,464,673.98 |
| DACF | 10,268,365.04 | 4,969,674.81 | 5,298,690.23 |
| MP’s CF | 1,104,080.02 | 1,152,043.21 | -47,963.19 |
| PWDs CF | 527,629.00 | 559,879.65 | -32,187.65 |
| MSHAP | 0.00 | 0.00 | 0.00 |
| DDF/DACF/RFG | 4,201,005.10 | 2,462,891.26 | 1,738,113.84 |
| MAG | 467,922.76 | 456,052.92 | 11,869.84 |
| EU | 3,590,272.00 | 1,893,855.00 | 1,696,417.00 |
| COVID-19 | 0.00 | 0.00 | 0.00 |
| MDF | 5,565,602.22 | 3,284,970.00 | 2,280,632.22 |
| GOG | 7,571,337.82 | 6,133,822.12 | 1,437,515.70 |
| SLR | 2,167,600.00 | 2,460,094.00 | -292,494.00 |
| OTHERS | 0.00 | 0.00 | 0.00 |
| Total | 42,079,431.96 | 28,524,226.99 | 13,555,204.97 |

A critical review of the total estimated cost of plan generated both locally and externally vis-a-vis the total amount received indicates that the income realised within the last plan period was not adequate to implement all programmes and projects. For instance, out of the total estimated income of Ghc42, 079,431.96, the Assembly was able to mobilise/receive GH¢ 28,524,226.99 representing a short fall of 32.2%. The trend is that there has been consistent fall in the Assembly’s revenue projections or planned as against the actual received from 2018 to 2021 as indicated in Table 1.2

The implication of this is that expenditure patterns are negatively affected as most development programme/projects cannot be executed and those that will be implemented may be unduly delayed or not be completed at all to improve the lives of the people. It is important that adequate resources are mobilised in the next plan period (2022-2025) to implement almost all the programmes/projects earmarked in the plan.

Figure1.3: Financial Performance from 2022-2025

Source: MPCU, 2021

## Lessons Learnt which have Implication for the 2022-2025 DMTDP

Some key lessons / experiences the district learnt / gathered during the execution of the 2018 - 2021 DMTDP which may have possible development implications for the 2022-2025 DMTDP include the following:

- Effective involvement / participation of communities, Private Sector, NGOs Donors, Decentralized Departments and other stakeholders in the implementation process was key.

- Low commitment of some communities towards projects implementation in communities.

- Targets set for certain projects were too high and unattainable during the plan period.

- Targets set for certain objectives were too high and unattainable during the plan period.

- Effective collaboration / partnership between the Assembly and other development partners, other Agencies, Donors, NGOs, CBOs and other stakeholders is key in service provision.

- M & E of projects was crucial in the successful implementation of the plan.

- Low income among the people and some peoples’ bad attitude towards payment of taxes affected revenue generation.

- De-politicization of local economic development programmes makes it more sustainable

- The multiplier effects of some projects during planed period were great.

- Poor/inadequate basic infrastructure facilities e.g. Roads badly affected the smooth implementation of the plan.

- Community needs and aspirations were too much for the available resources to meet.

- Data is Key to Revenue Mobilisation and there is the Need to Invest in Data Collection by the Assemblies

- Regular Stakeholders meeting improved service delivery

## Analysis of Existing Conditions of the Municipality

Analyses of existing conditions are essential elements or factors for determining socio-economic development of the Municipality.  This stems from the fact that apart from being potential resources, they also serve as framework within which all development activities take place.  The major factors that need critical analysis, and their implications for development in the Municipality include location and size, demographic characteristics, social, economic, infrastructure, environment, governance, hazard, disaster and security etc. The interaction between the human and physical environment and its development implications with respect to the above major factors are clearly and briefly described below.

1.9.1 Location and Size

The Bibiani- Anhwiaso-Bekwai Municipality is one of the Nine Municipal and District Assemblies (MDAs) in the Western North Region. The Municipality is located between latitude 6° N and 3° N and longitude 2° W, 3° W. The Municipality is bounded on the North by the Atwima Mponua District in the Ashanti Region, South by the Wassa Amenfi West in the Western Region, West by the Sefwi Wiawso Municipal Assembly in the Western North Region and East by the Upper Denkyira West and Amansie West in the Central Region and Ashanti region respectively. The Municipal capital, Bibiani is located 76km to Sefwi Wiawso, the Western North Regional capital and 88km to Kumasi, the nearest commercial centre.

The Municipality covers a total land area of 873 km square and there are at least 345 communities with about 124 having a population above 500 persons (2010 Population and Housing Census) making the Municipality predominately rural. The Municipality’s proximity to large commercial centre such as Kumasi coupled with good roads, makes it attractive in doing business. As a result, the municipality experiences very good market days for food stuff especially among subsistence farmers who dominate the population.

Figure 1.4: Location of the Municipality with respect to National and Regional Context

Source: BABMA, MPCU, 2021                                                                            Source: BABMA, MPCU, 2021

1.9.2 Demographic Characteristics

Development planning as a human centred activity seeks to ensure provision of services to meet the needs of the people.  Population analysis is therefore one of the cardinal components, which helps to determine the direction of the Planning Processes. The analysis of the demographic characteristics of the municipality focuses on thematic areas such as; Population size and growth rate, Age and sex distribution, Population structure and density, Dependency ratio and Migration.

- Population Size and growth rate

The 2021 Population and Housing Census (PHC) put the Municipal population 167,971which is made up of 82,798 males and 85,173 females, with a population growth rate of 1.8% with others factors affecting population changes held constant.

- Age and sex distribution

The age distribution of the Municipality is skewed towards the age groups of 0-14 and 15-64 as shown in Table 1.3: The age variation implies that the Municipality is endowed with a potential labour force and vibrant youth, which are necessary for any development-oriented society.

##### Table 1.3 Age Distribution in the Bibiani-Anhwiaso-Bekwai Municipality based on 2021 Population figure

| Age Group | Both Sexes |  |  | Type of locality |  |
| --- | --- | --- | --- | --- | --- |
|  | Total | Male | Female | Urban | Rural |
| All Ages | 167,971 | 82,798 | 85,173 | 70,083 | 97,888 |
| 0-14 | 66,852 | 32,958 | 33,894 | 27,877 | 38,975 |
| 15-64 | 93,560 | 46,125 | 47,435 | 39,015 | 54,545 |
| 65+ | 7,559 | 3,727 | 3,832 | 3,152 | 4,407 |
| Total Dependency Ratio | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 |
| Child Dependency | 71.5 | 71.4 | 71.4 | 71.4 | 71.4 |
| Old Age Dependency | 8.1 | 8.1 | 8.1 | 8.1 | 8.1 |

Source: MPCU, 2021

The sex composition of the municipality shows that the percentage of the female population is more than the male population. Although the sex distribution is almost at par, issues of female participation in local governance, formal education and other decision-making processes remain a challenge to the Bibiani-Anhwiaso-Bekwai Municipal Assembly.

iii.	Dependency ratio

The total dependency ratio of the municipality is 79.5% according to the 2021 PHC. While considering the fact that a large proportion of persons aged 15-64 is either unemployed or not economically active, it should also be noted the actual burden on the employed in the municipal would also be more serious, leading to a low standard of living. A high dependency ratio indicates that the economically active population and the overall economy face a greater burden to support and provide essential services needed by children and by older persons who are often economically dependent. The rural-urban variations show that whilst rural areas have a ratio of 79.5% the urban areas have also have a dependency ratio of same. It is therefore imperative to ensure access to basic services, such as education and health in order to promote the economic security of children and older persons.

Using the Municipality’s projected population of 181,234 for 2025 based on the 2021 PHC figure of 167,971 and all the factors that influence population change held constant, the structure of the population or population pyramid is illustrated in Figure 1.1 even though with an increase in the population, the structure is expected to change a little.

Figure 1.5: Population Pyramid of the Bibiani Anhwiaso Bekwai Municipality

Source: MPCU Construct based on 2021 PHC

From Figure 1.1, the working population group is larger than the combined child and aged population of the district. This active age group if given enough capacity building can be an instrument of development to the economy of the Municipality.

- Population distribution and density

The population in the municipality is not evenly distributed largely due to geophysical and statutory reasons. This phenomenon has implication for provision of social services and infrastructure. The higher percentage of the population concentrated along the main highway will improve the residents’ accessibility to health facilities mostly clustered along the Bibiani main highway. The 2021 Population and Housing census put municipal population density to about 192.4 persons per square kilometre, which is higher than the national averages of 129.3 and the Regional average of about 87.4 persons per square kilometre respectively.

- Migration

The Municipality is noted for its cocoa cultivation and that coupled with the mineral deposit serves as a pull factor in drawing people from all parts of Ghana and some beyond the borders of Ghana to work in the cocoa farms and the mining sector. However, the situation if not controlled can adversely affect the existing social amenities in the municipality and other increased social vices that is always associated with migration.

1.8.3 Environment

i. Vegetation

The Municipality’s vegetation is of the moist semi-deciduous (equatorial rain forest) type.  The Municipality has a forest District and manages eight (8) gazetted forest reserves with a total area of 401.974 sq.km. forest vegetation is made up of many different tree species including wawa (Triplochiton selerexylon), mahogany (Khaya invorensis), esa (Celtis), ofram (Terminalia superba), edinam (Entandro phragma ivorensio), onyina (Ceiba petandra), kyenkyen (Antiaris Africana) and odum (Milicia exelsa), Sapele etc. Hence, the Municipality is a suitable location for the establishment of timber firms. There are eight forest reserves located within the boundaries of the Municipality as   indicated in Table 1.4.

##### Table1.4: Forest Reserves in the Municipality

| Location | Area (sq.km) | Status |
| --- | --- | --- |
| Anhwiaso East | 121.334 | Production |
| Anhwiaso North | 14.61 | Production |
| Anhwiaso South | 22.020 | Production |
| Afao Hills | 35.820 | Production |
| Tano Suraw Extension | 75.080 | Production |
| Sumtwitwi | 3.620 | Production |
| Tano Suraw | 29.420 | Production |
| Upper Wassaw | 100.08 | Production |
| Total | 401.974 |  |

Source: BABMA, Forest Services Division, Bibiani, 2021

The eight forest reserves are productive reserves where timber harvesting is done of which eighteen Timber Contractors have registered to harvest both natural and plantation timber. Occasional bushfires, overexploitation and encroachment of land are threatening the existence of the reserves. The Municipality has large tracts of forest and economic trees. However, the high exploitation of timber for logs and lumber by both registered timber firms and illegal chainsaw operators has contributed significantly to deforestation in the municipality. Unchecked farming practices including cocoa farming has also compounded the situation through encroachment on the virgin forest and forest reserves. The heavily dependent of the people on firewood and charcoal for energy has seriously affected both secondary and virgin forests in the Municipality. This situation has serious implications such as threat to livelihood, soil degradation, forest depletion, adverse climatic conditions and endangered species in the Municipality.

Figure 1.6 Land Cover of Bibiani Anhwiaso Bekwai Municipal

II. Relief and Drainage

The Municipality forms part of the country’s dissected plateau. The lowest and the highest points in the district are 350m and 660m above sea levels respectively. This highest point is also the highest in the Western Region at Attanyamekrom (Adiembra), near Sefwi Bekwai.  A gently rolling landscape is found over lower Birimian rocks. Over the Tarkwaian rocks, the topography is rugged and hilly rather than smooth and flat or gently undulating.

The Municipality is also endowed with a number of rivers and streams, the most important of which is the Ankobra River.  The streams and rivers exhibit a dendritic pattern, which forms the Ankobra basin. Other forming tributaries are Awa, Krodua, Atronsu, Subriso, Kroseini, Suraw, Chira and Akataso.

The relief and drainage systems favour the development of fish farming, and cultivation of valley bottom rice, sugarcane and dry season vegetables. The rivers can also be taped as resources for future establishment of irrigation schemes and production of potable water for the people in the district. Due to the relatively low level of relief in the district, road construction is less difficult and expensive. However, the presence of many rivers and streams in the district also makes road construction at times very difficult and expensive. Figure 1.3 indicates the drainage system or map of the Municipality.

Figure 1.7 Drainage System of Bibiani Anhwiaso Bekwai Municipal

- Geology and Minerals

The geology for the Municipality is dominated by the Precambrian Metamorphic rocks of the Birrimian and Tarkwain formation which contains the mineral bearing rocks. There are also granite rocks and deposit of minerals such as gold and bauxite. The Oxysols soils are rich in mineral deposits making mining the most important and lucrative economic activity in the Municipality. The companies dealing in mining include; Mensin Gold Limited at Bibiani; Chirano Gold Limited at Chirano and Bossai Minerals Limited at Awaso. The presence of mineral deposits in the Municipality helps to generate royalties as revenue to the Municipal Assembly for development as well as create employment for the inhabitants. It also implies that there is an influx of people to the Municipality by the operations of the mining and social implications.

iii. Soil

The Municipality is endowed with rich forest ochrosols and oxysols which support the cultivation of a wide variety of crops including cocoa, coffee, oil palm, plantain, cocoyam and cassava, etc. and other vegetables. It also makes the Municipality have a comparative advantage in agriculture and agro-processing.

iv. Pollution

Air pollution is also one of the environmental problems cause by the use of energy sources in the Municipality which comes from the mining activities, information centres/sales vans and fume from vehicles.

v. Climate

The Municipality is located in the equatorial climate with the annual rainfall average between 1200mm and 1500mm.The pattern is bimodal, falling between March - August and September- October.  The dry season is noticeable between November - January. The peak periods for rainfall in the district are June and October. The average temperature throughout the year is about 26°c.There is a high relative humidity averaging between 75% in the afternoon and 95% in the night and early morning. The implication of the climate of the Municipality is that it is suitable for the growing of various crops particularly both cash and food crops. This is the reason why the district is one of the leading producers of the cash crop like cocoa in Ghana. The good climatic condition provides suitable water table which is good in potable water (boreholes and hand-dug wells) provision in the Municipality.

vi. Natural and Man-made Disasters

Apart from torrential rainfalls which causes flooding in some areas such as Bekwai, Kofikrom and Bibiani, pest insect infestation such as armyworm infestation and occasional bush / domestic fires sometimes cause extensive destruction to forest reserves, crops and properties in the Municipality.

1.8.4 Governance

The Municipal Assembly sees good governance as one of the cornerstones of development in the district. The various administrative structures of enhancing governance and ensuring citizen participation in the development process in the BABMA includes the Municipal Assembly, Decentralised Departments, Zonal Councils and Unit Committees and Traditional Authority. All stakeholders are given opportunity to participate in decision making processes of the Assembly including the vulnerable and marginalized. However, women participation in decision making is very low as only 0ne (1) out of the 36 elected Assembly members is a woman.

i. The Municipal Assembly

According to the second schedule, section 78 of the Act 936, the Municipal Assembly is composed of the Central Administration Department and Decentralized Departments. The Central Administration Department is composed of the Municipality Chief Executive, the Municipal Co-ordinating Director, the Planning Officer, the Budget Officer, Executive Officer, etc. There is also the General Assembly, which includes the Presiding Member, the Member of Parliament, the Municipal Chief Executive, and the Assembly members. The Municipal Assembly is also constituted into sub-committees and the Executive Committee. There are fifty-two Assembly members made up of thirty-six (36) elected members and sixteen (16) government appointees excluding Member of Parliament and District Chief Executive. However, women participation in governance in the municipality is very low as only one (1) out of the thirty-six (36) elected Assembly members is a woman.

ii. Sub-District Structures

The Municipal Assembly has nine (9) zonal Councils namely; Bibiani Town Council and Sefwi Bekwai, Humjibre, Awaso, Subri, Wenchi, Anhwiaso, Asawinso, Lineso zonal Councils through which devolution of authority is exercised from the Municipal level. Under the zonal Councils are 36 Electoral Areas and 36 Unit Committees at the various community levels for effective decision making. Internal feedbacks from these levels are sent to the Municipal level for harmonisation and decision making. The Zonal Councils and Unit Committees in the Municipality are bedevilled with inadequate funds and logistics, lack of office accommodation, capacity constraints, lack of remuneration and lack of commitment from community members. The Sub-District Structures going forward have to be supported in building their capacities in planning and budgeting, and local resource identification and effective strategies for revenue mobilisation.

Figure 1.8 Zonal Council of Bibiani Anhwiaso Bekwai Municipal

iii. Traditional Authority

The Municipality has 3 paramountcy’s comprising of Anhwiaso, Sefwi Bekwai and Chirano respectively. The traditional rulers in the Municipality play a pivotal role in the governance of the people and management of natural resources. The Municipal Assembly (MA) considers them as effective development partners and for that matter; they are always drawn to partake in any development-oriented activity. There exists a cordial working relationship among the existing traditional council which is a prerequisite for effective good governance.

iv. Security

Peace and stability emanate from a well-co-ordinated and effective security apparatus in every society. The Municipality is fortunate to have access to the Police Service, Immigration Service, Ghana National Fire Service, National Ambulance Service and BNI whose mandate are to enforce peace and order in a democratic dispensation. Armed robbery is not too rampant but the Municipality occasionally records some cases. There are also pockets of chieftaincy disputes in the Municipality which sometimes works against the peace and development.

1.8.5 Economy of the Municipality

The Bibiani-Anhwiaso-Bekwai Municipality is predominately an agrarian economy with minimal activities of secondary and tertiary sectors.  Agriculture employs about 76% of the total labour force or the population. Agriculture is rain fed and characterised by the use of outmoded farm implements and cultural practices. However, the Municipality has high potential for agro-processing, which is yet to be tapped.  The Municipality’s economy is described in terms of structure, Major Economic Activities, Services, Revenue and Expenditure Status, Revenue Base, Economic Resources, Inter/Intra-Trade, Economically Active Population/ Labour Force, etc.

i. Structure of Local Economy

This section of the plan looks at the structure of the economy with respect to the performance of the various sectors namely agriculture, industry and the services in terms of employment and contribution to household income. As stated earlier, the structure of the local economy is skewed towards agriculture, which employs about 76% of the district’s working population with 55.3% female participation. Next to agriculture is the service sector which employs about 15%. The industrial sector, which is dominated by small-scale industries follows the service sector in term of the working class also employs about 9.0%. Although the Municipality has great potential in agro-processing, the weak nature of its industrial sector remains a constraint to ensure balanced development to create jobs for the teaming youth.

ii. Types of Industries

The major types of industries found in the district are agro-processing, manufacturing and mining mainly undertaken by Mensin Gold Mines Bibiani Limited at Bibiani, Chirano Gold Company Limited at Chirano and Bauxite mining at Awaso by the Ghana Bauxite Company Limited. Out of the categories of manufacturing industries, only small-scale industries exist in the municipality. These range from carpentry and joinery, Jewellery, pottery metal smelting, palm and oil extraction, automobile fitting, refrigeration repair, cassava processing, cereal milling, bakery, shoe making, local gin (akpeteshie) distilling, tie and dye and batik making, to fuel dispensing.

a. Commerce

This sub-sector provides employment for a considerable number of people in the municipality. The major items of trade are agricultural products and inputs, orthodox and herbal drugs, auto-parts, clothing, provisions and petroleum and plastic products. Women dominate the commerce sub-sector in the municipality.  However, their contribution to the local economy is not much felt due to the small nature of their businesses (petty trading).

The Municipality has two major market centres located at Bibiani and Sefwi Bekwai and a minor one at Pataboso Junction. The markets do not have adequate essential structures such as stores/stalls, places of convenience and sanitary equipment.

b. Tourism

Bibiani-Anhwiaso-Bekwai Municipality possesses a wide range of natural and built attractive features. The major tourist sites include: Natural Forest Reserves ideal for Eco-Tourism at Bonkaso, Kanayerebo and Tano-Surano, Atta Nyamekrom Mountain at 660 metres, the highest peak in the Western North Region, mining sites at Bibiani and Awaso and Chirano, Traditional “Allue” Festival, Bibiani 6th March Festival and Lake Amponsah, Artificial lake. However, these sites have not been developed to boost the local economy. It is anticipated that with the right partnership, investments and support, the local tourism sector can boost employment creation, drive and help local economic growth.

c. Internally Generated Fund

A critical look at the revenue base of the BABMA reveal that the Assembly relies heavily on government grants, comprising Local Government Grants, Central Government Grants, Ceded Revenue and District Assembly Common Fund and sometimes Donor support.  The Municipality’s Assembly’s internally generated revenue is low and steps must be taken to improve the IGF to meet community needs.

1.8.6 Social Services

Social services of the district include education, health care, housing, water and sanitation etc. which are necessities of human life.

i. Education

The Educational Directorate of the Bibiani-Anhwiaso-Bekwai District which is divided into a number of Educational Circuits, runs 277 public and 196 private schools for an efficient and effective management of educational institutions of the Municipality. Table 1.5 presents public and private educational institutions in the district.

##### Table 1.5: Public Educational Institutions in the Municipality

| Institution | Public | Private |
| --- | --- | --- |
| Nursery | 0 | 48 |
| Pre-school | 101 | 52 |
| Primary School | 101 | 52 |
| Junior Secondary School | 74 | 43 |
| Senior Secondary School | 4 | 1 |
| Nursing Training College | 1 | 0 |
| Total | 277 | 196 |

Source: Municipal Education Directorate, BABMA, 2021.

a. School Enrolment

The district has an encouraging enrolment figure as most of the schools have over three hundred (300) pupils due largely to good government policies and programmes such as School Feeding Programme, Free School Uniforms and Exercise Books, Capitation Grant and the Municipal Assembly’s commitment to provide adequate school infrastructure. There are 51,560 pupils (25,366 males and 26,194 females) in the basic schools. However, some of the pupils walk about 4km to access education at the primary and JHS level.

b. School Infrastructure

Generally, school infrastructure or facilities in the Municipality are quite adequate in terms of numbers and quality. However, the situation in the Senior High Schools as well as some primary and JHS are not all that good. The schools have inadequate classrooms, hostels, library facilities, and logistics. Teacher accommodation in the district is a major problem in the communities as greater number of teachers in basic schools lack good accommodation. Many teachers, therefore, have to travel or walk long distances to schools from nearby towns.

c. Teacher/ Staffing Situation

The percentage of trained teachers in the public schools stands at 93% and that of private schools also stands at 15%.the is encouraging in the public schools but bad in the private schools.  Generally, the staffing situation can be described as good in terms of both quality and quantity.

The general good staffing situation in the Municipality could be attributed to the location of district and some level of good infrastructure particularly the good highway linking Kumasi. However, there is also lack of incentive packages to motivate teachers to accept posting to the district particularly rural areas. The details of staffing situation are provided in Tables 1.6.

##### Table 1:6 Categories of Teachers in Public and Private Schools

| Types of Teachers | Public Schools |  | Private Schools |  |
| --- | --- | --- | --- | --- |
|  | Number | Percent (%) | Number | Percent (%) |
| Trained | 1498 | 93 | 123 | 15 |
| Untrained | 115 | 7 | 686 | 85 |
| Total | 1,613 | 100 | 809 | 100 |

Source: Municipal Education Directorate, BABMA, 2021.

d. Community Participation and Involvement in Education

Generally, most of the Parent -Teacher Associations and School Management Committees in the district are not active and supportive. As a result, community participation in educational delivery at the local level is not the best in most communities. There is some form of apathy on the part of community members towards the execution of school programmes. Most parents do not provide their wards with basic school needs such as uniforms, stationery, footwear, and school bags. However, community participation in school management in general is not bad but can be improved to enhance implementation

ii. Health

Even though the health sector is under the direct management of the DHMT, other stakeholders from the public, private, Christian Health Association of Ghana (CHAG), NGOs and the mining companies have over the years contributed in diverse ways to the improvement of the health of the populace by providing out-patient, in-patient and outreach services to the people in the municipality. Looking at the health facilities with respect to the population of the municipality it is recommended that additional health facilities are built to improve access to health care delivery. The category and ownership of health facilities providing health services as well as spatial distribution in the municipality are as shown in Table 1.

##### Table 1.7: Health Facility by Provider

| Categories | Public | Private | Mining | CHAG | Sub-Total |
| --- | --- | --- | --- | --- | --- |
| Hospital | 1 | 5 | 2 | 0 | 8 |
| Health Centre | 3 | 1 | 0 | 0 | 4 |
| Clinics | 0 | 2 | 1 | 1 | 4 |
| CHPS with Compound | 24 | 0 | 0 | 0 | 24 |
| CHPS Without Compound | 25 | 0 | 0 | 0 | 25 |
| Total | 53 | 8 | 3 | 1 | 65 |

Source: Municipal Health Directorate, 2020

a. Incidence of Diseases

With the exception of malaria, upper respiratory tract infection, etc which threatens the health of the people and causing hospital admission and possibly death, the general population/inhabitants of the district are relatively healthy as portrayed by the number of reported cases of top ten diseases above which is very significant for increased productivity and production in the Municipality. Like in the country, malaria is the number one cause of morbidity in the Municipality.

b. Accessibility to Services

The surface accessibility is the ease with which one travels/moves from a given location to another location (s) within the Municipality in order to access a given/available facility (s) or service (s). This is measured in terms of the time spent in travelling between the two locations (travel time), which in turn depends on distance, means of transport and the route conditions.

The general accessibility to facilities or services particularly hospital, health centres, secondary school, weekly markets, banks, courts, extension services in the district can be described as good.  This is because the Municipality is one of the districts in the country which has one good highway but poor conditions of feeder roads as a result of heavy rainfall and untarred nature of the roads.

iii. Nutrition

The incidence of nutrition and malnutrition is a major public health and developmental concern in the Municipality. The nature of malnutrition cases reflects from patient’s levels of poverty, maternal education, health care, family planning and socioeconomic inequality and disparities. The Municipality has records of acute cases of malnutrition especially among under five infants and adults though there is increasing trend in dietary related non communicable diseases like Type 2 diabetes, obesity, metabolic syndrome etc. Although there is acute malnutrition among under five infants, the prevalence of stunting and underweight is seen significantly among children of teenage mothers and some adult mothers.

These cases and prevalence of malnutrition in the Municipality are resulting from factors of maternal age, hygiene practices of mothers, sanitation factors, and source of drinking water, recent medical history of diarrhoea and respiratory tract infections and lack of education.

In stemming the trend of malnutrition in the Municipality, efforts must be focused on the nutritional education on infants, proper feeding practices, restructuring of the Community, Management of Acute Malnutrition through the CHPS, building of capacity of service providers, and nutritional counselling to improve knowledge and skills in management of incidence of malnutrition.

iv. Child Protection

The incidence of child labour and protection, and related issues in the Municipality over the year has gained much interest of stakeholders.  The Municipal Child Protection Committee reports indicate a significant reduction of Child labour and protection incidence of 2017 value of 85% to 50% in 2020 due to increased awareness through sensitization in committees. The Family Tribunal and the Department of Social Development as well as Domestic Violence and Victim Support Unit (DOVVSU) indicates Child Protection Violations such as neglect, physical abuse, sexual abuse (rape and defilement), child labour, child exploitation, teenage pregnancy and school drop outs are rife in the Municipality. These incidences are characterised by children of school going ages been used as farm hands in cocoa farms during off school hours, child performing hazardous activities, children who have dropped out of school before ending basic education due to lack of economic support by parents and death in the family, and children involvement in gold mining (galamsey) and sexual exploitation of children by grownups especially defilement and rape.

The Municipal Assembly’s plan going forward is to embark on a comprehensive Child Protection programme through intensive sensitization of the general public and formation of Community Child Protection Committee in other communities and also strengthen existing once, and encourage victims to report cases to the police. The Assembly also will ensure that adequate school infrastructure is provided to cater for the increasing number of children who are back to school as a result of this programme and support parents in income generating activities in the next plan period. The Assembly will leverage on support from its Development Partners such as UNICEF, Cocoa Initiative, Jica, Care International etc. to reduce child abuse cases as well as erasing the bad image created by child protection violations under the economic activities in the Municipality.

v. HIV & AIDS

The Municipality being a mining area is bedevilled with high case and prevalence of Hiv/Aids and Sexually Transmitted Diseases though there exist sensitization, counselling and testing, training of peer educators, stigma reduction and support to PLHIVs association in the Municipality. For the plan period from 2017-2020, baseline HIV/AIDS prevalence of 2017 was 2.7% which rose to 3.8% in 2020. The Assembly made serious efforts to reduce the impact of HIV&AIDS on the infected and affected through free NHIS registration and ART for PLHIVs but the case keeps increasing.

The HIV & AIDS disease has become the worry for all stakeholders in the country and the Municipality is no exemption. Vibrant commercial activities in the Municipality involving; Mining (gold), Cocoa farming activities and two active markets coupled with the elevation with influx of migrants and closeness to Kumasi are major risk factors for the Municipality.

The Municipal Assembly and the Ghana AIDs Commission through the Municipal Health Directorate are showing much dedication in terms of provision of resources to fight the menace. There is however, a challenge of inadequate funds for HIV/AIDS activities, lack of support for PLHIV, poverty and stigmatization, and less impact of NGOs to support the drive at reducing the cases. These factors that have combined to influence the spread of HIV&AIDS in the Municipality include; unemployment, poverty, migration, commercial activities (vibrant market), curiosity, divorce and broken homes, stigmatization and discrimination against PLHIVs and their affected, attraction of expatriates at the mines to the youth and disguised prostitution.

The higher risk groups include the females in the youthful age brackets of 17 – 35 years, apprentices, commercial drivers, cocoa farmers, trekking    officers, and hotel and restaurant attendants. In stemming the HIV/AIDS menace in the Municipality, the focus lies in addressing the challenges outlined and strengthening of inter sectorial engagements through the Municipal Health Directorate.

vi. Biodiversity, Climate Change, Green Economy and Environment

The recently incidence of climatic change and variability in the climatic conditions of the Municipality coupled with land use and land cover changes have resulted in considerable changes in the forest reserves and cover with major implication on agriculture activities and rural livelihoods. From previously short dry season (harmattan) to almost long dry season has had damaging effects on the environment and farm outputs. The heavy and prolonged rains associated with variability in climate condition are adversely affecting cocoa harvest (drying of cocoa beans) and crop production.

These climatic changing activities are impacting negatively on the Municipality’s aim at achieving increasing crop production and increasing farmers’ incomes. Understanding the links between climate variability, land use and land cover changes and rural livelihood dynamics is key for decision making, especially regarding sustainable management of forest resources, monitoring of ecosystems and related livelihoods that depend on the land resources. It is therefore important to indicate the extent to which the biodiversity, climate change, green economy and environment provide opportunities and challenges including their impacts on the Municipality’s development.

Unfortunately, environmental and natural resource/capital depletion has the potentials of posing as a major obstacle to fulfilling the growth potentials of the citizens whose livelihood is heavily dependent on agriculture as it employs more than half of the population. Food production and supply is heavily climate dependent. The dependence on natural resources as major livelihood couples with incidence of biodiversity loss, flash flooding, disease burden level, water pollution and energy resources depletion, and increasing environmental degradation resulting from galamsey activities and illegal chainsaw milling practices within some communities calls for the Municipality to encourage green initiatives and climate change adaptability and mitigation measures. In going forward the Municipal developmental processes and activities must include measures at improving and adapting integrated water resources management, responsible consumption of forest resources, agroforestry, conservation, organic and climate smart agriculture, green building, passive design, building energy efficiency, clean fuel.

vii. Access to Safe Drinking Water

Access to potable water for the people in the Municipality is not much of a problem.  The district is endowed with a number of rivers and streams, the most important of which is the Ankobra River. The topography is also rich with good water table conducive for taping underground water for domestic and industrial uses. The good rainfall can also harness for rain harvesting for commercial and domestic uses. The targeted percentage of the population with access to safe drinking water according to main source of water for drinking are Bore-hole/Pump/Tube well, pipe-borne water and Public tap/Standpipe in the Municipality was not met. A percentage of 5 also rely on River/Stream as a source of water for drinking. Most rural households (63%) depend on Bore-hole/Pump/Tube well for drinking as against 20.5 per cent in the urban areas. The urban community within the Municipality for period has 74% of access to safe drinking water.

This achievement was through a conscious effort by the Assembly in constructing some boreholes and extension of the small-town water systems as well as a partnership with Safe Water Network to construct small town water systems to Humjibre, Tanoso, Muoho, and Kojina well as the construction of 15 Mechanized boreholes in the Municipality. Also, some boreholes that were broken down were rehabilitated. The Municipal assembly has again signed a memorandum of understanding with Safe Water Network to construct small-town water in Asawinso and extend Bibiani and Sefwi Bekwai Small Town Water System thus showing its commitment to the provision of safe water to the people as the water they say is life. The Assembly quest to improve access to safe and reliable water supply services for all is therefore on course. Also owing to the covid-19 pandemic and the free water programme, the number of applications for new water connection to the various water boards was reduced as most consumers relied on public stand pipe.

However just a little above 10% in the rural areas have Pipe-borne inside their dwellings as a source of water for drinking. As a result, the Municipal Assembly within the next plan period shall make adequate provision for potable water facilities and rehabilitate the existing ones to meet the growing demand for potable water to improve the health and development of the people.

viii. Settlement and other built environment

a. Conditions of the Built Environment

The built environment (settlements) in the Municipality lacks development control or settlement plans.  Settlements are built haphazardly with poor quality building materials, which have resulted in poor housing quality and its effect on the green economy. Most houses have structural defects: extinctive cracks appear dilapidated, weak foundations, and ripped off or leaking roofs. The dilapidated and poor structures also serve as death traps and a health hazard to the inhabitants which has serious implication on the already small incomes of the people and the government.

b. Settlement Pattern

With the present population density of 160 persons per square kilometre per the district’s projected population for 2017 based on the 2010 PHC, the district is not all that sparsely populated as compared with the regional average of 99.3 persons per square kilometre. There are at least 345 communities with about 65 having a population above 500 persons (2010 Population and Housing Census) making the Municipality predominately rural. Thus, the general settlement pattern of the district can best be described as dispersed type. This dispersed settlement pattern makes it difficult to provide essential social services to most people in the district.

c. Housing Stock

According to 2010 Population and Housing Census there were a total of 18,540 houses in the district with urban forming 26.1 per cent and rural constituting 73.9 per cent. The data also show that there are 27,961 households made up of 30.2 per cent in urban and 69.8 per cent in the rural areas in the district. Bibiani Anhwiaso Bekwai is a district with an average household size of 4.3 persons with the rural recording a slightly higher number of 4.4 persons and urban (4.0). Population per house in the district is also 6.5, with 7.0 persons in the urban and 6.3 persons in the rural areas.

## 1.10 Summary of Key Development Issues of the Agenda for jobs policy (From Performance Review of 2018- 2021 DMTDP

The essence of the performance review and profiling as the first main step in the preparation of DMTDPs are to: Identify particular problems/issues evolved during the plan implementation, draw lessons/experiences from the execution of the plan and identify the development implications for profiling

In the light of this, the Municipality during the implementation of the 2018-2021DMTDP and profiling of the Municipality, has identified the following key development issues as harmonised with the inputs from community needs and aspirations. This will ensure strong linkage and conformity as well as informing decision-making in planning/designing for new policies, programmes/projects in the future. The following are list of key identified issues in relation to the Agenda for Jobs Policy:

1.9.1 Economic Development

- Narrow tax base

- Limited access to credit by SMEs and Farmers

- Limited Skilled development or training for entrepreneurs

- Low public-private partnership for development in the Municipality

- Low productivity in staple crop production, livestock and poultry

- Inadequate improved planting materials and agricultural inputs

- Lack of youth interest in agriculture

- Inadequate start-up capital for the youth

- Poor tourism infrastructure and services

1.9.2 Social Development

- Low-capacity building for teachers

- Poor and inadequate educational infrastructure

- Inadequate furniture for schools

- Inadequate scholarship to needy but brilliant students

- Gaps in physical access to quality health care

- High morbidity rate of malaria

- Limited support for people living with disabilities

- High stigmatization and discrimination of HIV and AIDS

- Growing incidence of child marriage and teenage pregnancy

- Inadequate supply of potable water to households

- Inadequate maintenance of water facilities

- Poor sanitation and waste management

- Low awareness of child protection laws and policies

- Limited coverage of social protection interventions

- Poor and inadequate sports infrastructure

1.9.3 Environment, Infrastructure and Human Settlement

- Upsurge in illegal mining, otherwise known as “galamsey”

- Over exploitation and inefficient use of forest resources

- Low institutional capacity at the local level adapts to climate and mitigation measures

- Poor road transport network

- Inadequate and weak bridges and culverts

- Poor communication network in some rural communities in the Municipality

- Inadequate access to electricity

- Poor drainage system and recurrent incidence of flooding

- Scattered and unplanned human settlements

- Limited access to land acquisition (Assembly land banks) and documentation

1.9.4 Governance, Corruption and Public Accountability

- Poor infrastructure and lack of logistics for effective functioning of sub-district structures

- Lack of adequate representation of women in local elections and governance processes

- Inadequate capacity building for local governance practitioners

- Poor coordination in preparation and implementation of development plans

- Limited implementation of fiscal decentralization policy

- Inadequate and delays in central government transfers

- Weak involvement and participation of citizenry in planning and budgeting

- Inadequate staffing and poor-quality equipment, and infrastructure for security services

1.9.5 Emergency Planning and Response (Including Covid-19 Recovery Plan)

- Limited awareness on natural and man-made disasters in the district

- Limited institutional capacity for prevention and management of disasters

- Limited infrastructure for isolation centers

- Inadequate sensitization of the general public on covid-19 and other health emergencies

- Decline in internally generated revenue due to covid-19

- Decline in SMEs and local economic development activities

1.9.6 Implementation, Coordination, Monitoring and Evaluation

- Limited funds to undertake M&E activities

- Inadequate data for monitoring and evaluation

- Poor data and information storage in the Municipality

# CHAPTER TWO

# KEY DEVELOPMENT PRORITIES

## Introduction

On the basis of the summarised key development issues identified from the previous chapter, the MPCU undertook various activities as well as used various tools such as ranking, Linking of Community needs/aspirations with Key Development Issues/gaps from performance review and profile, subjected the adopted issues to Potentials, Opportunities, Constraints and Challenges (POCC) analysis. Also impact assessment, tool kits on migration, tool kit on nationally determined contributions and on water safety were also used   so as to understand how the main problems or issues identified can be addressed to enhance development of the Bibiani-Anhwiaso-Bekwai Municipality to better the lives of the people.

The issues considered as priorities from the POCC Analysis were further subjected to impact analysis. This was to enable the planning team assess the impact of the issues in terms of the following:

- Significant linkage effect on meeting basic human needs/rights

- Severity and diversity of problem(s) and intended benefits

- Significant effects of problem in sustainable spatial development of designated spaces or corridor

- Significant multiplier effect on economic efficiency

- Impact on:

- The different population groups (e.g. girls, aged, disabled);

- Balanced development;

- Natural resource utilisation;

- Cultural acceptability;

- Resilience and disaster risk reduction;

- Climate change mitigation and adaptation;

- Institutional reforms.

- Opportunities for the promotion of cross-cutting issues such as

- HIV and AIDS in terms of the target groups in the sector for targeted interventions e.g. elimination of stigmatisation;

- Gender equality with respect to practical and strategic needs and interests;

- Nutrition.

The impact analysis was very objective and guided by evidence of records. In conducting the impact analysis, members of the MPCU were grouped into four. Each group scored the adopted issues by consensus among the members. A scoring system of 1 – 3 in terms of priority in an ascending order was used. Thus issues that were considered as having less impact were scored 1 whereas those considered to have a very high impact were scored 3 by the groups.

This chapter highlights the steps that were taken to determine the prioritized development issues of the Bibiani Anhwiaso Bekwai Municipal Assembly for 2022-2025.

## 2.2 List of prioritized Development issues

As explained earlier, a consensus was reached between members to adopt issues that were ranked from 1st to 8th as the Municipality’s prioritized development issues. These issues are presented in the table below:

##### Table 2.1: Prioritized Development Issues

| DEVELOPMENT DIMENSION | FOCUS AREAS OF MTDP 2022-2025 | KEY PRIORITIZED ISSUES |
| --- | --- | --- |
| Economic Development | Strong and Resilient Economy | - Narrow tax base - Limited access to credit by SMEs and Farmers |
|  |  | - Low public-private partnership for development in the Municipality - Limited Skilled development or training for entrepreneurs - Limited local participation in economic development |
|  | Tourism and Creative Arts Development | - Poor tourism infrastructure and services |
|  | Agriculture and Rural Development | - Low productivity in staple crop production, livestock and poultry - Inadequate improved planting materials and agricultural inputs - Poor marketing system and structures - Inadequate access to land and security of tenure for agricultural production - Low application of science and technology among smallholder framers - Inadequate disease monitoring and surveillance system |
| Social Development | Education and Training | - Poor and inadequate educational infrastructure - Inadequate furniture - Low-capacity building for teachers |
|  | Health and Health Services | - Gaps in physical access to quality health care - High morbidity rate of malaria - High stigmatization and discrimination of HIV and AIDS |
|  | Water and Sanitation | - Inadequate supply of portable water to households - Inadequate institutional supply of portable water - Inadequate maintenance of water facilities - Poor sanitation and waste management |
|  | Child and Family Welfare | - Low awareness of child protection laws and policies |
|  | Social Protection | - Limited coverage of social protection interventions |
|  | Disability and Development | - Limited support for people living with disabilities |
|  | Sports and Recreation | - Poor and inadequate sports infrastructure |
| Environment, Infrastructure and Human Settlements | Deforestation, Desertification and Soil Erosion | - Upsurge in illegal mining, otherwise known as “galamsey” - Over exploitation and inefficient use of forest resources - Low level of energy variability adoption behavior of citizens |
|  | Climate Variability and Change | - Low institutional capacity at the local level adapt to climate and undertake mitigation measures |
|  | Disaster Management | - Poor drainage system and recurrent incidence of flooding |
|  | Transport Infrastructure: Road | - Poor road transport network - Ineffective road safety policy enforcement |
|  | Information Communication Technology | - Poor communication network in some rural communities in the Municipality - Poor ICT usage, integration and diffusion at basic educational levels |
|  | Energy and Petroleum | - Low levels of electricity coverage for rural communities - Low levels of energy variability adoption behavior of rural communities |
|  | Human Settlements and Housing | - Scattered and unplanned human settlements - Unavailability of local plans in various communities of the Municipality - Indiscriminate sale of lands and land disputes - Inadequate street naming and property addressing system - Limited documentation on Assembly land and acquisitions of land banks. |
| Governance, Corruption and Public Accountability | Local Government and Decentralization | - Poor infrastructure and lack of logistics for effective functioning of Assembly and sub-district structures - Lack of adequate representation of women in local elections and governance processes - Inadequate capacity building for local governance practitioners - Weak involvement and participation of citizenry in planning and budgeting |
|  | Human Security and Public Safety | - Inadequate staffing and poor-quality equipment, and infrastructure for security services |
| Emergency Planning and Response (Including Covid-19 Recovery Plan) | Hydro meteorological | - Limited awareness on natural and man-made disasters in the district |
|  | Biological | - Limited institutional capacity for prevention and management of disasters |
|  | Local Economic and Business climate- Covid 19 Recovery | - Significant indirect slowdown and shortfall in local SME economic activities. - Shortfalls in local revenue mobilization |
|  | Anthropogenic | - Limited infrastructure for isolation centers - Inadequate sensitization of the general public on covid-19 pandemic and other health emergencies |
| Implementation, Coordination, Monitoring and Evaluation | Implementation and Coordination | - Limited funds to undertake M&E activities - Limited data accessibility for monitoring and evaluation |
|  |  | - Non completion of development Plans |
|  | Monitoring & Evaluation | - Limited funds to undertake M&E activities |
|  | Production and Utilization of Statistics | - Poor data and information storage in the district |

Source: MPCU, 2021.

# CHAPTER THREE

# DEVELOPMENT PROJECTIONS, GOALS, OBJECTIVES AND STRATEGIES

## Introduction

In this chapter, the development issues were linked to four of the five goals of the National Medium Term Development Policy Framework (NMTDPF) 2022-2025 and prioritized. In this chapter, the development focus of the BABMA has been established and a clear goal consistent with the MTNDPF 2022-2025 has also been stated. The chapter also includes development projections for 2022-2025. Relevant policy objectives and strategies have also been adopted from the NMTDPF 2018-2021 to achieve the objectives of the Municipality and the national goals.

## Development Projections of the District for 2022 -2025

This part looks at the current and future needs of the Municipality for the period 2022-2025. The needs were derived from the POCC analysis and the population projections.

    - Population Projections

Population is the single most important factor for the distribution of development programmes among various groups of persons particularly for the distribution of social services. Population projections are crucial in development planning decisions.

Generally, assumptions under population projections affect investment decisions on schools, hospitals and roads as well as power, water and sanitation supplies. Clearly, the supply of these facilities are restricted to age group, both aggregate and desegregation (according to age, sex, occupation, etc.) of the population.

The projected population of the municipality serves as the basis for estimating service requirement of health, water, education etc. up to the end of the plan period 2025. They form the basis for the planning and programming phase of the development plan. The Municipality’s population is projected by using the exponential method based on the absolute figures and age distribution figures for the district in 2021Population and Housing Census.

The assumptions made about the projections are:

- The ratio of the Municipality’s population will grow at a constant rate throughout the plan period.

- The district’s growth rate (of 1.8%) will remain almost the same or will not change much up to the year 2025.

- Child mortality rate records in the Municipality will reduce further or not change during the plan period.

- Also, the life expectancy at birth for both male and female in Ghana of 61/64 years remains the same till 2025.

- Migration rate in the municipality will remain unchanged during the plan period.

- The age-cohorts of the municipality will not change much during the period.

Tables 3.1 and 3.2 present the projected population, sex composition and age groups of the Bibiani-Anhwiaso-Bekwai District respectively.

##### Table 3.1: Projected Total Population and Sex Composition of the Municipality 2022 – 2025

| Year | Total | Male | Percentage | Female | Percentage |
| --- | --- | --- | --- | --- | --- |
| 2021 | 167,971 | 82,798 | 49.3 | 85,173 | 50.7 |
| 2022 | 171,021 | 84,313 | 49.3 | 86,708 | 50.7 |
| 2023 | 174,128 | 85,845 | 49.3 | 88,283 | 50.7 |
| 2024 | 177,291 | 87,404 | 49.3 | 89,887 | 50.7 |
| 2025 | 180,511 | 88,992 | 49.3 | 91,519 | 50.7 |

Source: MPCU Estimates, based on 2021 PHC

##### Table 3:2 Age Distribution and Projected Population in the Municipality, 2022-2025

| Age Group | Percentage | 2021 | 2022 | 2023 | 2024 | 2025 |
| --- | --- | --- | --- | --- | --- | --- |
| 0-14 | 39.8 | 66,852 | 68,066 | 69,302 | 70,561 | 71,842 |
| 15-64 | 55.7 | 93,560 | 95,259 | 96,990 | 98,752 | 100,545 |
| 65+ | 4.5 | 7,559 | 7,696 | 7,836 | 7,978 | 8,124 |
| Total | 100 | 167,971 | 171,021 | 174,128 | 177,291 | 180,511 |

Source: MPCU Estimates, based on 2021 PHC

## 3.3 Revenue Projections from 2022-2025

In order to ensure smooth implementation of projects and programme from 2022-2025 it is imperative to know the revenue projection to enable the Assembly plan well. Table 3.3 outlines the revenue projections from all funding sources.

##### Table 3.3: Revenue projection from 2022-2025

| Revenue Sources | 2021 Baseline | 2022 | 2023 | 2024 | 2025 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| IGF | 2,308,890.00 | 2,424,334.50 | 2,470,512.30 | 2,539,779.00 | 2,562,867.90 | 9,997,493.70 |
| STOOL LANDS | 967,700.00 | 1,016.085.00 | 1,035,439.00 | 1,064,470.00 | 1,074,147.00 | 4,190,141.00 |
| MDF | 1,286,793.00 | 1,351,132.65 | 1,376,868.51 | 1,415,472.30 | 1,428.340.23 | 5,571,813.69 |
| MAG | 134,112.00 | 140,817.60 | 143,499.84 | 147,523.20 | 148,864.32 | 580,704.96 |
| MPs CF | 584,540.00 | 613,767.00 | 625,457.80 | 642,994.00 | 648,839.40 | 2,531,058.20 |
| PWD | 179,839.00 | 188,830.95 | 192,427.73 | 197,822.90 | 199,621.29 | 778,702.87 |
| DACF | 3,596,780.00 | 3,776,619.00 | 3,848,554.60 | 3,956,458.00 | 3,992,425.80 | 15,574,057.40 |
| DACF- RFG | 600,000.00 | 630,000.00 | 642,000.00 | 660,000.00 | 666,000.00 | 2,598,000.00 |
| GOG | 2,964,256.00 | 3,112,468.80 | 3,171,753.92 | 3,260,681.60 | 3,290,324.16 | 12,835,228.48 |
| GRAND TOTAL | 12,488,798.00 | 13,254,055.50 | 13,506,513.70 | 13,885,201.00 | 14,011,430.10 | 54,657,200.30 |

Source: BABMA, MPCU, 2021

3.2.2 Development Projections

Based on the gaps and development issues identified above, the Assembly is committed to ensuring improvement/progress in the following areas within the medium term (2022-2025) towards achievement of its mandate. The development prospects for the period are grouped under the NMTDPF 2022-2025.

##### Table 3.4:  Development Projections under the Development Dimensions

| S/N | Development | Development Projections |
| --- | --- | --- |
|  | Economic Development | - To achieve 100% annual revenue collection target by December, 2025 - Build adequate capacity of Municipal Assembly to mobilise more IGF - To achieve 40% increase in property rate and business operation permit payments in the Municipality by December, 2025 - The MA target is to help establish and support about 500 micro, small and medium scale enterprises by December, 2025 - The MA targets to help 20 industrial subcontracting exchange to link SMEs with large-scale construction enterprises by December, 2025 - The MA will also develop one tourist attraction sites to improve the tourism sector by December, 2025 through PPP. - Improve the level of agricultural technological practices among 500 farmer based organisations by December, 2025 - Increase about 40% of farmers and SMEs accessibility to credit/loans by December, 2025 - Support 500 youth to enter into production of other exportable crops by December, 2025 - Train 400 farmers’ groups on the prevention and handling of pest and black pod cocoa diseases to reduce post- harvest losses from 30% to 10% by December, 2025 - To improve facilities at four (4) Market Centre’s in the Municipality to boost trading activities by December 2025 - Construct New Markets at Sefwi Bekwai through PPP by December, 2025 - Promote local tourism and develop 2 available and potential sites to meet international standards by December, 2025 |
|  | Social Development | - Increase the stock of school infrastructure in 12 communities by December, 2025 - Rehabilitate about 4 old schools by December, 2025 - Supply 400 Mono and 4000 Dual Desks by December, 2025 - Build the capacity of 400 Teachers to improve their performance by December, 2025 - Ensure the provision of adequate qualified health personnel - Construct 5 CHPs Compounds in 5 Communities by December, 2025 - Reduce infant and adult malnutrition in the Municipality by December, 2025 - Establish an effective food safety and monitoring system for food vendors - Bridge gender gaps in the Municipality - Increase the percentage of active school management committee to an appreciable level by December, 2025 - Intensify monitoring and supervision in schools - Construction of Municipal Education Office - Carry out outreach programmes in the communities to reduce stigmatization of HIV/AIDS and PLWHAS - Give support and credit to 100 PWDs to learn skills, 20 children with physically disabilities to go to school by December, 2025 - The Assembly together with its development partners has projected to provide 25 boreholes in 20 communities and 2 small town pipe water systems at Asawinso and Subri by December, 2025. - Support to about 500 households to construct household latrines in major towns and construct 4 public places of convenience particularly in major towns and market centres by December, 2025 - Ensure all newly constructed buildings have toilet facilities as condition for approval of building and habitation permit by December, 2025 - The Assembly through the Environmental Health Unit will collaborate effectively with Zoom lion Ghana Limited to collect the waste generated regularly to make public places clean - Ensure and Strengthen child labour sensitization activities to reduce incidence of child rights violations by 2025 |
|  | Environment, Infrastructure and Human Settlement | - The MA to rehabilitate 100km major feeder roads per annum and maintain urban roads - Plant 400,000 trees across the Municipality by 2025 - Sensitize community members on the effect of deforestation and illegal mining - The Assembly will extend electricity to 16 communities and continues to embark upon streets lighting by December, 2025 - The MA has outlined a number of strategies to increase ICT coverage by 80% through effective collaboration with the central government, donors and the private sector - Strict enforcement of environmental and mining laws, planning and building regulations - Strict enforcement of road safety policies and sensitization of road users - The Assembly will facilitate preparation of 6 communities’ local plans and complete SNPA activities. - The Assembly will ensure legal documentation of properties and acquisition of 6 land banks - Intensify public education on devastating effects of climate change - Protect the natural forest and reduce biodiversity loss |
|  | Governance, Corruption and Accountability | - To equip the MA with the required capacity and resources to deliver its mandate within the plan period - To ensure strong linkage between planning and budgeting in the Municipality - Deeply involve and ensure participation of the citizens in the decentralised planning and budgeting systems - To enhance a more effective working relationship between the Central Administration and Decentralised Departments as well as traditional authorities. - To equip Area Councils and Unit Committees with the necessary skills and resources to carry out their constitutional roles effectively by December, 2025. - Construct a divisional police command and establish 1 police post - Construct New Assembly offices by 2025 - Construct 2 Zonal council offices by 2025 - Construct I No Guest House for the Assembly |
|  | Emergency Planning and Response (Including Covid-19 Recovery Plan) | - Vaccination of all people in the Municipality against public health emergencies such as Covid-19 - Sensitize all the people in the municipality on public health emergencies such as Covid-19 - Ensure local economic revitalization to withstand any public health emergencies - Strengthen IGF mobilization with technology during public health emergencies |
|  | Implementation, Coordination, Monitoring and Evaluation | - Conduct PM&E on all development projects - Involve all stakeholders in Monitoring and Evaluation - Prepare 2026-2029 DMTDP by 2025 |

## 3.3 Desired Future Map

The maps below indicate the projection or proposed facilities that the Municipality intends to pride within the plan period (2022-2025).

Figure: 3.1 Proposed Health Facilities Map

Source: BABMA, MPCU, 2021

Figure 3.2 Proposed Education Facilities Map

Figure 3.3 Proposed Water Facilities Map

## 3.4 Municipal Goals, Objectives and Strategies Linked with Medium-Term National Development Framework (MTNDPF)

The Development Issues, Goals, Objectives and Strategies/Activities identified by the Municipality are presented in Table 3.3. They have been designed to address the key development problems and reflect the aspirations of the Municipality to achieve the objectives of the municipality and national goals and aspirations. The overall goal of the 2022-2025 DMTDP is “to provide socio-economic infrastructure for sustained increase in productivity, poverty reduction, decentralized governance to improve quality of life of the people in a participatory manner”

##### Table 3.5:  District Goals, Objectives and Strategies Linked with Medium-Term National Development Framework (MTNDPF)

| DISTRICT GOALS, OBJECTIVES AND STRATEGIES |  |  |  | MEDIUM-TERM NATIONAL DEVELOPMENT PLAN FRAMEWORK (MTNDPF) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Development Dimension | Goals | Objectives | Strategies | Goals | Objectives | Strategies |
| Economic Development | Promote fiscal decentralization process and increase economic growth and job creation | To achieve 100% internally Generated revenue target by 2025 | - Expand the tax net through data collection and valuation of properties - Reduce leakages in internal revenue collection - Build the capacity of revenue collectors | Build a Prosperous Country | Ensure improved fiscal performance and sustainability | - Strengthen revenue institutions and administration (SDG Target 16.6) - Eliminate revenue collection leakages (SDG Targets 16.5, 16.6, 17.1) |
|  |  |  |  |  |  | Diversify sources of resource mobilization (SDG Targets 17.1, 17.3) |
|  |  | Support access to training and entrepreneurship skills development | Support apprenticeship and provide start-up kits to 400 youth across the municipality by 2025 |  | Ensure improved skills development for industry | Establish apprenticeship and skills development centres to train skilled labour force for specific industrial sectors (SDG Target 4.4) |
|  |  | Develop tourism infrastructure and services | Mainstream tourism development in district development planning system |  | Diversify and expand the tourism industry for economic development | - Promote public-private partnerships for investment in the sector (SDG Target 17.17) - Promote local tourism and develop available and potential sites to meet international standards (SDG Target 8.9) |
|  |  |  | Promote and develop local tourism through Public Private Partnerships |  |  |  |
|  |  | Ensure food security and improved incomes of farmers | Introduce high yielding and short duration crop varieties |  | Modernization and enhance agricultural production systems | - Reinvigorate extension services (SDG Target 2.a) - Promote integrated pest management (IPM) approaches - Increase supply of fertilizer and certified seed especially for rice, soya and maize to meet import substitution agenda - Increase fertilizer usage from 20kg/ha to 50kg/ha by 2024 - promote increased investment in rice production and processing to reach self-sufficiency in 2023 - Develop the capacity of farmers to use meteorological information (SDG Target 12.8) - Promote commercial farming (SDG Targets 2.3, 2.4)\ - Ensure effective implementation of the yield improvement Programmes under the Planting for Food and Jobs campaign (SDG Targets 2.1, 2.4) |
|  |  |  | Develop effective post-harvest management strategies particularly storage facilities at community levels |  |  |  |
|  |  |  | To collaborate with CSOs to provide technical and financial support for Actors (food crop, fish and livestock farmers, processors, aggregators) along the agriculture value chains, especially women, youth and the vulnerable and SMEs |  |  |  |
|  |  | Promote the application of science and technology in agriculture development | Develop appropriate irrigation schemes for different category of farmers to ensure production throughout the year. |  |  |  |
| Social Development | Enhance and sustain social development interventions | Improve school infrastructure and services | Expand school infrastructure and facilities at all levels | Create Opportunities for all | Enhance inclusive and equitable access to, and participation in quality education at all levels | Enhance quality of teaching and learning environment (SDG Targets 4.1, 4.2, 4.6, 4.c) |
|  |  |  |  |  |  | Expand infrastructure and facilities at all levels (SDG Targets 4.a, 4.c) |
|  |  |  |  |  | Promote inclusive education | Provide facilities in all learning centres to improve access for PWDs and people with special needs (SDG Targets 4.1, 4.2, 4.5. 4.a) |
|  |  | Promote quality health care delivery in the district | Expand and equip health facilities |  | Ensure affordable, accessible, quality and Universal Health Coverage for all | Accelerate implementation of community-based Health Planning and Services (CHPS) policy (SDG Targets 3.8, 3.c.) |
|  |  |  | Expand infrastructure to accelerate the implementation of CHPS policy to ensure equity in access to quality health care delivery Strengthen CHPS service delivery with portable water supply to involve general hygiene |  |  | Expand, upgrade and equip health facilities with private sector involvement (SDG Target 3.8, 3.c) |
|  |  |  | Strengthen Integrated Disease Surveillance and Response (IDRS) district-wide |  |  | Strengthen the district and sub-district health systems as the bedrock of the national primary healthcare strategy (Agenda 111) (SDG Targets 3.8, 16.6) |
|  |  |  |  |  | Reduce disability, morbidity, and mortality | Strengthen maternal, new-born care and adolescent services (SDG Targets 3.1, 3.2) |
|  |  |  |  |  |  | Strengthen prevention and management of malaria cases (SDGs Target 3.2, 16.6) |
|  |  |  |  |  |  | Implement key interventions to reduce maternal and child mortality such as the Ghana Essential Health Intervention Project (SDG Target 3.1, 3.3) |
|  |  |  | Intensify HIV/AIDs Testing and Counselling activities |  | Ensure reduction of new HIV/AIDs/STIs and other infections, especially among vulnerable groups | Expand and intensify HIV Counselling and Testing Programmes (SDG Targets 3.3, 3.7) |
|  |  |  | Intensify sensitization and education against HIV/AIDs stigmatization |  |  | Intensify education to reduce stigmatization (SDG Targets 3.7) |
|  |  |  | Intensify behavioural change communications for high-risk groups for HIV/AIDs |  |  | Strengthen collaboration among HIV/AIDs, TB and sexual and reproductive health Programmes (SDG Target 3.3, 3.7) |
|  |  |  | Ensure continuous access Antiretroviral Drugs Therapy |  |  | Improve access to antiretroviral therapy (SDG Targets 3.3, 3.7, 3.8) |
|  |  | Enhance Child rights and social protection in the district | Mainstream child protection interventions into district development planning systems and budgets |  | Improve the policy and legal environment for child protection and development | Development and implement plans of action to address issues of child trafficking, streetism and other neglected conditions (SDG Targets 8.7, 16.2) |
|  |  |  |  |  | Strengthen social protection for the vulnerable | Strengthen institutional arrangements for the implementation of social protection interventions (SDG Targets 5.c, 16.6) |
|  |  |  |  |  |  | Implement productive social inclusion interventions (SDG Targets 5.c, 16.6) |
|  |  |  | Promote inclusion of children and people with disability and special needs in key activities of the Assembly |  | Promote the rights and welfare of children | Enhance the inclusion of children with disability and special needs in all spheres of child development (SDG Targets 4.5, 4.a, 10.2, 11.2) |
|  |  |  | Eliminate the worse form of child labour by enforcing child labour laws |  | Prevent and protect children from all forms of violence, abuse, neglect and exploitation | Increase funding for the implementation of plans and strategies to end child labour in all its forms (SDG Targets 5.3, 16.2, 16.3) |
|  |  |  | Promote socially supportive community care systems for the aged based on positive traditional and modern values, devoid of stereotyping, discrimination and disrespect |  |  | Increase community engagements and behavioural change campaigns to promote positive parenting attitudes and practices among parents and caregivers |
|  |  |  |  |  | Attain gender equality and equity in political, social and economic development systems and outcomes | Increase education and advocacy on sexual and Gender-Based Violence and other Harmful cultural practices |
|  |  |  |  |  | Promote gender-mainstreaming in all sectors | Develop capacities of stakeholders for effective gender mainstreaming |
|  |  |  | Ensure effective utilization of the 3% DACF to PWDs in the Municipality |  | Strengthen institutions and systems for child and family welfare | Strengthen the capacities of relevant institutions (SDG Targets 16.2, 16.6) |
|  |  | Promote population management and Development | Increase registration of births and deaths in the municipality |  | Strengthen institutions responsible for births control and management | Support the capacities of relevant institutions for population management |
| Environment, Infrastructure and Human Settlements | Protect the natural environment and promote sustainable human settlement | Improve efficiency and effectiveness in natural resource management | Improved climate smart indigenous agricultural knowledge | Safeguard the natural environment and ensure a resilient built environment | Protect forest reserves | Support the protection remaining network of natural forest and biodiversity hotspots in the country (SDG Targets 6.6, 11.4, 12.2, 15.1, 15.2, 15.5, 15.9, 15.a, 16.b) |
|  |  |  | Facilitate training and knowledge sharing among institutions involved in climate and adaptation measures |  |  | Strengthen environmental governance and enforcement of environmental regulations (SDG Targets 16.6, 16.b) |
|  |  |  |  |  |  | Enhance capacity of MDAs and MMDAs to mainstream biodiversity into development planning and budgeting processes (SDG Targets 15.9, 16.7, 17.9) |
|  |  | Strengthen local institutions to combat disasters | Strengthen the capacity of NADMO to perform its functions effectively |  | Promote proactive planning for disaster prevention and mitigation | Strengthen capacity of the National Disaster Management Organization and other related institutions to perform functions more effectively (SDG Targets 3.d, 11.5, 11.b, 16.6) |
|  |  |  | Educate public and private institutions on natural and man-made hazards and disaster risk reduction |  |  | Educate public and private institutions on natural and man-made hazards and disaster risk reduction (SDG Targets 3.d, 13.3) |
|  |  |  | Strengthen early warning and response mechanism on disasters |  |  | Strengthen early warning and response mechanisms for disasters (SDG Targets 1.5, 5.5) |
|  |  | Improve Road Network and Conditions Improve enforcement of road safety regulations | Provide bitumen surfacing for urban roads and undertake regular reshaping of all feeder roads in the district Improve road safety and road accidents on major tank roads |  | Improve efficiency and effectiveness of road transport Strengthen Road Safety efforts | Expand and maintain the national road network (SDG 11.2) Reduce road related accidents and deaths. |
|  |  | Increase water coverage from 88% in 2020 to 100% by 2025 and sanitation services Increase access to sanitation services and end open defecation by 2025 | Construct mechanized boreholes and small-town water systems |  | Improve access to safe and reliable sustainable water supply services for all | Provide mechanized boreholes and small-town water systems to unserved areas (SDG Target 6.1) |
|  |  |  | Facilitate the tree planting along the banks of all major rivers and their tributaries to reduce silting and pollution from human activities |  |  | Strengthen institutional and public capacity for water resources management (SDG Targets 6.a, 6.4, 16.6) |
|  |  |  | Improve liquid and solid waste management |  |  | Improve liquid waste management (SDG Targets 6.3, 6.a, 6.b) |
|  |  |  |  |  |  | Promote National Total Sanitation Campaign (SDG Targets 6.2) |
|  |  |  | Undertake public education on solid waste management |  |  | Scale-up sensitization campaigns to promote proper hand washing and hygiene practices particularly among children (SDG Targets 6.2) |
|  |  | Improve sports infrastructure and services | Integrate sports and recreational needs of aged and children in the provision of facilities |  | Enhance sports and recreational infrastructure for all | Promote partnerships with private sector in development of sports and recreational infrastructure (SDG Targets 17.17) |
|  |  |  |  |  | Build capacity for sports and recreational development | Strengthen partnerships with stakeholders in the development of sports (SDG Targets 17.17) |
|  |  | Improve access to electricity supply | Support the implementation of rural electrification projects |  | Ensure availability of clean, affordable and accessible energy | Revise self-help electricity project (SHEP) and use means testing approaches to enable the poor to connect to the national grid (SDG Targets 1.4, 7.1) |
|  |  |  | Improve ICT education and delivery in the district |  | Enhance application of ICT in national development | Position the country as a regional ICT hub (SDG Targets 9.c) |
|  |  |  | Enhance communication networks in all communities |  |  | Improve quality of ICT services, especially internet and telephony (SDG Targets 9.c) |
|  |  |  | Prioritize development activities in all communities |  | Enhance quality of life in rural areas | Promote rural enterprise development, financial inclusion, service delivery, capacity building and local economic development (SDG Targets 2.a, 11.a) |
|  |  |  |  |  |  | Facilitate sustainable use and management of natural resources that support the development of rural communities and livelihoods (SDG Targets 11.3, 17.17) |
|  |  | Accelerate street naming, property addressing system and regular development control activities | Provide Municipal spatial development framework | Safeguard the natural environment and ensure a resilient built environment | Promote sustainable, spatially integrated and orderly development of human settlements | Ensure preparation of Spatial Development Frameworks, Structure Plans and Local Plans for MMDAs (SDG Targets 11.3, 11.7, 11.a) Enhance human capacity for spatial planning in MMDAs |
| Governance, Corruption and Public Accountability | Promote administrative and political decentralization | Deepen decentralization at the local level | Strengthening of district sub-structures for effective service delivery | Maintain a stable, united and safe country Mainstream emergency planning and preparedness into Ghana’s development planning agenda at all levels to respond to potential internal and external threats (including COVID-19) Improve delivery of development outcomes at all levels | Deepen political and administrative decentralization | Strengthen sub-structures (SDG Targets 16.6) |
|  |  |  |  |  |  | Create enabling environment for implementation of Local Economic Development (LED) and Public-Private Partnership (PPP) policies at district level (SDG Targets 17.14, 17.17; ECOWAS Protocol Art. Art. 23) |
|  |  |  |  |  |  | Strengthen the implementation of planning and budgeting provisions in LI 2232 and the Public Financial Management Act 2016 (Act 921) (SDG Targets 16.5, 16.6, 16.a) |
|  |  |  |  |  | Improve popular participation at regional and district levels | Promote effective stakeholder involvement in development planning process, local democracy and accountability (SDG Target 16.7, 11.3; ECOWAS Protocol Art. Art. 23) |
|  |  |  | Promote women empowerment in local governance processes |  |  |  |
|  |  |  | Provide infrastructure for effective security services |  | Enhance security service delivery | Transform security services into a world-class security institution with modern infrastructure, including accommodation, health and training infrastructure facilities (SDG Targets 16.6, 16.a) |
| Emergency Planning and Response (including covid-19 recovery plan) | Mainstream Emergency Response Activities into district development planning systems | Enhance capacity of institutions responsible for disaster management | Promote regular training of staff to educate and sensitize people on disaster related issues |  | Promote proactive planning for disaster prevention and mitigation | Develop and Implement national plan to make cities and communities resilient |
|  |  |  |  |  | Enhance surveillance system and build response capacity to prevent, detect, contain, and respond to a possible epidemic outbreak | - Enhance capacities of Health professionals and institutions or agencies Improve surveillance, monitoring and evaluation of Health threats and pandemics - Enhance the enforcement of the public health act |
|  |  | Establish District Disaster Management Fund | Strengthen budgetary allocations for disaster prevention and management |  | Enhance institutional capacity and coordination for effective emergency response | - Strengthen financial management and procurement for epidemics - Strengthen and expand designated hospitals to receive COVID-19 patients |
|  |  |  | - Ensure local economic revitalization to withstand any public health emergencies - Strengthen IGF mobilization with technology during public health emergencies |  | Strengthen access to finance for local SME businesses, | - Strengthen local economic development and entrepreneurship - Increase local economic activities and industrialization |
|  | Prevention and management of pandemics | Improve public education and funding for covid-19 related activities | - effective awareness creation and education of the public on covid-19 - Mobilize financial and logistical support for the management of covid-19 - Investigate rumors, events, reported outbreaks, and other public health emergencies - Vaccination of all residents in the Municipality - Initiate the implementation of the proposed control measures including capacity building |  | Ensure secured health systems | - Enhance the enforcement of the public health act - Develop a human capital development agenda that prioritizes sustainable financing, innovation and educational risk management - Improve surveillance, monitoring and evaluation of Health threats and pandemics |
| Implementation, Coordination, Monitoring and Evaluation | Improve percentage implementation of development Programmes | Increase resource mobilization, plan implementation, monitoring and evaluation | Provide adequate funds and logistics for plan implementation, monitoring and evaluation |  | Strengthen plan preparation, implementation and coordination at all levels | Enhance linkage between the annual national budget statement and economic policy to the Coordinated Programme of Economic and Social Development Policies (CPESDP) and the Medium-Term National Development Policy Framework (MTNDPF) |
|  |  | Improve citizen participation in governance |  |  |  | Strengthen and improve resource mobilization for plan implementation |
|  |  |  | Mainstream M&E activities into budgetary processes |  | Strengthen monitoring and evaluation systems at all levels | Strengthen M&E capacities at all levels |
|  |  |  |  |  |  | Develop effective communication arrangements for M&E results |
|  |  | Strengthen data collection and processing in the district | Provide adequate logistics for data storage to enhance integrity of information |  | Strengthen production and utilization of statistics at all levels | Strengthen data production, management and utilization |
|  |  |  |  |  |  | Improve investments in ICT and geographical information systems (GIS) for the production and utilization of statistics |
|  |  | Promote capacity building of staff and Assembly members to enhance service delivery | Ensure regular training and provision of logistics to increase productivity |  | Improve working environment in the municipality | Improve investment in staff training and capacity building |

## 3.5 Strategic Environmental Assessment (SEA) of MTDP – Compound Matrix Sustainability Tests

Strategic Environmental Assessment tool was applied to 2022-2025 DMTDP. A total of twenty-six (26) policy objectives were subjected to SEA using the compound matrix (Poverty Environmental Dimension) whilst the strategies were also subjected to Sustainable Test Appraisal method. Summary of result is presented below;

3.5.1 Compound Matrix

i. Effects on Livelihood

The results showed that PPP’s 5, 6, 12, 14 and 16 will impact negatively on livelihoods of the people including access to water, land, and timber resources. However, the rest of the PPP’s would not impact on livelihoods.

ii. Mitigation Measures

The removal of vegetation cover that would results in negative impacts on livelihoods by PPP’s 5, 6, 12, 14 and 16 would be mitigated through landscaping and afforestation programme on the affected portions of land to restore vegetation loss

iii. Effects on Health

The analysis of the assessment revealed that PPP’s 6 and 12 would affect the health status of the people whilst the rest of 24 PPP’s would not impact negatively on the health status of the people.

iv. Mitigation Measures

Appropriate agricultural practices and landscaping would be adopted to reduce the impacts of PPP’s 6 and 12 on the health status of the people.

v. Effects on Vulnerability

PPP’s 5 and 12 would potentially create crisis and induce vulnerability to the people. Other 24 PPP’s would either affects positively or neutral on the lives of the people and the environment.

vi. Mitigation Measures

Appropriate compensations would be paid to the affected land owners through the provision of the infrastructure.

3.5.2 Sustainable Appraisal Test

Individual strategies were also subjected to the sustainable appraisal tests to identify their effects on natural resources, social and cultural conditions, economy and the institutions concerned. Performance of the individual strategies has been discussed below;

i. Construction and Reshaping Strategies

The sustainability tests on the Construction and Rehabilitation strategies which seeks to promote school projects, health and accommodation facilities either work against the aim of natural resource conservation or supports it in cases where lands were already degraded. The Rehabilitation projects mostly have no significant effect on the reserves since they already exist.

All construction and rehabilitation works support social and cultural conditions namely health and well-being, gender, job creation, equity and participation. Others however limit access to land because the same piece of land could be used alternatively. Similarly, some also work against vulnerability and risk by causing epidemics or conflicts in cases where the said projects would serve more than one community. Construction and Rehabilitation enhances development and growth and again encourages retention of local capital in view of the fact that local artisans are mostly used.

As a result, degradation of land and rivers should be carefully considered for projects purpose especially in areas where it would be difficult to reforest or undertake landscaping activities.  New projects should always be sited on already degraded land to avoid further destruction of arable lands. Tree planting activities would be carried out along river banks to avoid direct sun shine which will potentially cause river dryness.

ii. Infrastructure and Human Settlement

Infrastructure strategies seeks to promote road construction and rehabilitation, extension of electricity, preparation and extension of planning schemes for the major communities. Extension of electricity to the rural and unserved areas and road rehabilitations would negatively affects the conservation of natural resources as lands would be cleared for such purpose. However, Planning Schemes would have no effect on natural resources. Infrastructure development would also negatively affect the natural vegetation as lands would be cleared for such purpose. Afforestation and landscaping around the affected land areas would be undertaken to replace the lost vegetation cover.

# CHAPTER FOUR

# COMPOSITE DEVELOPMENT PROGRAMMES

## Introduction

Chapter four discusses the Municipality’s Composite Development Programmes within the medium term planned period (2022-2025) and in line with programme-based budget covering Management and Administration, Social services Delivery, Infrastructure Development and Management and Environmental Management as well as sub-programmes. This chapter also encapsulates Indicative Financial Flan.

## Assumptions and methodologies used for projects costing

The Bibiani Anhwiaso Bekwai Municipal Assembly have a wide range of responsibilities when it comes to planning activities, budgeting and allocating its limited resources to successfully meets its planned aspirations and developmental agenda. A large part of the developmental project and programs planning involves making informed guesses about certain aspects of the projects/programmes that must be accurate and realistic to avoid compromising the integrity of the entire project and at the same time ensuring probity and sustainability of the projects/programmes. These informed decisions of budgeting are the assumption of cost and price inflation throughout the period of the planed phases which must be closely monitored to make quick, accurate adjustments wherever necessary.

4.2.1 Key Assumptions

- There would be political stability during the period

- Materials will arrive as planned within the programme schedule

- Contractors, Suppliers and Service providers would be able to execute the projects in stipulated time period

- The Assembly staff/project management team have the capacity to implement the programmes and projects

- Annual inflation rates would remain 10% on annual basis during the period

- Access to resources including funds, human and materials needed to complete the projects on time would be made available

- All constraints in relation to cost, time, scope and quality of executions would be overcome during the planned period

- Lands earmarked for the project’s activities would remain same and available during the period

- All relevant stakeholders would participate and play their roles for effective implementation of projects

- Cost of utilities, equipment and other project costs will remain unchanged during the period.

- Changes in material cost i.e. the raw materials needed for a project are part of the project total direct cost. Based on the past experiences and actual cost of materials considering inflation rate and time, we create material budget assumption documents which helps in our arrivals of budget estimates.

- Expected Income is one of the assumptions made during budget preparation since a budget is a plan for spending money, there must first be money to spend. We therefore make realistic assumption as to our expected revenue/income.

- Expected expenses are the expenses expected to be paid from the budget which are also part of the assumptions made.

- Time assumptions are one of the most significant cost related assumptions and one of the most difficult to get it right. For this reason, time assumptions are most often completed for each activity and totaled at the end.

4.2.2 Methodologies or steps used for costing

The following factors were considered in the steps for costing the 2022-2025 DMTDP;

- Resource requirements for each project

- Current prices for the various components of each project

- Duration and period for each project and

- Similar past projects cost which served as benchmarks for the estimations. Apart from these steps, certain specific activities or methods were employed in the estimation processes including;

- 2% of the cost of implementing all programmes and projects would be allocated to monitoring and evaluation

- The elements contributing to the cost of scaling up varies across the communities in the municipality as a result of proximity to the Municipal capital and project design as well as site conditions

- Existing previous costs of similar projects were identified and then applied 10% annual incremental values to arrive at the cost for a particular year

- Market survey were conducted to identify the cost of materials and labour including consulting the PPA website for infrastructure estimation tool

- Estimations were done for various projects components including materials, labour and overheads costs and add them up to arrive at total cost of each project

- A contingency of 10% was applied across board to cater for emergencies and price fluctuations due to market forces

## 4.3 Programmes of Action (PoA) for 2022-2025

For the Municipality to address the development gaps identified earlier and to achieve the spatial development option together with the development focus, broad programmes were identified. These were done to ensure reliability, continuousness as well as complementarity in implementation. The broad programmes which are both physical and non-physical have been presented in Table 4.1 with their corresponding sub-programmes.

##### Table 4.1 Programme of Action for Bibiani-Anhwiaso-Bekwai Municipal Assembly (2022-2025)

| Goals | Objectives | Programme (PBB) | Sub- Programme (PBB) | Time Frame |  |  |  | Cost GH₵ |  |  | Programme Status |  | Implementing Institution |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 2022 | 2023 | 2024 | 2025 | GoG | IGF/ | Others | New | On- going | Lead | Collaborating |
| Build a Prosperous Country | Achieve 100% internally generated revenue target by 2025 | Management and Administration | Finance |  |  |  |  | 450,000.00 | 839,295.97 | 360,000.00 |  | - | Finance | CA |
|  | Support access to training and entrepreneurship skills development | Economic Development | Trade, Industry and Tourism Services |  |  |  |  | 600,000.00 | - | 1,150,000.00 | √ | - | BAC | RTF, Financial Institutions |
|  | Develop tourism infrastructure and Services | Economic Development | Trade, Industry and Tourism Services |  |  |  |  | 1,590,000.00 | 1,160,000.00 | 125,000.00 |  | - | CA | GTB |
|  | Ensure food security and improved incomes of farmers | Economic Development | Agricultural Services and Management |  |  |  |  | 230,000.00 | 70,000.00 | 2,568,000.00 | √ |  | MDA | CA |
|  | Promote the application of science and technology in agriculture development | Economic Development | Agricultural Services and Management |  |  |  |  | 100,000.00 | 100,000.00 | 1,054,000.00 | √ | - | MDA | CA |
| Create opportunities for all | Improve school infrastructure and Services | Social Services Delivery | Education, youth and sports and Library Services |  |  |  |  | 7,700,000.00 | 570,000.00 | 150,000.00 | √ |  | GES | CA, MOE |
|  | Promote quality health care delivery in the Municipal | Social Services Delivery | Public health Services and Management |  |  |  |  | 6,500,000.00 | 80,000.00 | 70,000.00 | √ |  | GHS | MOH, NGOs |
|  | Enhance Child rights and social protection in the Municipal | Social Services Delivery | Social Welfare and Community Services |  |  |  |  | 150,000.00 | 408,000.00 | 76,000.00 | √ | - | SWCD | CA, UNICEF |
|  | Promote population management and Development | Social Services Delivery | Birth and Death Registration Services |  |  |  |  | 1,450,000.00 | 430,000.00 | 41,670.00 |  | - | GHS | CA, Birth and Death |
|  | Increase access to sanitation services and end open defection by 2025 | Social Services Delivery | Environmental Health and sanitation Services |  |  |  |  | 2,750,000.00 | 150,000.00 | 80,000.00 | √ | √ | EHU | CA, CWSA |
|  | Improve sports infrastructure and Services | Social Services Delivery | Education, youth and sports and Library Services |  |  |  |  | 430,000.00 | 45,000.00 | 270,000.00 | √ | √ | GES | MOE, CA |
|  | Improve public education and funding for covid-19 related activities | Social Services Delivery | Public Health Services and management |  |  |  |  | 180,000.00 | 230,000.00 | - | √ | √ | GHS | CA, MOH, RCC |
| Safeguard the Natural Environment and Ensure a Resilient Built Environment | Improve efficiency and effectiveness in natural resource management | Environmental Management | Natural Resource Conservation and Management |  |  |  |  | 880,000.00 | - | 568,000.00 | √ | √ | FC | CA, NGOs, |
|  | Strengthen local institutions to combat disasters | Environmental Management | Disaster prevention and management |  |  |  |  | 89,007.00 | 1,150,000.00 | 100,000.00 | √ | √ | NADMO | CA |
|  | Improve road network and conditions | Infrastructure Development and Management | Urban Roads and Transport Services |  |  |  |  | 4,760,000.00 | - | - | √ | √ | Works Dept. | Urban Roads, Feeder Roads, CA |
|  | Improve enforcement of road safety regulations | Infrastructure Development and Management | Urban Roads and Transport Services |  |  |  |  | 1,139,890.00 | - | - | √ | √ | Works Dept. | Urban Roads, Road safety Commission |
|  | Increase water coverage from 88% to 100% by 2025 | Infrastructure Development and Management | Public works, rural housing and water management |  |  |  |  | 1,960,000.00 | 230,000.00 | 100,000.00 | √ | √ | Works | CWSA, CA |
|  | Improve access to electricity supply | Infrastructure Development and Management | Public works, rural housing and water management |  |  |  |  | 970,000.00 | 100,000.00 | 400,000.00 | √ | - | Works | ECG, CA |
|  | Accelerate street naming, property addressing system and regular development control activities | Infrastructure Development and Management | Spatial Planning |  |  |  |  | 860,700.00 | - | 245,000.00 |  |  | Physical Planning Dept. | CA, RCC, MLGDRD |
| Maintain a stable, united and safe country | Deepen political and administrative decentralization | Management and Administration | General Administration |  |  |  |  | 526,770.00 | 3,789,600.00 | 2,073,563.00 | √ | - | CA | MLGDRD, RCC |
| Mainstream emergency planning and preparedness into Ghana’s development planning agenda at all levels to respond to potential internal and external threats (including COVID-19) | Enhance capacity of institutions responsible for disaster management | Environmental Management | Disaster prevention and Management |  |  |  |  | 170,000.00 | 257,900.00 | - | √ | √ | GHS | CA, MOH, NADMO |
|  | Establish Municipal Disaster Management Fund | Environmental Management | Disaster prevention and Management |  |  |  |  | 50,000.00 | - | 250,000.00 | √ | √ | NADMO | CA, RCC |
| Improve delivery of development outcomes at all levels | Increase resource mobilization, plan implementation, monitoring and evaluation | Management and Administration | Planning, Budgeting, Monitoring and evaluation |  |  |  |  | 890,000.00 | 50,000.00 | 130,000.00 | √ | √ | CA | RCC, MLGDRD |
|  | Improve citizen participation in governance | Management and Administration | Planning, Budgeting, Monitoring and evaluation |  |  |  |  | 270,000.00 | 40,000.00 | 40,000.00 |  | - | CA | MLGDRD, RCC, TA |
|  | Strengthen data collection and processing in the municipality | Management and Administration | Planning, Budgeting, Monitoring and evaluation |  |  |  |  | 300,000.00 | 65,000.00 | 75,000.00 |  | - | Statistics Dept. | CA, GSS, RCC |
|  | Promote capacity building of staff and Assembly members | Management and Administration | Human Resource |  |  |  |  | 480,000.00 | 75,000.00 | 160,000.00 |  | - | HRM | CA, MLGDRD |
| TOTAL |  |  |  |  |  |  |  | 35,476,367.00 | 9,839,795.97 | 10,086,233.00 | 55,402,395.97 |  |  |  |

## 4.4 Indicative Financial Plan (2022-2025)

The well designed and co-ordinated poverty reduction programmes/strategies towards improving the living standards of the people are meaningless if the needed resources are not mobilized both locally and externally to execute them within the plan period of 2022-2025.

The Indicative Financial strategy for the planned period is prepared to deal with the means for mobilising and utilising financial resources for the implementation of the MTDP. The Major expenditure areas of the Municipality with respect to the Medium Term Development Plan relates to financing the Projects, Programme and activities under four major programme areas namely Social Services Delivery, Infrastructural Development, Environmental Management and Management and Administration for the period.

The Assembly intends to finance the planned projects and programmes mainly from three major sources of funding which includes projected Central Government inflows made up of the DACF, DACF-RFG, GoG, GETFund etc., the Internally Generated Fund mainly mobilised by the Assembly from revenues accruing from activities in the Municipality which includes rates, rents, fines, licences, fees etc. and Donor funds from Development Partners and the Private Sector which include Mining Companies who operates within the District.

The Assembly intends also to rely on the Road Fund to finance majority of the urban roads project. Part of the “One Million Dollars per Constituency” though not administered under the MMDAs has been considered as other source of funding which will help address the issues identified. This is resulting from the fact that, almost the same issues came up during the needs assessment by the secretariat.

The Rural Enterprises Project (REP) with funds from the African Development Bank would provide funds for skills training programmes. Also other funding agencies are the Ghana Highway Authority, Ministry of Education, Ministry of Health, Ministry of Food and Agriculture, as well as the Ministry of Energy.

In sum, the total cost of the projects and programmes for the MTDP for the plan period will be GH¢ 55,402,395.97 and the anticipated revenue from all sources of funding will amount to GH¢54,657,200.30. The total revenue difference will also amount to GH¢745,195.67.

The indicative financial strategy for mobilisation of funds or revenue in a sustainable manner for the implementation of the programmes/projects over the four (4) year period (2022-2025) is presented in table 4.2 below;

##### Table 4.2 Programme Financing (2022 – 2025)

| Development Dimension | Programmes | Programme Cost (GH¢) | Expected Revenue and Sources of Funding (GH¢) |  |  |  |  |  | Total (GH¢) | Gap (GH¢) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | GoG (GH¢) | IGF (GH¢) | DACF (GH¢) | DACF-RFG | DPs (GH¢) | Others (GH¢) |  |  |
| Economic Development | Management and Administration | 1,649,295.97 | 96,500.00 | 859,295.97 | 609,500.00 | - | - | 97,000.00 | 1,662,295.97 | 13,000.00 |
|  | Economic Development | 8,747,000.00 | 76,000.00 | 1,230,000.00 | 3,916,039.44 | 451,600.00 | 487,600.56 | 1,540,760.00 | 7,702,000.00 | -1,045,000.00 |
| Social Development | Social Services Delivery | 21,760,670.00 | 4,488,250.48 | 2,063,000.00 | 9,911,646.03 | 993,400.00 | - | 4,070,994.69 | 21,527,291.20 | -233,378.80 |
| Environmental, Infrastructure and Human Settlement | Environmental Management | 2,787,007.00 | 700,000.00 | 1,150,000.00 | 700,000.00 | 60,000.00 | 23,000.00 | 80,000.00 | 2,713,000.00 | -74,007.00 |
|  | Infrastructure Delivery and Management | 10,765,590.00 | 4,760,800.00 | 330,000.00 | 2,145,800.00 | 765,000.00 | - | 1,476,000.00 | 9,477,600.00 | -1,287,990.00 |
| Governance, Corruption and Public Accountability | Management and Administration | 6,389,933.00 | 659,000.00 | 3,789,600.00 | 1,065,833.00 | - | - | 890,500.00 | 6,404,933.00 | 15,000.00 |
| Emergency Planning and Response (including covid-19) | Environmental Management | 727,900.00 | 978,000.00 | 257,000.00 | 100,000.00 | - | 45,340.00 | 256,700.00 | 1,637,040.00 | 909,140.00 |
| Implementation, Coordinating, Monitoring and Evaluation | Management and Administration | 2,575,000.00 | 1,076,678.00 | 318,597.73 | 435,000.00 | 328,000.00 | 24,764.40 | 1,350,000.00 | 3,533,040.13 | 958,040.13 |
| TOTAL |  | 55,402,395.97 | 12,835,228.48 | 9,997,493.70 | 18,883,818.47 | 2,598,000.00 | 580,704.96 | 9,761,954.69 | 54,657,200.30 | (745,195.67) |

Source: MPCU, 2021

4.4.1 Mechanisms to fill Gap

The analysis of the financial status of the programmes and sub-programmes of the 2022 -2025 MTDP indicate that the Assembly would raise a total of Fifty-Four Million, Six Hundred and Fifty-Seven Thousand, Two Hundred and Thirty pesewas (GH¢54,657,200.30) as a total revenue for the period. The total expected expenditure for the implementation of the plan also stood at Fifty Five Million, Four Hundred and Two Thousand, Three Hundred and Ninety Five Ghana cedis and Ninety Seven pesewas (GH¢55,402,395.97. This leaves a financing gap of Seven Hundred and Forty Five Thousand, One Hundred, Ninety Five Ghana cedis and Sixty Seven pesewas (GH¢745,195.67)

The Assembly has therefore put in place measures to raise the additional resources to finance the gap to ensure smooth implementation of the plan. The following are some of the proposal put forward to achieve the above stated objective.

- Appeal to the Private Sector such as Mining Companies, Financial Institutions & NGOs/DPs to support the implementation of some activities of the plan.

- The Assembly would adopt a labour intensive approach in the implementation of some its programmes which does not demand high technical skills.

- Expand the local tax net through the upscaling of implementation of DLREV software. This would be done through the expansion of street naming and property addressing system in the municipal.

- Continue the valuation of business and individual properties to improve property rate collections during the period.

- Educate and sensitize communities to adopt self-help projects instead of relying on the Assembly to finance the entire costs of their projects.

- The Assembly would undertake aggressive sensitization of the general public on the need to pay local revenues to improve socio-economic development of the municipal.

## Maintenance Plan

Ensuring effective assets maintenance by the Assembly is essential to improve the lifespan of these assets as well as achieving sustainability in terms of the utilization of these assets. The Plan also indicate the appropriate skill sets for each maintenance task. The content of the Plan include type of infrastructure and maintenance, schedule of maintenance, the estimated cost, located and the responsibility arrangements. Details of the plan is outlined in Appendices II

## 4.6 Spatial Development Framework/Structure Plan

The Assembly do not have spatial development framework or a structure plan due to the cost involve. Untimely releases of the statutory funds as inadequate mobilization of the internally generated revenue accounted for not meeting some of the development priorities and hence the inability to prepare the spatial development plan till now. However, efforts are been made to prepare one for the Assembly in due course.

# CHAPTER FIVE

# ANNUAL ACTION PLANS FOR 2022-2025

## 5.1 Introduction

This chapter presents planned programmes, projects and activities to be implemented on annual basis from 2022-2025. These activities are linked to the NMTDPF, the SDGs and AU Agenda 2063, adopted policy objectives and strategies under the Governance, Corruption and Public Accountability development dimension of the Coordinated Programme for Economic and Social Development Policies; Agenda for Jobs. The annual activities and their corresponding indicative budgets form the basis for the Assembly’s annual budgetary requests to Development partners. The outer year activities are subject to review annually based on successive implementation.

Tables 5.1 to table 5.4 below present the Programme Based Budget, Sub-programme, Broad Activity, Location, time frame, estimated budgets, Sources of funding for the implementation of planned activities for the period 2022-2025 and implementing Institution.

##### Table 5.1 Annual Action Plan for 2022

2022 Composite Annual Action Plan

| Programme (PBB) | Sub- Programme (PBB) | Broad Activities |  | Location | Time Frame |  |  |  |  | Cost |  |  |  | Programme Status |  |  |  | Implementing Institution |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 |  | Q2 | Q3 | Q4 | GoG (GH¢) | IGF (GH¢) |  | Others (GH¢) | New |  | On-going |  | Lead |  | Collaborating |  |
| DEVELOPMENT DIMENSION 1: ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Strong and Resilient Economy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Finance | 1. Train revenue collectors and key staff on revenue collection strategies |  | Bibiani |  |  |  |  |  | - | 10,000.00 |  | - |  |  | - |  | Finance . |  | CA, GIZ Statistics Dept. |  |
| Management and Administration | Finance | 2. Continue the valuation of Assembly properties |  | Municipal Wide |  |  |  |  |  | - | - |  | 100,000.00 | - |  |  |  | Finance |  | GIZ, CA |  |
| Management and Administration | Finance | 3. Strengthen Rateable property data collection and revenue collection digitalization |  | Municipal Wide |  |  |  |  |  | - | 10,000.00 |  | - | - |  |  |  | Finance |  | CA |  |
| Focus Area: Private Sector Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Trade, Industry and Tourism | 4. Organize Quarterly Business sections and follow-ups for 240 business owners |  | Bibiani |  |  |  |  |  | - | 16,000.00 |  | - | - |  |  |  | BAC |  | RTF/CA |  |
|  |  | 5. Rehabilitation of Humjibre Market |  | Humjibre |  |  |  |  |  | 45,000.00 | - |  | - | - |  |  |  | Works |  | CA |  |
|  |  | 6. Conduct monthly monitoring visits for 306 MCP beneficiaries to assess status and impacts of programme |  | Municipality-wide |  |  |  |  |  | - | 12,000.00 |  | - |  |  | - |  | BAC |  | CA/GOG, Private Sector |  |
|  |  | 7. Organize 4 radio talk shows to sensitize the youth on You-Starts and Ghana Jobs and skills programme |  | Municipality-Wide |  |  |  |  |  | 18,000.00 | - |  | - |  |  | - |  | BAC |  | CA |  |
|  |  | 8. Facilitate access to credit facilities for 175 SMEs |  | Municipality- wide |  |  |  |  |  | 5,000.00 | - |  | - |  |  | - |  | BAC |  | CA |  |
|  |  | 9. Organize monthly monitoring CAPBUSS loan to assess recovery rate of 270 beneficiaries |  | Municipality- wide |  |  |  |  |  | - | - |  | 24,000.00 |  |  | - |  | BAC |  | EU, Sefwiman Rural Bank |  |
| Economic Development | Trade, Industry and Tourism | 10. Organize skills training and provision of start up-kits to 735 women and youth to improve their economic empowerment |  | Bibiani |  |  |  |  |  | - | 100,000.00 |  | - |  |  |  |  | BAC |  | CA |  |
| Focus Area: Agriculture and Rural Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Agricultural Services and Management | 11. Organize District Farmers Day Celebration |  | Asawinso |  |  |  |  |  | - | - |  | 70,000.00 |  |  | - - |  | MDA. |  | CA |  |
|  |  | 12. Organize 4 quarterly technical review meeting |  | Bibiani |  |  |  |  |  | - | - |  | 4,080.00 | - |  |  |  | MDA |  | CA |  |
|  |  | 13. Train MDA, MISO and MEO on TEDMAG |  | Bekwai |  |  |  |  |  | 1,500.00 | - |  | - |  |  | - |  | MDA |  | CA |  |
|  |  | 14. Train 25 Technical staff on TEDMAG |  | Humijibre |  |  |  |  |  | 610.00 | - |  | - |  |  | - |  | MDA |  | CA |  |
|  |  | 15. Organize Agriculture sector stakeholder meeting |  | Bibiani |  |  |  |  |  | - | 725.00 |  | - |  |  | - |  | MDA |  | NCCE, ISD |  |
|  |  | 16. Update and intensely the use of mass communication systems and electronic media |  | Municipal wide |  |  |  |  |  | - | - |  | 2,610.00 |  |  | - |  | MDA |  | CA, MoFA & Farmers, |  |
|  |  | 17. Dessiminate 1,152 Extension information through 12 AEAs fortnightly home and farm visits |  | Municipality- wide |  |  |  |  |  | - | - |  | 11,520.00 |  |  | - |  | MDA |  | CA |  |
|  |  | 18. Train 20 farmers (male, female, PWDs, Aged and youth) on nursey management, GAPs |  | Municipal Wide |  |  |  |  |  | - | - |  | 5,000.00 |  |  | - |  | MDA |  | CA, Farmers |  |
|  |  | 19. Sensitize 500 youth in planting for Food and Jobs and other Government initiatives |  | Bibiani |  |  |  |  |  | - | - |  | 4,000.00 |  |  | - |  | MDA |  | CA, Farmers, Staff members |  |
|  |  | 20. Conduct quarterly monitoring by BMAOs and MDA |  | Municipality-Wide |  |  |  |  |  | - | - |  | 13,800.00 |  |  | - |  | MDA |  | CA,MOFA, Statistics Dept. |  |
|  |  | 21. MDA and staff attending workshops, seminars and conferences with other stakeholders |  | Municipality-Wide |  |  |  |  |  | - | - |  | 3,000.00 |  |  | - |  | MDA |  | CA |  |
|  |  | 22. Set-up 2 demonstration farms by 12 AEAs |  | Municipality-Wide |  |  |  |  |  | - | - |  | 2,000.00 |  |  | - |  | MDA |  | CA |  |
|  |  | 23. Organize 2 field days per each demonstration farm by 12 AEAs for 30 farmers |  | Municipality-Wide |  |  |  |  |  | - | - |  | 4,000.00 | - |  |  |  | MDA |  | CA |  |
|  |  | 24. Sensitize and train 20 Ghana School Feeding Caterers on the use of local food ingredients |  | Municipality-Wide |  |  |  |  |  | - | - |  | 2,000.00 |  |  | - |  | MDA |  | C, JICA |  |
| Focus Area: Tourism and Creative Arts Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Trade, Industry and Tourism | 25. Support the preparation and participation of municipal groups at NAFAC |  | Bibiani & Bekwai |  |  |  |  |  | 10,000.00 | - |  | - |  |  | - |  | CA |  | GTA |  |
|  |  | 26. Support the organization of municipal festival of Arts and Culture |  | Selected Schools |  |  |  |  |  | 15,000.00 | - |  | - |  |  | - |  | GES |  | CA |  |
|  |  | 27. Organize inter-schools festival of Arts and Culture |  | Selected Schools |  |  |  |  |  | 10,000.00 | - |  | - |  |  |  |  | GES |  | CA |  |
| DEVELOPMENT DIMENSION 2: SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Education and Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education, Youth & Sports and Library services | 28. Support My 1st Day at school |  | Selected Schools |  |  |  |  |  | 5,000.00 | 10,000.00 |  | - |  |  | - |  | GES |  | MA |  |
|  |  | 29. Organize Inter-schools’ sports and athletic competition |  | Municipality- Wide |  |  |  |  |  | - | 5.000.00 |  | - |  |  | - |  | GES |  | MA |  |
|  |  | 30. Organize mock exams for BECE candidates |  | Municipality- Wide |  |  |  |  |  | 116,160.00 | - |  | - |  |  | - |  | GES |  | MA |  |
|  |  | 31. Re-roofing of Pataboso M/A Primary School |  | Pataboso |  |  |  |  |  | - | 32,000.00 |  | - |  |  | - |  | GES |  | CA |  |
|  |  | 32. Organise Capacity Building for Teachers |  | Bibiani |  |  |  |  |  | 70,000.00 | - |  | - |  |  | - |  | GES |  | CA |  |
|  |  | 33. Furnishing and Provision of Laboratory equipment for Sefwi Bekwai SHS |  | Sefwi Bekwai |  |  |  |  |  | - | 247,135,69 |  | - |  |  | - |  | GES |  | Works |  |
|  |  | 34. Procurement of 1,000 mono desk for basic schools |  | Selected Schools |  |  |  |  |  | - | 100,000.00 |  | 150,000.00 |  |  | - |  | GES |  | CA |  |
|  |  | 35. Procurement of 1,135 dual desk for basic schools |  | Municipality- Wide |  |  |  |  |  | - | 245,500.00 |  | - |  |  | - |  | GES |  | CA |  |
|  |  | 36. Supply of 794 Dual and 360 Mono Desks for Basic Schools |  | Selected Basic Schools |  |  |  |  |  | - | 327,454.40 |  | - |  |  | - |  | GES |  | CA |  |
|  |  | 37. Construction of 1 No. 6-unit Classroom Block with 6-seater pour flash toilet facility and overhead tank, store, office and 240 pieces of furniture for Queens SHS in Anhwiaso |  | Anhwiaso Queens SHS |  |  |  |  |  | 791,936.00 | - |  | - |  |  | - |  | GES |  | CA |  |
| Focus Area: Health and Health Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Service Delivery | Public Health Services and Management | 38. Completion of 1No. CHPs at Surano 'A' |  | Surano 'A' |  |  |  |  |  | 198,391.55 | - |  | - |  |  |  |  | GHS |  | CA |  |
|  |  | 39. Rehabilitate 6 No. broken down boreholes |  | Municipality- Wide |  |  |  |  |  | 120,000.00 | - |  | - | - - |  | - |  | Works |  | CA |  |
|  |  | 40. Support for HIV/ AIDs control Activities |  | Municipality- Wide |  |  |  |  |  | - | - |  | 20,000.00 |  |  | - |  | GHS |  | CA, CSOs |  |
|  |  | 41. Intensify education on HIV/AIDs to reduce stigmatisation |  | Municipality- Wide |  |  |  |  |  | - | - |  | 5,000.00 |  |  | - |  | GHS |  | CA |  |
|  |  | 42. Intensify behavioural change strategies, especially for high risks groups for HIV/AIDS and TB |  | Municipality- Wide |  |  |  |  |  | - | - |  | 5,000.00 |  |  | - |  | GHS |  | CA |  |
|  |  | 43. Support National immunization campaigns and neglected tropical Diseases control programme |  | Municipality- Wide |  |  |  |  |  | - | 10,000.00 |  | - |  |  | - |  | GHS |  | CA, private sector |  |
|  |  | 44. Organise quarterly Public Health Emergency Management Committee meeting |  | Municipality- Wide |  |  |  |  |  | - | 10,000.00 |  | - |  |  | - |  | GHS |  | CA |  |
|  |  | 45. Organise quarterly Municipal Health Committee Meetings |  | Municipality- Wide |  |  |  |  |  | - | 15,000.00 |  | - |  |  | - |  | GHS |  | CA |  |
|  |  | 46. Management of public Health emergencies. i e. disease outbreak, etc. |  | Municipality- Wide |  |  |  |  |  | - | 200,000.00 |  | - |  |  | - |  | GHS |  | CA |  |
|  |  | 47. Support Malaria Control Activities |  | Municipality- Wide |  |  |  |  |  | - | 15,000.00 |  | - |  |  | - |  | GHS |  | CA |  |
|  |  | 48. Distribution of long-lasting insecticide treated net to all households in the municipality |  | Municipality- Wide |  |  |  |  |  | - | 15,000.00 |  | - |  |  |  |  | GHS |  | CA |  | On-Going |
|  |  | 49. Provide public education on solid waste management in 40 communities |  | Municipality-Wide |  |  |  |  |  | - | 20,000.00 |  | 12,000.00 |  |  | - |  | MEHO |  | CA |  |
|  |  | 50. Promote public health education and hygiene in 32 basic schools |  | Municipality- Wide |  |  |  |  |  | - | - |  | 12,000.00 |  |  | - |  | GHS |  | CA |  |
|  |  | 51. Training and screening of 900 food vendors |  | Municipality- Wide |  |  |  |  |  | - | - |  | 12,000.00 |  |  | - |  | MEHO/GHS |  | CA |  |
|  |  | 52. Conduct environmental health /hygiene education in 32 communities |  | Municipality- Wide |  |  |  |  |  | - | 20,000.00 |  | - |  |  | - |  | MEHO/GHS |  | CA |  |
| Social Service Delivery | Public Health Services and Management | 53. Support the establishment of college of health services |  | Anhwiaso |  |  |  |  |  | - | 380,178,00 |  | - |  |  | - |  | GHS |  | CA |  |
|  |  | 54. Organize quarterly sensitizations on Pest and vector control |  | Municipality- Wide |  |  |  |  |  | - | 10,000.00 |  | - |  |  | - |  | MEHO/GHS |  | CA |  |
| Focus Area: Food and Nutrition Security (Fns) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Service Delivery | Public Health Services and Management | 55. Promote nutritionally sensitive and cost effective diet through education and sensitization |  | Municipality- Wide |  |  |  |  |  | - | 5,000.00 |  | 5,000.00 | - |  | - |  | GHS |  | CA |  |
|  |  | 56. Promote the production of diversified, nutrient-rich food and consumption of nutrition foods |  | Municipality- Wide |  |  |  |  |  | 10,000.00 | - |  | - |  |  | - |  | GHS |  | CA |  |
|  |  | 57. Sensitisation to reduce infant and adult malnutrition |  | Municipality- Wide |  |  |  |  |  | 15,000.00 | - |  | - |  |  | - |  | GHS |  | CA |  |
|  |  | 58. Conduct demonstrative engagement on kitchen gardens and balance diets in 10 communities |  | Municipality- Wide |  |  |  |  |  | 10,000 | 10,000 |  | - |  |  | - |  | MDA |  | CA |  |
| Focus Area: Population Management and Migration for Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Public Health Services and management | 59. Organise sensitisation programme on Teenage pregnancy in the Municipality |  | Municipal Wide |  |  |  |  |  | - | 2,000.00 |  | 2,000.00 |  |  | - |  | SWCD |  | NCCE |  |
| Social Services Delivery | Public Health Services and management | 60. Collaborate with immigration service to strengthen immigration data collection within the Municipality |  |  |  |  |  |  |  | - | 5,000.00 |  | 2,000.00 |  |  | - |  | Statistics |  | CA, GIS |  |
| Social Services Delivery | Public Health Services and management | 61. Support for National Immunization Campaigns and Neglected Tropical Disease Control |  | Municipality-Wide |  |  |  |  |  | 10,000.00 | - |  | - |  |  | - |  | GHS |  | CA |  |
| Social Services Delivery | Public Health Services and management | 62. Collaborate with civil society groups and the media to sensitize the youth on the dangers of irregular migration |  | Municipality Wide |  |  |  |  |  | - | 2,000.00 |  | 2,000.00 |  |  | - |  | SW&CD |  | UNICEF |  |
| Focus Area: Reducing Poverty and Inequality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Services | 63. Monitor and coordinate Livelihood Empowerment Against Poverty (LEAP) programme |  | Municipality-Wide |  |  |  |  |  | - | - |  | 4,000.00 |  |  | - |  | SW&CD |  | CA |  |
|  |  | 64. Coordinate activities of School Feeding Programme |  | Beneficiary schools |  |  |  |  |  | - | - |  | 10,000.00 |  |  | - |  | SW&CD |  | CA |  |
|  |  | 65. Provision of Medical Support to the vulnerable |  | Municipality Wide |  |  |  |  |  | - | - |  | 50,000.00 |  |  | - |  | SWCD |  | CA |  |
|  |  | 66. Support 1,000 Vulnerable people to get NHIS Cards |  | Municipality- Wide |  |  |  |  |  | - | - |  | 15,000.00 |  |  | - |  | SWCD |  | CA |  |
| Focus Area: Water and Environmental Sanitation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | Public Works, Rural Housing and Water Management | 67. Construction & Mechanization of 5 Boreholes with overhead tank |  | Aboduabo, Nzema Nkwanta, Adzenkye, Surano “A’ |  |  |  |  |  | 217,135.30 | - |  | - | 0- |  |  |  | Works Dept. |  | CA, CWSA |  |
|  |  | 68. Construction & Mechanization of 6 Boreholes with overhead tank |  | Gov’t. Hospital, Degede, Ahodwo, Breman, Bibiani Market & Bibiani Police Station |  |  |  |  |  |  |  |  | 90,000.00 |  |  |  |  | Works |  | CWSA |  |
|  |  | 69. Construction of 1 No. 12- Seated Pour Flush Toilet |  | Chirano |  |  |  |  |  | - | 218,502.38 |  | - | - |  |  |  | Works |  | CA |  |
| Social Services Delivery | Environmental Health and Sanitation Services | 70. Formation and training of WATSANS members in 10 communities |  | Selected Communities |  |  |  |  |  | 10,000.00 | - |  | - |  |  | - |  | Works |  | CA |  |
|  |  | 71. Acquisition of land for final disposal site |  | Bibiani & Bekwai |  |  |  |  |  | 52,000.00 | - |  | - |  |  | - |  | Works |  | CA |  |
|  |  | 72. Solid and liquid waste management, Disinfestation, Manage wasteland fills contract with Zoomlion |  | Municipal Wide |  |  |  |  |  | 300,000.00 | - |  | - |  |  | - |  | EHU |  | MA, Zoomlion |  |
|  |  | 73. Construction of Slaughter House |  | Bibiani |  |  |  |  |  | 400,000.00 | - |  | - |  |  | - |  | EHU |  | CA |  |
|  |  | 74. Monitoring of sanitation services |  | Municipality-Wide |  |  |  |  |  | - | 15,000.00 |  | - |  |  | - |  | EHSU |  | CA |  |
|  |  | 75. Quarterly meeting with Sanitation Service Providers |  | Bibiani |  |  |  |  |  | - | 12,000.00 |  | - |  |  | - |  | EHSU |  | CA |  |
|  |  | 76. Sensitization of the general public on air quality and noise pollution in the municipality |  | Municipality-wide |  |  |  |  |  | - | 15,000.00 |  | - |  |  | - |  | EHSU |  | CA |  |
|  |  | 77. Promote household toilet construction (CLTS) |  | Selected Communities |  |  |  |  |  | - | 20,000.00 |  | - |  |  | - |  | EHSU |  | CA |  |
|  |  | 78. Compilation/Gazetting of Assembly Bye Law |  | Municipality-Wide |  |  |  |  |  | - | 12,000.00 |  | - |  |  | - |  | EHSU |  | CA |  |
|  |  | 79. Quarterly Performance Review Meeting with Environmental Health Zonal Heads |  | Bibiani |  |  |  |  |  | - | 3000.00 |  | - |  |  | - |  | EHSU |  | CA |  |
| Focus Area: Child Protection and Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Services | 80. Formation of Community Child Protection Committees in 10 Child labour endemic communities and train them on child labour issues |  | Selected Towns |  |  |  |  |  | - | 2,000.00 |  | 10,000.00 |  |  | - |  | SW&CD |  | CA, NGOs |  |
|  |  | 81. Organize sensitization programmes on child labour |  | Bibiani |  |  |  |  |  | 20,000.00 | - |  | 20,000.00 |  |  | - |  | SW&CD |  | CA, NGOs |  |
|  |  | 82. Remediation support for children |  |  |  |  |  |  |  | 10,000.00 | - |  | 20,000.00 |  |  | - |  | SW&CD |  | CA, NGOs |  |
| Focus Area: Gender Equality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Services |  | 83. Organise sensitisation programme on the need to involve women in decision making and participation in local governance | Municipal wide |  |  |  |  |  | 12,000.00 | 2,000.00 |  | - |  |  | - |  | SW&CD |  | MA, NGOs |  |
|  |  |  | 84. Organise sensitization programme on Persistent negative discriminatory socio-cultural, traditional beliefs and customary practices against women | Bibiani |  |  |  |  |  | 5,000.00 | - |  | 5,000.00 |  |  | - |  | SW&CD |  | CA, NGOs |  |
|  |  |  | 85. Organize skills training and income generating activities for 80 women and groups to improve their economic empowerment | Municipal Wide |  |  |  |  |  | 15,000.00 | - |  | 15,000.00 |  |  | - |  | SWCD |  | CA NGO’s BAC |  |
| Focus Area: Sports and Recreation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education, youth &sports and library services | 86. Organize football competition among communities in the municipality |  | Municipality-wide |  |  |  |  |  | - | 20,000.00 |  | - |  |  | - |  | CA |  | NGOs |  |
| Focus Area: Social Protection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Welfare and Community Services | 87. Organize radio programme on child right and child protection issue |  | Bibiani |  |  |  |  |  | 2,000.00 | - |  | 5,000.00 |  |  | - |  | SW& CD |  | CA |  |
| Focus Area: Disability-Inclusive Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Welfare and Community Services | 88. Organize Advocacy & awareness creation on the rights & responsibilities of PWDs |  | Bibiani |  |  |  |  |  | 2,000.00 | - |  | - |  |  | - |  | SW& CD |  | CA, PWDs |  |
|  |  | 89. Provide educational/ apprenticeship support to PWDs |  | Municipality-wide |  |  |  |  |  | 10,000.00 | - |  | - | - |  | - |  | SW& CD |  | CA, PWDs |  |
|  |  | 90. provide medical /assistive device to PWDs |  | Municipality-wide |  |  |  |  |  | 10,000.00 | - |  | - | - |  | - |  | SW& CD |  | CA, PWDs |  |
|  |  | 91. Strengthening the registration of persons with Disability |  | Bibiani |  |  |  |  |  | 18,000.00 | - |  | - |  |  | - |  | SW& CD |  | CA, PWDs |  |
|  |  | 92. Procure items such as fridges, tricycles, start-ups etc., to support PWDs to enter into income generation activities |  | Bibiani |  |  |  |  |  | 60,000.00 | - |  | - |  |  | - |  | SW& CD |  | CA, PWDs |  |
|  |  | 93. Organize focus group discussions on home management, environmental cleanness and personal hygiene in 10 communities |  |  |  |  |  |  |  | 10,000.00 | - |  | - |  |  | - |  | SWCD |  | CA |  |
| Focus Area: Employment and Decent Work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Services | 94. Support government flagship programmes such as NABCO &YEA |  | Bibiani |  |  |  |  |  | 20,000.00 | - |  | - |  |  | - |  | YEA |  | CA, NABCO |  |
| DEVELOPMENT DIMENSION 3: ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Protected Areas |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Management | 95. Facilitate alternative livelihoods including eco-tourism support schemes for fringe communities along protected areas |  | Chine, Anhwiaso, Aboduabo, Asawinso |  |  |  |  |  | 2,000.00 | - |  | 10,000.00 |  |  | - |  | FC |  | CA, NGOs, CSO, Traditional Authority |  |
|  |  | 96. Monitor forest reserves to prevent illegal logging |  | Forest Reserves |  |  |  |  |  | 20,000.00 | - |  | - |  |  | - |  | FC |  | Chiefs, MA |  |
| Focus Area: Mineral Extraction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Management | 97. Regulate the implementation of community mining activities |  | Selected communities |  |  |  |  |  | 10,000.00 | - |  | - |  |  | - |  | NADMO |  | MA, NGOs, CSO, Chiefs Minerals Commission |  |
|  |  | 98. Organize sensitization programme on illegal mining, deforestation and land reclamation |  | Selected communities |  |  |  |  |  | - | 20,000.00 |  | - | - |  | - |  | NADMO |  | CA, NGOs, CSO, Chiefs Minerals Commission |  |
| Infrastructure Maintenance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | Public works, rural housing and water management | 99. Installation of Street lights |  | Selected communities |  |  |  |  |  | - | 75,600.00 |  | - |  |  | -- |  | Works |  | CA |  |
| Infrastructure Development and Management | Public works, rural housing and water management | 100. Extension of electricity to Ntakam, Akaasu & Akaaso CHPS Compound |  | Ntakam, Akaasu & Akaasu |  |  |  |  |  | - | 39,430.00 |  | - |  |  |  |  | Works |  | CA |  |
|  |  | 101. Renovation of National Ambulance Unit and Fire Tender sation in Sefwi Bekwai |  | Bekwai |  |  |  |  |  | - | 180,000.00 |  | - |  |  | - |  | Works |  | GNFS |  |
| Focus Area: Water Resources Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Management | 102. Enforcement of development control on water bodies |  | Municipal wide |  |  |  |  |  | 10,000.00 | - |  | - |  |  | - |  | Works |  | CA, NGOs, CSO, Chiefs, Minerals Commission |  |
|  |  | 103. Dredging of River Chira Stream Chennel |  | Chira |  |  |  |  |  | - | 45,000.00 |  | - |  |  | - |  | Works |  | NADMO |  |
| Focus Area: Environmental Pollution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Management | 104. Enforce environmental laws and regulations to prevent noise pollution |  | Municipal Wide |  |  |  |  |  | - | - |  | 2,000.00 |  |  | - |  | MEHU |  | MA, NGOs, CSO, MWST, NADMO |  |
| Focus Area: Deforestation, Desertification and Soil Erosion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Management | 105. Establishment of forest plantations in degraded forest land through Modified Taungya and industrial plantation |  | Anhwiaso, Aboduabo |  |  |  |  |  | 10,000.00 | - |  | - |  |  | - |  | Forestry Commission |  | CA |  |
|  |  | 106. Promote the use of LPG as alternative sources of energy by households |  | Municipal wide |  |  |  |  |  | 4,000.00 | - |  | - |  |  | - |  | NADMO |  | Forestry Commission |  |
|  |  | 107. Train farmers on climate smart agriculture technologies |  | Municipal Wide |  |  |  |  |  | 5,000.00 | - |  | - |  |  | - |  | MDA |  | CA, NGOs, CSO, NADMO |  |
| Focus Area: Climate Variability and Change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Mgt. | 108. Organize sensitization and community durbar on climate change in 10 Communities |  | Selected towns |  |  |  |  |  | 2,000.00 | - |  | - |  |  | - |  | NADMO |  | CA, NGOs, CSO, Mineral Commission |  |
|  |  | 109. Planting of 7,000 assorted tree seedlings to support to promote afforestation in off reserve areas |  | Municipal wide |  |  |  |  |  |  |  |  | 20,000.00 |  |  |  |  | Forestry Commission |  | CA |  |
|  |  | 110. Support Planting of 400,000 assorted tree seedlings across the municipality under the green Ghana programme |  | Municipal wide |  |  |  |  |  | - | - |  | 100,000.00 |  |  | - |  | Forestry Communities |  | NADMO |  |
| Focus Area: Disaster Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Disaster Prevention and management | 111. Formation of Disaster Risk Reduction clubs in 20 schools |  | Selected Schools |  |  |  |  |  | 2,000.00 | - |  | 5,000.00 |  |  | - |  | NADMO |  | Transport Unions, NGOs, CSO, MWST, NADMO |  |
|  |  | 112. Organize community sensitization on domesetic and bush fires |  | Selected Towns |  |  |  |  |  | 3,000.00 | - |  | 3,000.00 |  |  | - |  | NADMO |  | GNFS, CA |  |
| Environmental Management | Disaster Prevention and management | 113. Maintenance of fire Tenders |  | Municipal Wide |  |  |  |  |  | 20,000.00 | - |  | 25,000.00 |  |  | - |  | CA |  | GNFS |  |
| Environmental Management | Disaster Prevention and management | 114. Organize community education programme on hydrometer disaster |  | Municipal Wide |  |  |  |  |  | 2,000.00 | - |  | - |  |  |  |  | NADMO |  | CA |  |
| Focus Area: Transportation: Road & Road Safety |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | Urban roads and transport services | 115. Reshape 100 km of feeder roads/ Rehabilitate old bridges |  | Municipal Wide |  |  |  |  |  | 300,000.00 | 100,000.00 |  | - |  |  | - |  | Works |  | Urban Roads |  |
|  |  | 116. Sensitization on Road Safety policy for drivers and user |  | Municipal Wide |  |  |  |  |  | 10,000.00 | - |  | - |  |  | - |  | Works |  | Urban Roads |  |
|  |  | 117. De-silting of drains |  | Bibiani |  |  |  |  |  | 35,000.00 | - |  | - |  |  |  |  | Works |  | Urban Roads |  |
|  |  | 118. Potholes Patching |  | Bibiani |  |  |  |  |  | 350,000.00 | - |  | - |  |  |  |  | Works |  | Urban Roads |  |
|  | Urban roads and transport services | 119. Grass Cutting |  | Bibiani |  |  |  |  |  | 35,000.00 | - |  | - |  |  |  |  | Works |  | Urban Roads |  |
|  |  | 120. Grading of Town Road |  | Bibiani |  |  |  |  |  | 140,000.00 | - |  | - | \ |  |  |  | Works |  | Urban Roads |  |
|  |  | 121. Construction of 3 No. culverts at Praga, Dansokrom & Kojina |  | Praga, Dansokrom & Kojina |  |  |  |  |  |  | 80,000.00 |  | - | - |  |  |  | Works |  | Urban Roads |  |
| Focus Area: Information Communication Technology Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | ICT | 122. Organize ICT training for the 100 youth |  |  |  |  |  |  |  | 5,000.00 | 5,000.00 |  | - |  |  | - |  | CA |  | CA, NGOs |  |
| Focus Area: Human Settlements Development and Housing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | Spatial Planning | 123. Continue the street naming and property addressing |  | Bekwai, Awaso, Bibiani Extension |  |  |  |  |  | 100,000.00 | - |  | 100,000.00 |  |  | - |  | Physical Planning |  | CA, TA, SPC |  |
|  |  | 124. Conduct Revision and Preparation of local plan |  | Bibiani Extension/ Lineso |  |  |  |  |  | 200,000.00 | - |  | - |  |  | - |  | Physical Planning |  | CA, TA, SPC |  |
|  |  | 125. Landscaping and Gardening |  | Bibiani |  |  |  |  |  |  | 5,000.00 |  | - |  |  | - |  | Physical Planning |  | CA, TA, SPC |  |
|  |  | 126. Undertake building inspections to ensure compliance with the national building code |  | Municipal Wide |  |  |  |  |  |  | 20,000.00 |  | - |  |  | - |  | Works |  | CA, SPC |  |
| Focus Area: Drainage and Flood Control |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | Public Works, Rural Housing and Water Management | 127. Construction of 6m foot bridge |  | Gee Akurase |  |  |  |  |  | 150,000.00 | - |  | - |  |  | - |  | Works |  | CA |  |
|  |  | 128. Rehabilitation/Reshaping of feeder roads (40km) |  | Municipal wide |  |  |  |  |  | 100,000.00 | - |  | - |  |  | - |  | Works |  | CA |  |
| DEVELOPMENT DIMENSION 4: GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Local Governance and Decentralisation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | General Administration | 129. Organize Statutory meetings (Management Meetings, Sub-Committee, Executive Committee & General Assembly Meetings, SAT Meetings etc.) |  | Bibiani |  |  |  |  |  | - | 300,000.00 |  | - |  |  | - |  | CA |  | MLGDRD |  |
|  |  | 130. Internal management of organization (utility, fuel, call credit, hotel accommodation, NALAG dues etc.) |  | Bibiani |  |  |  |  |  | - | 50,000.00 |  | - |  |  | - |  | CA |  | MLRDRD |  |
|  |  | 131. Maintenance of office equipment |  | Bibiani |  |  |  |  |  | 20,000.00 | 30,000.00 |  | - |  |  | - |  | CA |  | MLGDRD |  |
|  |  | 132. Rehabilitation of Assembly Offices |  | Bibiani |  |  |  |  |  | 120,000.00 | - |  | - |  |  | - |  | Works |  | CA |  |
|  |  | 133. Maintenance of Assembly Vehicles |  | Bibiani |  |  |  |  |  | 30,000.00 | 20,000.00 |  | - |  |  | - |  | CA |  | MLGDRD |  |
|  |  | 134. Procurement of Office Equipment/logistics (6-No servers, 6-No laptops, UPS & Networking Equipment) |  | Bibiani |  |  |  |  |  | 50,000.00 | - |  | - |  |  | - |  | CA |  | MLGDRD |  |
|  |  | 135. Procurement of 2 No. Dell Servers, 1 No. External Hard Disk Drive (2TB) and 1 No. Private Branch Exchange (PBX) |  | Bibiani |  |  |  |  |  | 20,000.00 | - |  | - |  |  | - |  | CA |  | MLGDRD |  |
| Management and Administration | General Administration | 136. Procure 1 No. office desktop and 3 No. laptop computers for administrative unit, development planning, procurement and works department |  | Bibiani |  |  |  |  |  | 16,800.00 | - |  | - |  |  | - |  | CA |  | MLGDRD |  |
|  |  | 137. Support to Self Help Projects |  | Municipal Wide |  |  |  |  |  | 200,000.00 | - |  | - |  |  | - |  | CA |  | Works |  |
|  |  | 138. Support the sub-structures in the Municipality/ |  | Zonal Councils |  |  |  |  |  | 250,000.00 | - |  | - |  |  | - |  | CA |  | MLGDRD |  |
|  |  | 139. Rehabilitation of Assembly Bungalows |  | Bibiani |  |  |  |  |  | 60,000.00 | - |  | - |  |  | - |  | Works |  | CA |  |
|  |  | 140. Provision, Installation and Maintenance of Streetlight to Bibiani and Bekwai Township |  | Bibiani & Bekwai |  |  |  |  |  | 270,616.80 |  |  | - |  |  | - |  | Works |  | CA |  |
|  |  | 141. Support Decentralized Dept. and WNRCC |  | Bibiani |  |  |  |  |  | 50,000.00 |  |  | - |  |  | - |  | CA |  | MLGDRD |  |
|  |  | 142. Implement Capacity building plan/Staff development |  | Bibiani |  |  |  |  |  | 50,000.00 | 10,000.00 |  | - |  |  | - |  | HRM |  | CA |  |
|  |  | 143. Internal Management of organization (Utility, fuel, call credit, Hotel Accommodation, NALAG Dues etc.) |  | Bibiani |  |  |  |  |  | 50,000.00 | 50,000.00 |  | - |  |  | - |  | CA |  | MLGDRD |  |
|  |  | 144. Organize 1 No. training programme for 54 Assembly Members and 15 heads of department on basic principles of administrative laws and processes involved in the enactment of bye-laws and prosecution of offenders. |  | Bibiani |  |  |  |  |  | 25,000.00 | - |  | - |  |  | - |  | HRM |  | CA |  |
|  |  | 145. Organize 1 No. training programme for 10 administrative staff and 25 heads of department on modern techniques in minutes taking and report writing skills |  | Bibiani |  |  |  |  |  | 17,578.00 | - |  | - |  |  | - |  | CA |  | MLGDRD |  |
| Management and Administration | Planning, Budgeting, Monitoring & Evaluatio | 146. Organize quarterly MPCU meetings |  | Bibiani |  |  |  |  |  | 30,000.00 | 10,000.00 |  | - |  |  | - |  | CA |  | MLGDRD |  |
|  |  | 147. Preparation of 2023 composite budget and fee-fixing resolution |  | Bibiani |  |  |  |  |  | 25,000.00 | - |  | - |  |  | - |  | CA |  | MLGDRD |  |
| Management and Administration | Finanace | 148. Enumeration of ratable properties/ Data Collection |  | Municipality-wide |  |  |  |  |  |  | 10,000.00 |  | 50,000,00 |  |  | - |  | Statistics |  | CA |  |
|  |  | 149. Conduct monthly market readings at Sefwi Bekwai and Bibiani |  | Bibiani & Bekwai |  |  |  |  |  | 5,000.00 | - |  | - |  |  | - |  | Statistical Service Dept. |  | CA |  |
|  |  | 150. Build Municipal administration data hub comprising of all departments and agencies, |  | Bibiani |  |  |  |  |  | 15,000.00 | - |  | - |  |  | - |  | Statistics Service Dept. |  | CA |  |
| Focus Area: Public Accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Planning, Budgeting, Monitoring & Evaluation | 151. Organize Social Accountability Fora ie. Town Hall meeting, Meet the Press & Social Audit |  | Bibiani & Bekwai |  |  |  |  |  | 40,000.00 | 10,000,00 |  |  |  |  |  |  | CA |  | MLGDRD |  |
| Focus Area: Human Security and Public Safety |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | General Administration | 152. Support for Security operations & MUSEC activities |  | Bibiani |  |  |  |  |  | 30,000,00 | 10,000.00 |  | - | - |  |  |  | CA |  | MLGDRD |  |
| Focus Area: Corruption and Economic Crimes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | General Administration | 153. Support Anti- Corruption Agencies /Implement NACAP |  | Municipal wide |  |  |  |  |  | 10,000.00 | - |  | - |  |  | - |  | CA |  | CHRAJ, Audit Service, NCCE,NGOs |  |
| Focus Area: Civil Society, And Civic Engagement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | General Administration | 154. Conduct Stakeholders /management meetings |  | Area council capitals |  |  |  |  |  | 5,000.00 | 5,000.00 |  | - |  |  | - |  | CA |  | MLGDRD |  |
| DEVELOPMENT DIMENSION 5: EMERGENCY PLANNING AND PREPAREDNESS (INCLUDING COVID-19 RECOVERY PLAN) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Biological |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Public Health Services and management | 155. Organize sensitization and education programmes on Covid-19 and enforcement of safety protocols |  | Municipality- wide |  |  |  |  |  | 20,000.00 | 10,000.00 |  | - |  |  | - |  | NADMO |  | CA |  |
|  |  | 156. Support Municipal Public Health Emergency Management Committee &Municipal Public Health Emergency Rapid Response Team activities |  | Bibiani |  |  |  |  |  | 20,000.00 | - |  | - |  |  | - |  | GHS |  | CA |  |
|  |  | 157. Vaccination against public health emergencies such as Covid-19 |  | Municipal wide |  |  |  |  |  | 10,000.00 | - |  | - |  |  | - |  | GHS |  | CA |  |
| Focus Area: Anthropogenic |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Public Health Services and management | 158. Organize disaster mitigation public awareness programmes |  | Selected communities |  |  |  |  |  | 5,000.00 | 2,000.00 |  | - |  |  |  | - |  | NADMO |  | CA / GHS |  |  |  |
| Relief Assistance and Victim Welfare |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Disaster Prevention and management | 159. Support disaster victims with relief items |  | Municipal wide |  |  |  |  |  | 100,000.00 | - |  | - |  |  |  | - |  | NADMO |  | CA, NGOs |  |  |  |
| DEVELOPMENT DIMENSION 6: IMPLEMENTATION, COORDINATION, MONITORING AND EVALUATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Planning, Budgeting, Monitoring & Evaluation | 160. Conduct PM&E of programmes on projects |  | Selected Towns |  |  |  |  |  | 50,000.00 |  | - | - |  |  | - |  | CA |  | MLGDRD |  |
|  |  | 161. Monitor 2022 budget implementation and participate in 2023 Composite Budget hearings |  | Bibiani |  |  |  |  |  | 15,000 |  | - | - |  |  | - |  | CA |  | MLGDRD |  |
|  |  | 162. Undertake mid-year review of 2022 Action Plan and Programme Based Budget |  | Bibiani |  |  |  |  |  | 5,000.00 |  | - | - |  |  | - |  | CA |  | MLGDRD |  |
|  |  | 163. Provision of matching funds for donor related projects and programmes. |  | Bibiani |  |  |  |  |  | 2,000.000.00 |  | - | - |  |  | - |  | CA |  | MLGDRD |  |
| Management and Administration | Planning, Budgeting, Monitoring & Evaluation | 164. Organize sensitization workshops for LED Stakeholders and platforms for selected LED products |  | Bibiani |  |  |  |  |  | 17,000,00 |  | - | - |  |  | - |  | BAC |  | CA |  |
|  |  | 165. Organize quarterly LED platform / Business forum for stakeholders to enhance business growth |  | Bibiani |  |  |  |  |  | 40,000.00 |  | - | - |  |  | - |  | BAC |  | CA |  |
|  |  | 166. Organize annual progress report preparation sessions for departmental heads |  | Bibiani |  |  |  |  |  | 10,000.00 |  | - | - |  |  |  |  | CA |  | MLGDRD |  |
| Total |  |  |  |  |  |  |  |  |  | 5,952,135.85 |  | 2,123,002.38 | 1,749,647.00 | 9,824,785.23 |  |  |  |  |  |  |  |

Table 5.2 Annual Action Plan for 2023

Composite Annual Action Plan for 2023

| Programme (PBB) | Sub- Programme (PBB) | Broad Activities |  | Location | Time Frame |  |  |  |  |  |  | Cost |  |  |  |  | Programme Status |  |  |  | Implementing Institution |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 |  |  | Q2 | Q3 |  | Q4 | GoG (GH¢) |  | IGF (GH¢) |  | Others (GH¢) | New |  | On-going |  | Lead |  | Collaborating |  |
| DEVELOPMENT DIMENSION 1: ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Strong and Resilient Economy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Finance | 1. Train revenue collectors and key staff on revenue collection strategies |  | Bibiani |  |  |  |  |  |  |  | - |  | 15,000.00 |  | 5,000.00 |  |  | - |  | Finance |  | CA, GIZ |  |
| Management | Finance | 2. Update the list of ratable properties and businesses to enhance revenue mobilization |  | Municipal Wide |  |  |  |  |  |  |  | - |  | 30,000.00 |  | - |  |  | - |  | Finance Dept./ |  | CA |  |
| Focus Area: Private Sector Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Trade, Industry and Tourism | 3, Organize monthly business counselling sections and follow-ups for 300 SMEs |  | Municipality- wide |  |  |  |  |  |  |  | 20,000.00 |  | 30,000.00 |  | 10,000.00 |  |  | - |  | BAC |  | CA |  |
|  |  | 4. Organize basic skills training in soap making 100 unemployed women and youth |  | Municipality-Wide |  |  |  |  |  |  |  | 20,000.00 |  | 30,000.00 |  | - |  |  | - |  | BAC |  | CA, Donors |  |
|  |  | 5. Organize basic management training for 250 SMEs and business associations in entrepreneurship |  | Municipality- wide |  |  |  |  |  |  |  | 20,000.00 |  | 20,000.00 |  | 10,000.00 |  |  | - |  | BAC |  | CA, RTF, Donors |  |
|  |  | 6.Facilitate access to credit facilities by 100 SMEs from the financial institutions |  | Municipality wide |  |  |  |  |  |  |  | 30,000.00 |  | - |  | - |  |  | - |  | BAC |  | CA |  |
|  |  | 7. Conduct monthly exercise for 200 CAPBUSS loan beneficiaries to assess the recovery rate |  | Municipality- wide |  |  |  |  |  |  |  | - |  | - |  | 24,000.00 |  |  | - |  | BAC |  | Sefwiman Rural Bank |  |
|  |  | 8. Organize quarterly LED platform meetings / business forum to improve business growth |  | Municipality- wide |  |  |  |  |  |  |  | - |  | 36,000.00 |  | - |  |  | - |  | BAC |  | Financial Institutions, |  |
| Focus Area: Agriculture and Rural Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 21Economic Development | Agricultural Services and Management | 9. Organize District Farmers Day Celebrations |  | Selected Community |  |  |  |  |  |  |  | 70,000.00 |  | - |  | - |  |  | - |  | MDA |  | CA |  |
|  |  | 10. Disseminate Extension Information through 15 AEAs fortnightly home and farm visits including Vet AEAs |  | Municipality- wide |  |  |  |  |  |  |  | 10,800.00 |  | - |  | - |  |  | - |  | MDA |  | CA |  |
|  |  | 11. Conduct monitoring, MDA and Municipal Assembly officers |  | Municipality- wide |  |  |  |  |  |  |  | 8,000.00 |  | - |  | - |  |  | - |  | MDA |  | CA |  |
|  |  | 12. Train 10 pig farmers (male, female & youth) on feed formulation |  | Municipal Wide |  |  |  |  |  |  |  | 2,000.00 |  |  |  | - |  |  | - |  | MDA |  | CA |  |
|  |  | 13. Train 15 farmers (male, female, and youth on IMO technology |  | Bibiani |  |  |  |  |  |  |  | 2,495.00 |  | - |  | - |  |  | - |  | MDA |  | CA |  |
|  |  | 14. Follow up visit to 30 rice farmers PWD, Aged and Youth by MDA, MIS. |  | Municipality- wide |  |  |  |  |  |  |  | 1,800.00 |  | - |  | - |  |  | - |  | MDA |  | CA |  |
|  |  | 15. Train 15 farmers (male, female and youth) on climate smart Agriculture |  | Municipality- wide |  |  |  |  |  |  |  | 3,000.00 |  | - |  | - |  |  | - |  | MDA |  | CA |  |
|  |  | 16. Train 60 farmers (women PWD, youth) in post-harvest management of cereal crops |  | Municipality- wide |  |  |  |  |  |  |  | 6,000.00 |  | - |  | - |  |  | - |  | MDA |  | CA |  |
|  |  | 17. Organize monitoring visits by MDA and MAQ visits |  | Municipality- wide |  |  |  |  |  |  |  | 4,560.00 |  | - |  | - |  |  | - |  | MDA |  | CA |  |
|  |  | 18. Sensitize and Train 20 farmers (women, PWD, youth) on the use of local food ingredients and Nutrition |  | Municipality- wide |  |  |  |  |  |  |  | 5,000.00 |  | - |  | - |  |  | - |  | MDA |  | CA |  |
|  |  | 19. Support for Planting for Food and Jobs (PFJs) &Planting for Export and Rural Development (PERD) and other agricultural programme. |  | Municipality- wide |  |  |  |  |  |  |  | 56,000.00 |  | - |  | - |  |  | - |  | MDA |  | CA |  |
|  |  | 20. Attend Regional meetings, workshops, seminars and conference with other stakeholder’s engagements by MDA, MACs, driver and other staff |  | Municipality- wide |  |  |  |  |  |  |  | 6,000.00 |  | - |  | - |  |  |  |  | MDA |  | CA |  |
|  |  | 21. Facilitate the signing of MOUs between 10-member Rice FBO and market women |  | Bibiani |  |  |  |  |  |  |  | 1,000.00 |  | - |  | - |  |  | - |  | MDA |  | CA |  |
|  |  | 22. Sensitization of 100 livestock farmers (male, female, PWD, Youth) on vaccination of Pets against Rabies and PPR by December 31st 2023 |  | Municipality- wide |  |  |  |  |  |  |  | 2,500.00 |  | - |  | - |  |  |  |  | MDA |  | CA |  |
|  |  | 23. Train 60 female farmers on feeding from the 4-star food groups |  | Municipality- wide |  |  |  |  |  |  |  | 3,857.00 |  | - |  | - |  |  |  |  | MDA |  | CA |  |
|  |  | 24. Organize 2 technical Review Meeting by the MIS officer |  | Bibiani & Bekwai |  |  |  |  |  |  |  | 2,400.00 |  | - |  | - |  |  |  |  | MDA |  | CA |  |
|  |  | 25. Train 10 fish farmers (male, female & youth) on good aquaculture practices |  | Municipality- wide |  |  |  |  |  |  |  | 2,000.00 |  | - |  | - |  |  |  |  | MDA |  | CA |  |
|  |  | 26. Train 20 female farmers, PWD and youth on food safety and environmental hygiene |  | Municipality- wide |  |  |  |  |  |  |  | 2,000.00 |  | - |  | - |  |  |  |  | MDA |  | CA |  |
|  |  | 27.Internal Management of organization (utility bills, electricity, water, office supplies, internet bundles etc) |  | Municipality- wide |  |  |  |  |  |  |  | 4,800.00 |  | - |  | - |  |  |  |  | MDA |  | CA |  |
|  |  | 28.Train 15 farmers and 10, Agro, inputs dealers (women, PWD, youth) illegal chemicals and potential health effects of pesticides |  | Municipality- wide |  |  |  |  |  |  |  | 2,300.00 |  | - |  | - |  |  | - |  | MDA |  | CA |  |
| Economic Development | Agricultural Services and Management | 29. Train 25 Female Farmers, PWD, youth) on alternative source of livelihoods power zone preparation |  | Municipality- wide |  |  |  |  |  |  |  | 2,000.00 |  | - |  | - |  |  | - |  | MDA |  | CA |  |
| Economic Development | Agricultural Services and Management | 30.Runing and maintenance of 12 official Motorbikes for MAOs and AEAs (insurance, roadworthy and fuel allowance) |  | Bibiani |  |  |  |  |  |  |  | 1, 860.00 |  | - |  | - |  |  |  |  | MDA |  | CA |  |
| Economic Development | Agricultural Services and Management | 31. Quarterly Runing and Maintenance of official vehicle (insurance, roadworthy, purchase of safety guard) |  | Bibiani |  |  |  |  |  |  |  | 6,000.00 |  | - |  | - |  |  |  |  | MDA |  | CA |  |
| Economic Development | Agricultural Services and Management | 32.Repairs and maintenance of office and MDA premises – painting, leakages, toilet facilities, pipelines and water systems |  | Municipality- wide |  |  |  |  |  |  |  | 21,000.00 |  | - |  | - |  |  |  |  | MDA |  | CA |  |
| Economic Development | Agricultural Services and Management | 33. Train 10 female farmers and youth in snail rearing as an alternative source of livelihoods |  | Bibiani |  |  |  |  |  |  |  | 2,375.00 |  | - |  | - |  |  | - |  | MDA |  | CA |  |
| Economic Development | Agricultural Services and Management | 34. Train 20 female FBO members on the dynamics of group formation and records / data collection |  | Humijibre |  |  |  |  |  |  |  | 3,200.00 |  | - |  | - |  |  | - |  | MDA |  | CA |  |
| Economic Development | Agricultural Services and Management | 35. Train 20 female, PWD and youth on processing and packaging of plantation into CHIPS |  | Bekwai |  |  |  |  |  |  |  | 2,000.00 |  | - |  | - |  |  | - |  | MDA |  | CA |  |
| Focus Area: Tourism and Creative Arts Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Trade, Industry and Tourism | 36. Project Independence Day celebration |  | Municipal wide |  |  |  |  |  |  |  | - |  | 20,000.00 |  | 50,000.00 |  |  | - |  | CA |  | Private Sector |  |
|  |  | 37. Organize radio sensitizations to educate public on issues including marriage rites and puberty rights |  | Bibiani & Bekwai |  |  |  |  |  |  |  | - |  | 20, 000.00 |  | - |  |  | - |  | Dept. of Arts & Culture |  | CA |  |
| Economic Development | Economic Development | 38. Establishment of an Arts center to promote local Arts & Culture |  | Bibiani |  |  |  |  |  |  |  | - |  | 20,000.00 |  | - |  |  | - |  | Dept. of Arts & Culture |  | CA |  |
| Economic Development | Economic Development | 39. Organize 2023 Municipal Festival of Arts and Culture |  | Bibiani |  |  |  |  |  |  |  | - |  | 90,000.00 |  | - |  |  | - |  | Dept. of Arts & Culture |  | CA |  |
| DEVELOPMENT DIMENSION 2: SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Education and Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 40. Construction of 1 No. 6-Unit Classroom Block with office, Store, and 5-Seater WC toilet facility at Queens SHS |  | Anhwiaso |  |  |  |  |  |  |  | 791,920.30 |  | - |  | - |  |  | - |  | GES |  | Works |  |
|  |  | 41. STMIE for 30 students from selected schools |  | Municipal wide |  |  |  |  |  |  |  | - |  | 20,000.00 |  | 27,000.00 |  |  | - |  | GES |  | MA, Private sector |  |
|  |  | 42. Construct 1 No. 3-Unit Classroom Block with Office. Store, 5-seater pour flush toilet facility and 120 No. Dual Desks for Debiso M/A Primary School |  | Debiso |  |  |  |  |  |  |  | 495,774.00 |  | - |  | - |  |  | - |  | GES |  | Works |  |
|  |  | 43. Supply 400 pieces of Dual Desks for selected basic schools in the Municipality |  | Municipality-Wide |  |  |  |  |  |  |  | 180,000.00 |  | - |  | - |  |  | - |  | GES |  | Works |  |
|  |  | 44. Mock exams for BECE candidates |  | Municipal wide |  |  |  |  |  |  |  | 153,000.00 |  | - |  | - |  |  | - |  | GES |  | CA |  |
|  |  | 45. Organize Inter-schools’ sports and athletic competition |  | Municipal Wide |  |  |  |  |  |  |  | - |  | 30,000.00 |  | - |  |  | - |  | GES |  | CA |  |
|  |  | 46. Organise capacity building for Teachers |  | Bibiani |  |  |  |  |  |  |  | 20,000.00 |  | - |  | 20,000.00 |  |  | - |  | GES |  | CA |  |
|  |  | 47. Supply of 1,000 Mono Desks for schools |  | Selected Schools |  |  |  |  |  |  |  | - |  | - |  | 82,916.25 |  |  | - |  | GES |  | CA |  |
|  |  | 48. Supply of 1,135 Dual Desk for schools |  | Selected Schools |  |  |  |  |  |  |  |  |  |  |  | 50,830.08 |  |  |  |  |  |  |  |  |
|  |  | 49. Supply of 500 No. Mono Desks for Queens and Chirano SHS |  | Queens & Chirano SHS |  |  |  |  |  |  |  | 154,425.00 |  | - |  | - |  |  | - |  | GES |  | LMC |  |
| Focus Area: Health and Health Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 50. Procurement of 8 delivery sets for CHPS Compounds |  | Debiso, Adupiri, Surano A’, Ntakam, Akaaso, Akaasu, Aboduabo & Kumkumso |  |  |  |  |  |  |  | 50,496.00 |  | - |  | - |  |  | - |  | GHS |  | CA |  |
|  |  | 51. Procurement of 5 delivery beds for CHPS compounds |  | Selected CHPS Zones |  |  |  |  |  |  |  | 50,000.00 |  | - |  | - |  |  | - |  | GHS |  | CA |  |
|  |  | 52. Support training in malaria case management |  | Municipal wide |  |  |  |  |  |  |  | 25,000.00 |  | 10,000.00 |  | - |  |  | - |  | GHS |  | CA, Private Sector, NGOs |  |
|  |  | 53. Support for national immunization campaigns and support for neglected tropical Disease control programme |  | Municipal wide |  |  |  |  |  |  |  | - |  | 30,000.00 |  | 30,000.00 |  |  | - |  | GHS |  | CA |  |
|  |  | 54. Intensify education to reduce stigmatization on HIV/AIDs and other diseases |  | Municipal wide |  |  |  |  |  |  |  | 16,000.00 |  | 20,000.00 |  | - |  |  | - |  | GHS |  | CA |  |
|  |  | 55. Intensify behavioral change strategies, especially for high risks groups for HIV/AIDS and TB |  | Municipal wide |  |  |  |  |  |  |  | 6,000.00 |  | 10,000.00 |  | - |  |  | - |  | GHS |  | CA |  |
|  |  | 56. Rehabilitation of malnourished children ward and support other Nutritional activities |  | Bibiani |  |  |  |  |  |  |  | 50,000.00 |  | - |  | - |  |  | - |  | GHS |  | CA |  |
|  |  | 57. Organise quarterly Municipal health Committee meetings |  | Bibiani |  |  |  |  |  |  |  | - |  | 35,000.00 |  | - |  |  | - |  | GHS |  | CA |  |
|  |  | 58. Support the management of Public Health emergencies i e. disease outbreak |  | Municipal wide |  |  |  |  |  |  |  | - |  | - |  | 250,000.00 |  |  | - |  | GHS |  | CA |  |
| Focus Area: Food and Nutrition Security |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Service Delivery | Public Health Services and Management | 59. Promote nutritionally sensitive and cost-effective diet through education and sensitization through radio and community visits |  | Municipal wide |  |  |  |  |  |  |  | 28,000.00 |  | 50,000.00 |  | 2,000.00 |  |  | - |  | GHS |  | CA, Private Sector, |  |
|  |  | 60. Promote the production of diversified, nutrient-rich food and consumption of nutrition foods |  | Municipal wide |  |  |  |  |  |  |  | - |  | 20,000.00 |  | 30,000.00 |  |  | - |  | GHS |  | CA |  |
|  |  | 61. Sensitisation to reduce infant, adult malnutrition, and dietary non communicable diseases |  | Municipal wide |  |  |  |  |  |  |  | 15,000.00 |  | 30,000.00 |  | - |  |  | - |  | GHS |  | CA |  |
| Social Service Delivery | Public Health Services and Management | 62. Organise demonstrative training workshop for women on kitchen gardens and food basal in 10 communities |  | Selected Communities |  |  |  |  |  |  |  | - |  | 20,000.00 |  | 30,000.00 |  |  | - |  | SWCD |  | CA |  |
| Focus Area: Population Management and Migration for Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Public Health Services and management | 63. Organise sensitization programme on teenage pregnancy on radio |  | Bibiani |  |  |  |  |  |  |  | - |  | 22,000.00 |  | - |  |  | - |  | SWCD |  | NCCE UNICEF |  |
| Social Services Delivery | Population Management | 64. Collaboration with Immigration service on migration data within the Municipality |  | Municipal Wide |  |  |  |  |  |  |  | 10,000.00 |  | 25,000.00 |  | - |  |  | - |  | Statistics Dept |  | CA GIS |  |
| Focus Area: Reducing Poverty and Inequality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Services | 65. Monitor and coordinate Livelihood Empowerment Against Poverty (LEAP) programme |  | Municipal Wide |  |  |  |  |  |  |  | - |  | - |  | 34,000.00 |  |  | - |  | SW&CD |  | CA |  |
|  |  | 66. Coordinate activities of School Feeding Programme |  | Beneficiary schools |  |  |  |  |  |  |  | 30,000.00 |  | 20,000.00 |  | - |  |  | - |  | SW&CD |  | CA |  |
|  |  | 67. Provision of Medical Support to the vulnerable |  | Municipal Wide |  |  |  |  |  |  |  | 70,000.00 |  | 30,000.00 |  | - |  |  | - |  | SWCD |  | CA |  |
|  |  | 68. Support 1,000 Vulnerable people to get NHIS Cards |  | Municipal Wide |  |  |  |  |  |  |  | 30,000.00 |  | 50,000.00 |  | 15,000.00 |  |  | - |  | SWCD |  | CA |  |
| Focus Area: Water and Environmental Sanitation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | Public Works, Rural Housing and Water Management |
|  |  | 69. Formation and training of WATSANS members in 10 communities |  | Selected Towns |  |  |  |  |  |  |  | 40,000.00 |  | 20,000.00 |  | - |  |  | - |  | EHU |  | MA |  |
| Social Services Delivery | Environmental Health and Sanitation Services | 70. Procure 2 No motorbike for monitoring activities of sanitation service providers |  | Bibiani |  |  |  |  |  |  |  | 86,000.00 |  | - |  | - |  |  | - |  | EHU |  | CA |  |
|  |  | 71. Procure 5 No. refuse containers and sanitary tools |  | Municipal Wide |  |  |  |  |  |  |  | 70,000.00 |  | - |  | - |  |  | - |  | EHU |  | CA |  |
|  |  | 72. Conduct screening of 800 food vendors |  | Municipal Wide |  |  |  |  |  |  |  | 20,000.00 |  | 35,000.00 |  | - |  |  | - |  | EHU |  | CA |  |
|  |  | 73. Promote household toilet construction in 10 communities (CLTS) |  | Municipal Wide |  |  |  |  |  |  |  | 5,500.00 |  | 20,000.00 |  | - |  |  | - |  | EHU |  | CA |  |
|  |  | 74. Conduct environmental health /hygiene education in 40 communities |  | Municipal Wide |  |  |  |  |  |  |  | 32,000.00 |  | - |  | - |  |  | - |  | EHU |  | GES, NGOs |  |
|  |  | 75. Organize spraying to control Pests and vectors in the municipality |  | Bibiani |  |  |  |  |  |  |  | 30,000.00 |  | 20,000.00 |  | - |  |  | - |  | EHU |  | MA |  |
|  |  | 76. Solid and liquid waste management, (Fumigation, manage wasteland fills Contract with Zoomlion) |  | Municipal Wide |  |  |  |  |  |  |  | 300,000.00 |  | - |  | - |  |  | - |  | EHU |  | CA, Zoomlion |  |
|  |  | 77. Conduct quarterly Evaluation and Performance Review meetings with Environmental Health Zonal Heads |  | Bibiani |  |  |  |  |  |  |  | 20,000.00 |  | 25,000.00 |  | - |  |  | - |  | EHU |  | CA |  |
|  |  | 78. Conduct monthly monitoring of Sanitation service providers |  | Municipal Wide |  |  |  |  |  |  |  | 15,000.00 |  | 20,000.00 |  | - |  |  | - |  | EHU |  | CA |  |
|  |  | 79. Conduct quarterly meeting of Sanitation Service providers |  | Bibiani |  |  |  |  |  |  |  | 12,000.00 |  | 12,000.00 |  | - |  |  | - |  | EHU |  | CA |  |
|  |  | 80. Construction of Slaughter House in Bibiani |  | Bibiani |  |  |  |  |  |  |  | 400,000.00 |  | - |  | - |  |  | - |  | EHU |  | CA |  |
|  |  | 81. Procurement of 1 ambient meter for controlling public noise |  | Selected Communities |  |  |  |  |  |  |  | 15,000.00 |  | - |  | - |  |  | - |  | EHU |  | CA |  |
|  |  | 82. Construction of Pour Flush Toilet Facility |  | Bibiani |  |  |  |  |  |  |  | 400,000.00 |  | - |  | - |  |  | - |  | EHU |  | CA |  |
|  |  | 83. Provide public education on solid waste management |  | Municipal wide |  |  |  |  |  |  |  | 10,000.00 |  | 4000.00 |  | 4000.00 |  |  | - |  | EHU |  | CA |  |
|  |  | 84. Promote public health education and hygiene in basic schools |  | Municipal wide |  |  |  |  |  |  |  | 10,.000.00 |  | 40,000.00 |  | 5000.00 |  |  | - |  | EHU |  | CA |  |
|  |  | 85. Training of food vendors on safety and proper handling of food |  | Municipal wide |  |  |  |  |  |  |  | - |  | 20,000.00 |  | 15,000.00 |  |  |  |  | EHU |  | CA |  |
|  |  | 86. Construction and Mechanization of 8 No. Boreholes with overhead tanks |  | BISEC, Ntakam, Fawokabra, Anyinase, Asempaneye, Ohiampeneka, Degede & Mota yard |  |  |  |  |  |  |  | 393,306.90 |  | - |  | - |  |  | - |  | EHU |  | LMC |  |
| Focus Area: Child Protection and Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Services | 87. Formation of Community Child Protection Committees in 10 Child labour endemic communities and train them on child labour issues |  | Selected Towns |  |  |  |  |  |  |  | - |  | 32,000.00 |  | 10,000.00 |  |  | - |  | SW&CD |  | MCPC |  |
|  |  | 88. Organize sensitization programmes on child labour |  | Bibiani |  |  |  |  |  |  |  | - |  | 20,000.00 |  | 20,000.00 |  |  | - |  | SW&CD |  | MCPC |  |
|  |  | 89. Remediation support for children |  |  |  |  |  |  |  |  |  | 10,000.00 |  | 20,000.00 |  | 20,000.00 |  |  | - |  | SWCD |  | CA |  |
| Focus Area: Gender Equality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Services |  | 90. Organise sensitization programme on the need to involve women in decision making and local governance in 20 communities | Municipal wide |  |  |  |  |  |  |  | 18,000.00 |  | 7,000.00 |  | - |  |  | - |  | SW&CD |  | CA, NGOs |  |
|  |  |  | 91. Organise sensitization programme on Persistent negative discriminatory socio-cultural and customary practices against women | Bibiani |  |  |  |  |  |  |  | 25,000.00 |  | 10,000.00 |  | 5,000.00 |  |  | - |  | SW&CD |  | CA, NGOs |  |
|  |  |  | 92. Provide educational support to 10 female students pursuing science at the Tertiary level | Municipality- wide |  |  |  |  |  |  |  | 30,000.00 |  | 30,000.00 |  | - |  |  | - |  | CA |  | GES |  |
|  |  |  | 93. Organize basic skills training in poultry farming for 65 women cocoa farmers | Municipality- Wide |  |  |  |  |  |  |  | 25,000.00 |  | 10,000.00 |  | - |  |  | - |  | BAC |  | CA |  |
| Focus Area: Sports and Recreation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education, youth &sports and library services | 94. Organise community football galas |  | Bibiani |  |  |  |  |  |  |  | 40,000.00 |  | 20,000.00 |  | - |  |  | - |  | CA |  | Community members |  |
| Focus Area: Youth Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education, youth &sports and library services | 95. Organise skills training in alternative livelihoods for 80 youth in cocoa growing areas |  | Municipality- Wide |  |  |  |  |  |  |  | 25,000.00 |  | 10,000.00 |  | - |  |  | - |  | BAC |  | CA |  |
| Focus Area: Social Protection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Welfare and Community Services | 96. Organise radio programme on child right and child protection issue |  | Bibiani |  |  |  |  |  |  |  | 12,000.00 |  | 10,000.00 |  | 5,000.00 |  |  | - |  | SW& CD |  | CA, MCPC |  |
| Focus Area: Disability-Inclusive Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Welfare and Community Services | 97. Provide medical /assistive devices to PWDs |  | Municipal wide |  |  |  |  |  |  |  | 30,000.00 |  | 20,000.00 |  | - |  |  | - |  | SW& CD |  | CA |  |
|  |  | 98. Organise Advocacy & awareness creation on the rights & responsibilities of PWDs |  | Bibiani |  |  |  |  |  |  |  | 12,000.00 |  | 20,000.00 |  | - |  |  | - |  | SW& CD |  | CA |  |
|  |  | 99. Provide educational/ apprenticeship support to PWDs |  | Municipality-wide |  |  |  |  |  |  |  | 10,000.00 |  | 10,000.00 |  | - |  |  | - |  | SW& CD |  | CA |  |
|  |  | 100. Procure items such as fridges, Tricycles, start-ups to support PWDs to enter income generation activities |  | Municipal wide |  |  |  |  |  |  |  | 60,000.00 |  | 20,000.00 |  | - |  |  | - |  | SW& CD |  | CA |  |
|  |  | 101. Strengthening organization of Persons with Disability |  | Bibiani |  |  |  |  |  |  |  | 18,000.00 |  | 20,000.00 |  | - |  |  | - |  | SW& CD |  | CA |  |
| DEVELOPMENT DIMENSION 3: ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Protected Areas |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Management | 102. Facilitate alternative livelihoods including eco-tourism support schemes for fringe communities along protected areas |  | 5 Selected Communities |  |  |  |  |  |  |  | 22,000.00 |  | 20,000.00 |  | 10,000.00 |  |  | - |  | Forestry Commission |  | CA, Care International |  |
|  |  | 103. Sensitization of communities to prevent illegal activities in forest reserves |  | Forest Reserves |  |  |  |  |  |  |  | 20,000.00 |  | 30,000.00 |  | - |  |  | - |  | Forestry Commission |  | Chiefs, CA |  |
| Focus Area: Mineral Extraction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Management | 104. Organise sensitization programme on illegal mining, deforestation and land reclamation |  | Selected communities |  |  |  |  |  |  |  | 20,000.00 |  | 22,000.00 |  | - |  |  | - |  | Minerals Commission |  | CA, NGOs, CSO, Chiefs Minerals Commission |  |
| Infrastructure Maintenance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | Public works, rural housing and water management | 105. Rehabilitation of Bibiani and Bekwai Markets |  | Bibiani & Bekwai |  |  |  |  |  |  |  | 400,000.00 |  | - |  | - |  |  | - |  | Works |  | MLGDRD |  |
| Infrastructure Development and Management | Public works, rural housing and water management | 106.. Rehabilitation of Humijibre Market |  | Humijibre |  |  |  |  |  |  |  | 30,000.00 |  |  |  |  |  |  |  |  | Works |  | MLGDRD |  |
| Infrastructure Development and Management | Public works, rural housing and water management | 107. Renovation of National Ambulance Unit and Fire Tender station in Sefwi Bekwai |  | Sefwi Bekwai |  |  |  |  |  |  |  | 180,000.00 |  | - |  | - |  |  | - |  | Works |  | MLGDRD |  |
| Focus Area: Water Resources Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Management | 108. Enforcement of development control on water bodies |  | Municipal wide |  |  |  |  |  |  |  | 40,000.00 |  | 30,000.00 |  | - |  |  | - |  | Forestry Commission |  | CA, NGOs, CSO,Chiefs, Minerals Commission |  |
| Focus Area: Environmental Pollution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Management | 109. Enforce environmental laws and regulations to prevent noise pollution |  | Municipal Wide |  |  |  |  |  |  |  | 32,000.00 |  | - |  | - |  |  | - |  | EHU |  | CA, NGOs, CSO, MWST, |  |
|  |  | 110. Promote the use of LPG as alternative sources of energy by households |  | Municipal wide |  |  |  |  |  |  |  | 2,000.00 |  | - |  | 2,000.00 |  |  | - |  | NADMO |  | FC |  |
| Focus Area: Deforestation, Desertification and Soil Erosion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Management | 111. Support the planting of 400,000 assorted tree seedlings in the municipality |  | Municipal wide |  |  |  |  |  |  |  | 120,000.00 |  | - |  | - |  |  | - |  | Forestry Communities |  | NADMO |  |
|  |  | 112. Establishment of forest plantations in degraded forest land through Modified Taungya and industrial plantation |  | Anhwiaso, Aboduabo |  |  |  |  |  |  |  | 10,000.00 |  | - |  | - |  |  | - |  | Forestry Commission |  | CA |  |
| Environmental Management | Natural Resource Conservation and Mgt. | 113. Support the implementation of youth in afforestation programme |  | Municipal wide |  |  |  |  |  |  |  | - |  |  |  | 20,000.00 |  |  | - |  | Forestry Commission |  | CA |  |
| Focus Area: Climate Variability and Change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation & Mgt | 114. Organize sensitization campaigns on climate change variability and adaptation in 30 communities in line with the Ghana Cocoa Forest REDD+ Programme |  | Selected communities |  |  |  |  |  |  |  | 12,000.00 |  |  |  | - |  |  | - |  | NADOM |  | CA NGO’s, FC |  |
| Environmental Management | Natural Resource Conservation & Mgt | 115. Undertake education on fire prevention and management in 30 communities in line with the Ghana Cocoa Forest REDD+ Programme |  | Selected towns |  |  |  |  |  |  |  | 2,000.00 |  | 20,000.00 |  | - |  |  | - |  | NADMO |  | CA, NGOs, CSO, Mineral Commission, FC |  |
| Focus Area: Disaster Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Disaster Prevention and management | 116. Formation of Disaster Risk Reduction clubs in 20 schools |  | Selected Schools |  |  |  |  |  |  |  | 2,000.00 |  | - |  | 5,000.00 |  |  | - |  | NADMO |  | GES |  |
|  |  | 117. Organise community sensitization on hazards of fire |  | Selected Towns |  |  |  |  |  |  |  | 3,000.00 |  | - |  | 3,000.00 |  |  | - |  | NADMO |  | GNFS, CA |  |
| Environmental Management | Disaster Prevention and management | 118. Sensitization of the public on the prevention and management of domestic and bush fires |  | Selected Communities |  |  |  |  |  |  |  | - |  | 2,000.00 |  | - |  |  | - |  | GNFS |  | CA |  |
| Environmental Management | Disaster Prevention and management | 119. Training of fuel stations, markets and other public places on management of fire outbreaks |  | Selected Communities |  |  |  |  |  |  |  | - |  | 2,000.00 |  | - |  |  | - |  | GNFS |  | CA |  |
| Focus Area: Transportation: Road & Road Safety |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | Urban roads and transport services | 120. Reshape 19km of feeder roads and building of culvert |  | Municipal Wide |  |  |  |  |  |  |  | 300,000.00 |  | 100,000.00 |  | - |  |  | - |  | Works |  | CA |  |
|  |  | 121. De-silting of 10km of drains, grass cutting and patching of potholes |  | Municipality-wide |  |  |  |  |  |  |  | 420,000.00 |  | - |  | - |  |  | - |  | Works |  | CA, Urban Roads |  |
|  |  | 122. Grading of 5km Town Roads |  | Municipality-wide |  |  |  |  |  |  |  | 140,000.00 |  | - |  | - |  |  | - |  | Works |  | CA, Urban Roads |  |
|  |  | 123. Traffic Management |  | Municipality-wide |  |  |  |  |  |  |  | 105,000.00 |  | - |  | - |  |  | - |  | Works |  | CA, RSC |  |
|  |  | 124. Installation of Street lights |  | Municipality-wide |  |  |  |  |  |  |  | 75,600.00 |  | - |  | - |  |  |  |  | Works |  | ECG |  |
|  | Urban roads and transport services | 125. Sensitization on Road Safety policy for drivers and user |  | Municipal Wide |  |  |  |  |  |  |  | 10,000.00 |  | 5,000.00 |  | - |  |  | - |  | Works |  | CA, NRSC, NCCE |  |
| Focus Area: Information Communication Technology Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | ICT | 126. Organise ICT training for 150 youth |  | Municipal Wide |  |  |  |  |  |  |  | 5,000.00 |  | 15,000.00 |  | - |  |  |  |  | GES |  | CA, NGOs |  |
| Focus Area: Human Settlements Development and Housing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | Spatial Planning | 127. Continue the street naming and property addressing system |  | Anhwiaso, Chirano |  |  |  |  |  |  |  | 100,000.00 |  |  |  | 100,000.00 |  |  | - |  | Physical Planning |  | CA, TA .SPC |  |
|  |  | 128. Preparation and revision of local settlement plans |  | Sefwi Bekwai, Chirano, Ampenkrom |  |  |  |  |  |  |  | 100,000.00 |  | - |  | - |  |  | - |  | Physical Planning |  | CA, TA, SPC |  |
|  |  | 129. Landscaping and Gardening of principal streets in Bibiani |  | Bibiani |  |  |  |  |  |  |  | 5,000.00 |  | 10,000.00 |  | - |  |  | - |  | Physical Planning |  | CA,TA , SPC |  |
|  |  | 130. Undertake building inspections to ensure compliance with the national building code |  | Municipal Wide |  |  |  |  |  |  |  | - |  | 20,000.00 |  | - |  |  | - |  | Physical Planning |  | CA, TA, SPC |  |
| Focus Area: Drainage and Flood Control |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | Public Works, Rural Housing and Water Management | 131. Construction of 6 No. culverts |  | Kofikrom, Chira Nzema Nkwanta,Mframakrom, Abokyikrom |  |  |  |  |  |  |  | 40,000.00 |  | - |  | - |  |  | - |  | NADMO |  | CA |  |
| DEVELOPMENT DIMENSION 4: GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Local Governance and Decentralization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | General Administration | 132. Organize Statutory meetings (Management Meetings, Sub-Committee, Executive Committee & General Assembly Meetings, SAT Meetings etc) |  | Bibiani |  |  |  |  |  |  |  | - |  | 260,000.00 |  | - |  |  | - |  | CA |  | MLGDRD |  |
|  |  | 133. Maintenance of office equipment |  | Bibiani |  |  |  |  |  |  |  | 20,000.00 |  | 30,000.00 |  | - |  |  | - |  | CA |  | MLGDRD |  |
|  |  | 134. Rehabilitation & Furnishing of Assembly Hall complex |  | Bibiani |  |  |  |  |  |  |  | 180,000.00 |  | - |  | - |  |  | - |  | Works |  | MLGDRD |  |
|  |  | 135. Procurement of 100kva generator for the Assembly and other offices |  | Bibiani |  |  |  |  |  |  |  | 100,000.00 |  | - |  | - |  |  | - |  | Works |  | CA |  |
|  |  | 136. Maintenance of Assembly Vehicles/ General Equipment |  | Bibiani |  |  |  |  |  |  |  | 30,000.00 |  | 20,000.00 |  | - |  |  | - |  | CA |  | MLGDRD |  |
|  |  | 137. Renovation of 4 Assembly Bungalows & Offices |  | Bibiani |  |  |  |  |  |  |  | 50,000.00 |  | 130,000.00 |  | - |  |  | - |  | CA |  | MLGDRD |  |
|  |  | 138. Procurement of Office Equipment /Logistics (6-No servers, 6-No laptops, UPS & Networking Equipment) |  | Bibiani |  |  |  |  |  |  |  | 50,000.00 |  | 20,000.00 |  | - |  |  | - |  | CA |  | MLGDRD |  |
|  |  | 139. Gazetting of Assembly’s Bye-Laws |  | Bibiani |  |  |  |  |  |  |  | 30,000.00 |  | - |  | - |  |  | - |  | CA |  | MLGDRD |  |
| Management and Administration | General Administration | 140. Support to Self Help Community Projects |  | Municipality- Wide |  |  |  |  |  |  |  | 200,000.00 |  | 100,000.00 |  | - |  |  | - |  | CA |  | MLGDRD |  |
|  |  | 141. Support the sub-structures in the Municipality/Construction of 1 No. Zonal Council Office |  | Sefwi Bekwai |  |  |  |  |  |  |  | 300,000.00 |  | - |  | - |  |  | - |  | CA |  | MLGDRD |  |
|  |  | 142. Supply, Installation and maintenance of streetlight and extension of electricity |  | Selected communities |  |  |  |  |  |  |  | 150,000.00 |  | 50,000.00 |  | - |  |  | - |  | Works |  | CA |  |
|  |  | 143. Support Decentralized Dept. and WNRCC |  | Bibiani |  |  |  |  |  |  |  | 50,000.00 |  | - |  | - |  |  |  |  | CA |  | MLGDRD |  |
|  |  | 144. Implement Capacity building plan/Staff development |  | Bibiani |  |  |  |  |  |  |  | 50,000.00 |  | 30,000.00 |  | - |  |  | - |  | HRM |  | MLGDRD |  |
|  |  | 145. Provision for official day celebrations |  | Selected Communities |  |  |  |  |  |  |  | 150,000.00 |  | - |  | - |  |  | - |  | CA |  | MLGDRD |  |
|  |  | 146. Internal Management of organization (Utility, fuel, call credit, Hotel Accommodation, NALAG Dues etc) |  | Bibiani |  |  |  |  |  |  |  | 100,000.00 |  | 100,000.00 |  | - |  |  | - |  | CA |  | MLGDRD |  |
| Focus Area: Public Accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Planning, Budgeting, Monitoring & Evaluation | 147. Organise Social Accountability Fora ie. 2 Town Hall meetings, Meet the Press & Social Audit |  | Bibiani & Bekwai |  |  |  |  |  |  |  | 40,000.00 |  | 10,000,00 |  | - |  |  | - |  | CA |  | MLGDRD |  |
| Focus Area: Human Security and Public Safety |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | General Administration | 148. Support for Security operations & MUSEC activities |  | Bibiani |  |  |  |  |  |  |  | 80,000,00 |  | 20,000.00 |  | - |  |  | - |  | CA |  | MLGDRD |  |
| Focus Area: Corruption and Economic Crimes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | General Administration | 149. Support Anti- Corruption Agencies /Implement NACAP |  | Municipal wide |  |  |  |  |  |  |  | 10,000.00 |  | 20,000.00 |  | - |  |  | - |  | CA |  | CHRAJ, Audit Service, NCCE, NGOs |  |
| DEVELOPMENT DIMENSION 5: EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19 RECOVERY PLAN) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Hydro meteorological |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Public Health Services and management | 150. Organize community education programme on hydro meteorological disaster |  | Selected Communities |  |  |  |  |  |  |  | 5,000.00 |  | 30,000.00 |  | - |  |  | - |  | NADMO |  | CA |  |
| Focus Area: Biological |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Public Health Services and management | 151. Organise sensitization and education programmes on Covid-19 and other pandemics and enforcement of safety protocols |  | Municipal wide |  |  |  |  |  |  |  | 20,000.00 |  | 10,000.00 |  | - |  |  | - |  | GHS |  | CA |  |
|  |  | 152. Support Municipal Public Health Emergency Management Committee & Municipal Public Health Emergency Rapid Response Team activities |  | Bibiani |  |  |  |  |  |  |  | 20,000.00 |  | 40,000.00 |  | - |  |  | - |  | GHS |  | CA |  |
|  |  | 153. Vaccination against public health emergencies such as Covid-19 and other pandemics |  | Municipality- wide |  |  |  |  |  |  |  | 10,000.00 |  | 10,000.00 |  | - |  |  | - |  | GHS |  | CA |  |
| Focus Area: Anthropogenic |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Public Health Services and management | 154. Organise 4 quarterly disaster mitigation and public awareness programmes |  | Selected communities |  |  |  |  |  |  |  |  | 5,000.00 | 12,000.00 |  | - |  |  |  | - |  | NADMO |  | CA |  |  |
| Relief Assistance and Victim Welfare |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Disaster Prevention and management | 155. Support 200 disaster victims with relief items |  | Municipal wide |  |  |  |  |  |  |  |  | 100,000.00 | - |  | - |  |  |  | - |  | NADMO |  | CA |  |  |
| DEVELOPMENT DIMENSION 6: IMPLEMENTATION, COORDINATION, MONITORING AND EVALUATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Planning, Budgeting, Monitoring & Evaluation | 156. Organize 4 Quarterly MPCU and budget committee meetings |  | Bibiani |  |  |  |  |  |  |  | 30,000.00 |  |  | 10,000.00 | - |  |  | - |  | CA |  | MLGDRD |  |
|  |  | 157. Preparation of 2024 composite Annual Action Plan and budget |  | Bibiani |  |  |  |  |  |  |  | 25,000.00 |  |  | - | - |  |  | - |  | CA |  | MLGDRD |  |
|  |  | 158. Conduct projects and programme evaluations and APR preparation sessions for HODs. |  | Selected Towns |  |  |  |  |  |  |  | 50,000.00 |  |  | 30,000.00 | - |  |  | - |  | CA |  | MLGDRD |  |
|  |  | 159. Dissemination of 2023 approved composite and Gazetting of fee-fixing |  | Bibiani |  |  |  |  |  |  |  | 15,000.00 |  |  | 10,000.00 | - |  |  | - |  | CA |  | MLGDRD |  |
|  |  | 160. Undertake consultative meetings and prepare 2024 Fee-Fixing Resolutions |  | Bibiani |  |  |  |  |  |  |  | 5,000.00 |  |  | 20,000.00 | - |  |  | - |  | CA |  | MLGDRD |  |
|  |  | 161. Undertake Mid-Year Review of the 2023 Composite Budget |  | Bibiani |  |  |  |  |  |  |  | 14,000.00 |  |  | - | - |  |  | - |  | CA |  | MLGDRD |  |
| Production and Utilization of Statistics |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Planning, Budgeting, Monitoring & Evaluation | 162. Conduct monthly market readings at Sefwi Bekwai and Bibiani |  | Bekwai & Bibiani |  |  |  |  |  |  |  | 5,000.00 |  |  | - | - |  |  | - |  | Statistics |  | CA |  |
| Management and Administration | Planning, Budgeting, Monitoring & Evaluation | 163. Build community register in 3 endemic communities of child labour using Ghana Child Labour Monitoring System |  | Selected Communities |  |  |  |  |  |  |  | 10,000.00 |  |  | - | - |  |  | - |  | Statistics |  | CA |  |
| Total |  |  |  |  |  |  |  |  |  |  |  | 9,150,372.00 |  |  | 1,480,000.00 | 1,577,000.00 | 12,207,372.00 |  |  |  |  |  |  |  |

##### Table 5.3 Annual Action Plan for 2024

| DEVELOPMENT DIMENSION: ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme (PBB) | Sub- Programme (PBB) | Broad Activities |  |  | Location | Time Frame |  |  |  |  |  |  | Cost |  |  |  | Programme Status |  | Implementing Institution |  |
|  |  |  |  |  |  | Q1 |  | Q2 | Q3 |  |  | Q4 | GoG (GH¢) | IGF (GH¢) |  | Others (GH¢) | New | Ongoing | Lead | Collaborating |
| Focus Area: Strong and Resilient Economy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Finance | 1. Train revenue collectors and key staff on revenue collection strategies |  |  | Bibiani |  |  |  |  |  |  |  | 30,000.00 | 5,000.00 |  | - |  | - | Finance Dept. | CA GIZ |
|  | Finance | 2. Strengthen Rateable property data collection and revenue collection digitalization |  |  | Municipal Wide |  |  |  |  |  |  |  | 20,000.00 | 30,000.00 |  | - |  | - | Finance Dept. | CA |
| Focus Area: Private Sector Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Trade, Industry and Tourism | 3. Construction of market |  |  | Asawinso |  |  |  |  |  |  |  | 300,000.00 | - |  | - |  | - | Works | CA, MLGRD |
|  |  | 4. Training and provision of start-up kits for 60 people in Gari processing, bee keeping, Soap making, Baking &confessionary |  |  | Municipal wide |  |  |  |  |  |  |  | - | 60,000.00 |  | 110,000.00 |  | - | BAC | CA |
|  |  | 5. Provide apprenticeship and start -ups for 30 youth to in carpentry, Masonry, Auto-Mechanics, Welding& Fabrication |  |  | Municipal wide |  |  |  |  |  |  |  | - | 50,000.00 |  | 230,000.00 |  | - | BAC | CA, RTF |
|  |  | 6. Organise management training for 120 SMEs and Entrepreneurs |  |  | Municipal wide |  |  |  |  |  |  |  | 20,000.00 | 50,000.00 |  | 15,000.00 |  | - | BAC | CA |
|  |  | 7. Support Agriculture value chain Actors & 20 SMEs with Revolving Funds |  |  | Municipal wide |  |  |  |  |  |  |  | - | - |  | 400,000.00 |  | - | BAC | EU, Sefwiman Rural Bank |
| Focus Area: Agriculture and Rural Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Agricultural Services and Management | 8. Implement government flagship programmes in Agric ie MAG, PFJ, DCACT, PERD |  |  | Municipal wide |  |  |  |  |  |  |  | - | - |  | 100,000.00 |  | - | MDA | CA, Farmers, Financial Institutions |
|  |  | 9. Organize District Farmers Day Celebrations |  |  | Asawinso |  |  |  |  |  |  |  | - | - |  | 70,000.00 |  | - | MDA | CA, Farmers, Financial Institutions |
|  |  | 10. Organise Sensitization for the youth to go into Agriculture |  |  | Municipal Wide |  |  |  |  |  |  |  | - | 10,000.00 |  | - |  | - | MDA | CA |
|  |  | 11. Supply of subsidized fertilizers, improved seedlings, animal breeds and other inputs to farmers |  |  | Municipal wide |  |  |  |  |  |  |  | - | - |  | 50,000.00 |  | - | MDA | CA, MoFA & Farmers, |
|  |  | 12. Provision of veterinary and Extension services to farmers |  |  | Municipal wide |  |  |  |  |  |  |  | - | - |  | 10,000.00 |  | - | MDA | CA, Farmers, Financial Institutions |
|  |  | 13. Support farmers with Agriculture equipment such as Tillers, tractors etc |  |  | Municipal Wide |  |  |  |  |  |  |  | - | - |  | 20,0000.00 |  | - | MDA | CA, Farmers |
|  |  | 14. Organise bi-monthly technical review and stakeholder meetings |  |  | Bibiani |  |  |  |  |  |  |  | - | - |  | 24,000.00 |  | - | MDA | CA, Farmers |
|  |  | 15. Conduct monthly data collection on yield studies and market surveying |  |  | Municipal Wide |  |  |  |  |  |  |  | - | - |  | 15,000.00 |  | - | MDA | CA, Farmers |
|  |  | 16. Organise monthly field demonstration on crop and animal production |  |  | Municipal Wide |  |  |  |  |  |  |  | - | - |  | 13,000.00 |  | - | MDA | CA, Farmers |
|  |  | 17. Support MDA and staff attending Region planning sessions, workshops, seminars and conferences |  |  | Municipal Wide |  |  |  |  |  |  |  | - | - |  | 30,000.00 |  | - | MDA | CA, Farmers |
|  |  | 18. Support the procurement of extension materials and Covid 19 PPEs |  |  | Municipal Wide |  |  |  |  |  |  |  | - | - |  | 9,000.00 |  | - | MDA | CA, Farmers |
|  |  | 19. Support MDA running and maintenance of official vehicles, motor bikes and office equipment |  |  | Municipal Wide |  |  |  |  |  |  |  | - | - |  | 14,000.00 |  | - | MDA | CA |
| Focus Area: Tourism and Creative Arts Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Trade, Industry and Tourism | 20. Project independence day celebration |  |  | Municipal wide |  |  |  |  |  |  |  | - | 20,000.00 |  | 100,000.00 |  | - | CA | Private Sector |
|  |  | 21. Support LED committee activities and business forum |  |  | Municipal Wide |  |  |  |  |  |  |  | - | 70,000.00 |  | 130,000.00 |  | - | BAC | CA |
|  |  | 22. Printing of booklets on Assembly Projects to support revenue drive and accountability of revenue utilisation |  |  | Municipal Wide |  |  |  |  |  |  |  | 58,000.00 | - |  | - |  | - | CA | CA Private sector |
| DEVELOPMENT DIMENSION 2: SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Education and Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Service Delivery Social Service Delivery | Education, Youth & Sports and Library services Education, Youth & Sports and Library services | 23. Construction of 1No. K.G Block with Ancillary Facilities |  |  | Wiakyiren |  |  |  |  |  |  |  | 250,000.00 | - |  | - |  | - | GES | CA |
|  |  | 24. Construction of 2No.3-Units Classroom Block with Ancillary Facilities |  |  | Bekwai Methodist J. H.S,.Mframandwo |  |  |  |  |  |  |  | 380,000.00 | - |  | 380.000.00 |  | - | GES | CA |
|  |  | 25. Construction of 2 No. 6-Unit Classroom Block with Office and Store |  |  | Chiraa, Bibiani Community |  |  |  |  |  |  |  | 600.000.00 | - |  | - |  | - | GES | CA |
|  |  | 26. Construction of KG for Methodist primary ‘B’ |  |  | Bibiani |  |  |  |  |  |  |  | 302,000.00 | - |  | - |  | - | GES | CA |
|  |  | 27. Rehabilitation of Schools |  |  | Anglican JHS Anhwiaso |  |  |  |  |  |  |  | 300.000.00 | - |  | - |  | - | GES | CA |
|  |  | 28. Organize best teacher awards |  |  | Bibiani |  |  |  |  |  |  |  | - | 50,000.00 |  | 50,000.00 |  | - | GES | CA, CSOs |
|  |  | 29. STMIE for 30 students from selected schools |  |  | Municipal wide |  |  |  |  |  |  |  | - | 50,000.00 |  | 31,000.00 |  | - | GES | CA |
|  |  | 30. Mock exams for 3872 BECE candidates |  |  | Municipal wide |  |  |  |  |  |  |  | 55,000.00 | 30,000.00 |  | 115,000.00 |  | - | GES | CA |
|  |  | 31. Support My 1st Day at school |  |  | Selected Schools |  |  |  |  |  |  |  | 15,000.00 | 5,000.00 |  | - |  | - | GES | CA |
|  |  | Organize Inter-schools’ sports and athletic competition |  |  | Municipal Wide |  |  |  |  |  |  |  | - | 10.000.00 |  | 10,000.00 |  | - | GES | CA |
|  |  | 32. Organise capacity building for Teachers |  |  | Bibiani |  |  |  |  |  |  |  | 30,000.00 | 20,000.00 |  | 20,000.00 |  | - | GES | CA |
|  |  | 33. Supply of 1000 Mono Desk & 1000 Dual Desk for schools |  |  | Selected Schools |  |  |  |  |  |  |  | 100,000.00 | 50,000.00 |  | - |  | - | GES | CA |
| Focus Area: Health and Health Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Service Delivery | Public Health Services and Management | 34. Construction of 2No. CHPS Compound |  |  | Nambro, Adobewura No. 2 |  |  |  |  |  |  |  | 350,000.00 | - |  | - |  | - | GHS | CA |
|  |  | 35. Construction of 3No mechanised borehole in existing CHPS Compound |  |  | Wenchi, Bassengale Humjibre |  |  |  |  |  |  |  | 135,000.00 | - |  | - |  | - | GHS | CA |
|  |  | 36. Procurement of 10 delivery beds for CHPS |  |  | Selected CHPS compounds |  |  |  |  |  |  |  | 50,000.00 | - |  | - |  | - | GHS | CA |
|  |  | 37. Procurement of delivery sets for CHPS compound |  |  | Selected CHPS compounds |  |  |  |  |  |  |  | 35,000.00 | - |  | - |  | - | GHS | CA |
|  |  | 38. Establishment of Laboratory at Health Centre |  |  | Humjibre |  |  |  |  |  |  |  | 100,000.00 | 50,000.00 |  | - |  | - | GHS | CA |
|  |  | 39. Support malaria control activities |  |  | Municipal wide |  |  |  |  |  |  |  | 45,000.00 | - |  | - |  | - | GHS | CA, NGOs |
|  |  | 40. Support for HIV/Aids control activities |  |  | 10 Towns/ 1 FM Stations |  |  |  |  |  |  |  | - | 30,000.00 |  | - |  | - | GHS | CA, CSOs |
|  |  | 41. Intensify education to reduce stigmatisation on HIV/AIDS and other public health diseases |  |  | Municipal wide |  |  |  |  |  |  |  | 17,000.00 | 10,000.00 |  | - |  | - | GHS | CA |
|  |  | 42. Intensify behavioural change strategies, especially for high risks groups for HIV/AIDS and TB |  |  | Municipal wide |  |  |  |  |  |  |  | 17,000.00 | - |  | - |  | - | GHS | CA |
|  |  | 43. Support for National Immunization campaigns and Neglected Tropical Diseases Control programme |  |  |  |  |  |  |  |  |  |  | 20,000.00 | 20,000.00 |  | - |  | - | GHS | CA |
|  |  | 43. Public Health Emergency Management Committee (PHEMC) meetings |  |  |  |  |  |  |  |  |  |  | 50,000.00 | 20,000.00 |  | - |  | - | GHS | CA |
|  |  | 44. Municipal Health Committee meetings |  |  | Municipal wide |  |  |  |  |  |  |  | 20,000.00 | 15,000.00 |  |  |  | - | GHS | CA |
|  |  | 45. Management of Public Health emergencies i e. disease outbreaks, etc |  |  | Municipal wide |  |  |  |  |  |  |  | 250,000.00 | - |  | - |  | - | GHS | CA |
|  |  | 46. Distribution of long-lasting insecticide treated net to all households in the municipality |  |  | Municipal Wide |  |  |  |  |  |  |  | 5,000.00 | 30,000.00 |  | - |  | - | GHS | CA |
|  | Hygiene | 47. Provide public education on solid waste management in 40 communities |  |  | Municipal wide |  |  |  |  |  |  |  | 10,000.00 | 5000.00 |  | 5000.00 |  | - | MEHO | CA |
|  |  | 48. Promote public health education and hygiene in 32 basic schools |  |  | Municipal wide |  |  |  |  |  |  |  | 15,000.00 | 20,000.00 |  | 2000.00 |  | - | MEHO/GHS | CA |
|  |  | 49. Training and screening of 800 food vendor |  |  | Municipal wide |  |  |  |  |  |  |  | 47,000.00 | 60,000.00 |  | - |  | - | MEHO/GHS | CA |
| Focus Area: Food and Nutrition Security |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Service Delivery | Public Health Services and Management | 50. Promote nutritionally sensitive and cost effective diet through education and sensitization in 10 communities |  |  | Municipal wide |  |  |  |  |  |  |  | 16,000.00 | 50,000.00 |  | 16,000.00 |  | - | SWCD | CA, Private Sector, |
|  |  | 51. Promote the production of diversified, nutrient-rich food and consumption of nutrition foods |  |  | Municipal wide |  |  |  |  |  |  |  | 42,000.00 | 50,000.00 |  | - |  | - | GHS | CA |
|  |  | 52. Sensitisation to reduce infant and adult malnutrition and dietary related non-communicable disease |  |  | Municipal wide |  |  |  |  |  |  |  | 20,000.00 | 50,000.00 |  | - |  | - | GHS | CA |
| Focus Area: Population Management and Migration for Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Services | 53. Collaborate with civil society groups and the media to sensitize the youth on the dangers of irregular migration, TIP and SOM |  |  | Municipal Wide |  |  |  |  |  |  |  | 50,000.00 | 32,000.00 |  | 2,000.00 |  | - | SW&CD | CA UNICEF |
| Focus Area: Reducing Poverty and Inequality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Services | 54. Monitor and coordinate Livelihood Empowerment Against Poverty (LEAP) programme |  |  | Municipal Wide |  |  |  |  |  |  |  | 24,000.00 | 30,000.00 |  | - |  | - | SW&CD | CA |
|  |  | 55. Coordinate activities of School Feeding Programme |  |  | Beneficiary schools |  |  |  |  |  |  |  | 30,000.00 | 30,000.00 |  | - |  | - | SW&CD | CA |
|  |  | 56. Provision of Medical Support to the vulnerable |  |  | Municipal Wide |  |  |  |  |  |  |  | 50,000.00 | 50,000.00 |  | - |  | - | MP | CA |
|  |  | 57. Support 1000 Vulnerable people to get NHIS Cards |  |  | Municipal Wide |  |  |  |  |  |  |  | 55,000.00 | 50,000.00 |  | - |  | - | MP | CA |
| Focus Area: Water and Environmental Sanitation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | Public Works, Rural Housing and Water Management | 58. Construction of 10No. Mechanized boreholes |  |  | Degede, Nsesaye,Aboduabo,Kroboano, Besiekrom |  |  |  |  |  |  |  | 160,000.00 | 40,000.00 |  | 160,000.00 |  | - | Works Dept. | CWSA |
|  |  | 59. Construction of Toilet facility(Support households to construct improved household toilets facilities- Technical & Material |  |  | Lineso |  |  |  |  |  |  |  | 350,000.00 | 50,000.00 |  | - |  | - | Works Dept. | EHU, CWSA |
|  |  | 60. Formation and training of WATSANS members in 7 communities |  |  | Selected Towns |  |  |  |  |  |  |  | 10,000.00 | 30,000.00 |  | - |  | - | EHU | CA |
|  |  | 61. Maintenance of 10 No. Borehole |  |  | 10 communities |  |  |  |  |  |  |  | 40,000.00 | 40,000.00 |  | - |  | - | Works Dept. | CWSA |
| Social Services Delivery | Environmental Health and Sanitation Services | 62. Procure 5No. refuse containers and sanitary tools |  |  | Selected Towns |  |  |  |  |  |  |  | 70,000.00 | 40,000.00 |  | - |  | - | EHU | CA |
|  |  | 63. Conduct screening of food vendors |  |  | Municipal Wide |  |  |  |  |  |  |  | 20,000.00 | 15,000.00 |  |  |  | - | EHSU | CA |
|  |  | 64. Conduct environmental health /hygiene education in 20 communities |  |  | Municipal Wide |  |  |  |  |  |  |  | 2,000.00 | 20,000.00 |  | - |  | - | EHSU | GES, NGOs |
|  |  | 65. Pest and vector control |  |  | Bibiani |  |  |  |  |  |  |  | 10,000.00 | 20,000.00 |  | - |  | - | EHSU | CA |
|  |  | 66. Declare 9 communities ODF basic |  |  | Selected communities |  |  |  |  |  |  |  | - | 9,000.00 |  | - |  | - | EHSU | CA |
|  |  | 67. Solid and liquid waste management, (Fumigation, manage wasteland fills Contract with Zoomlion) |  |  | Municipal Wide |  |  |  |  |  |  |  | 300,000.00 | - |  | - |  | - | EHSU | CA, Zoomlion |
|  |  | 68. Construction of Toilet Facility |  |  | Bibiani |  |  |  |  |  |  |  | - | 400,000.00 |  | - |  | - | EHSU | CA |
|  |  | 69. Promote household toilet construction (CLTS) |  |  | 10 Communities |  |  |  |  |  |  |  | 20,000.00 | 20,000.00 |  | - |  | - | EHSU | CA |
|  |  | 70. Conduct quarterly performance review meetings with Environmental Health Zonal Heads |  |  | Bibiani |  |  |  |  |  |  |  | - | 26,000.00 |  | - |  | - | EHSU | CA |
| Focus Area: Child Protection and Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Services | 71. Formation of Community Child Protection Committees in 10 Child labour endemic communities and train them on child labour issues |  |  | Selected Towns |  |  |  |  |  |  |  | 20,000.00 | 32,000.00 |  | 10,000.00 |  | - | SW&CD | CA NGOs |
|  |  | 72. Organize sensitization programmes on child labour |  |  | Bibiani |  |  |  |  |  |  |  | 20,000.00 | 30,000.00 |  | 20,000.00 |  | - | SW&CD | CA, NGOs |
|  |  | 73. Remediation support for children |  |  | Bibiani |  |  |  |  |  |  |  | 10,000.00 | 20,000.00 |  | 20,000.00 |  | - | SW&CD | CA, NGOs |
| Focus Area: Gender Equality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Services |  | 74. Organise sensitisation programme on the need to involve women in decision making in 20 communities |  | Municipal wide |  |  |  |  |  |  |  | 22,000.00 | 40,000.00 |  | - |  | - | SW&CD | CA, NGOs |
|  |  |  | 75. Provide capacity building training for women who contest local level elections |  | Bibiani |  |  |  |  |  |  |  | 15,000.00 | 20,000.00 |  | - |  | - | SW&CD | CA, NGOs |
|  |  |  | 76. Conduct training workshop for 100 women in income generating activities and skills for involved livelihood |  | Municipal Wide |  |  |  |  |  |  |  | 30,000.00 | 20,000.00 |  |  |  | - | SW&CD | CA NGO’s BAC |
|  |  |  | 77. Organise sensitization programme on Persistent negative discriminatory socio-cultural, traditional beliefs and customary practices against women |  | Selected Communities |  |  |  |  |  |  |  | 5,000.00 | 20,000.00 |  | 5,000.00 |  | - | SW&CD | CA, NGOs |
|  |  |  | 78. Conduct home visits and monitoring on domestic, environmental and personal hygiene in 10 communities |  | Municipal Wide |  |  |  |  |  |  |  | 32,000.00 | 20,000.00 |  | - |  | - | SW&CD EHSU | CA NGO’s |
|  |  |  | 79. Provide educational support to 10 female students pursuing science at the Tertiary level |  | Municipal wide |  |  |  |  |  |  |  | 30,000.00 | 20,000.00 |  | - |  | - | SW&CD | CA |
| Focus Area: Sports and Recreation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education, youth &sports and library services | 80. Organise community football gala |  |  | Bibiani |  |  |  |  |  |  |  | 20,000.00 | 30,000.00 |  | - |  | - | CA | Community members |
| Focus Area: Youth Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education, youth &sports and library services | 81. Organise capacity building workshops for the youth to orient them on the need to venture into entrepreneurship |  |  | Bibiani |  |  |  |  |  |  |  | 25,000.00 | 25,000.00 |  | 20,000.00 |  | - | BAC | CA, Private Sector, NABCO |
| Focus Area: Social Protection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Welfare and Community Services | 82. Organise radio programme on child right and child protection issue |  |  | Bibiani |  |  |  |  |  |  |  | 12,000.00 | 5,000.00 |  | 5,000.00 |  | - | SW& CD | CA |
| Focus Area: Disability-Inclusive Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Welfare and Community Services | 83. Provide medical /assistive device to PWDs |  |  | Municipal wide |  |  |  |  |  |  |  | 10,000.00 | 20,000.00 |  | - |  | - | SW& CD | CA, PWDs |
|  |  | 84. Organise Advocacy & awareness creation on the rights & responsibilities of PWDs |  |  | Bibiani |  |  |  |  |  |  |  | 12,000.00 | 30,000.00 |  | - |  | - | SW& CD | CA, PWDs |
|  |  | 85. Provide educational/ apprenticeship support to PWDs |  |  | Municipal wide |  |  |  |  |  |  |  | 10,000.00 | 60,000.00 |  | - |  | - | SW& CD | CA, PWDs |
|  |  | 86. Procure items such as fridges, Tricycles, start-ups etc, to support PWDs to enter into income generation activities |  |  | Municipal wide |  |  |  |  |  |  |  | 60,000.00 | 60,000.00 |  | - |  | - | SW& CD | CA, PWDs |
|  |  | 87. Strengthening organisation of person with Disability |  |  | Bibiani |  |  |  |  |  |  |  | 28,000.00 | - |  | - |  | - | SW& CD | CA, PWDs |
| Focus Area: Employment and Decent Work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Welfare and Community Services | 88. Support government flagship programmes such as NABCO &YEA |  |  | Bibiani |  |  |  |  |  |  |  | 20,000.00 | - |  | - |  | - | NABCO, YEA | CA |
| DEVELOPMENT DIMENSION 3: ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Protected Areas |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Management | 89. Facilitate alternative livelihoods including eco-tourism support schemes for fringe communities along protected areas |  |  | Selected Communities |  |  |  |  |  |  |  | 4,000.00 | 40,000.00 |  | 10,000.00 |  | - | Forestry Commission | CA, NGOs, CSO, Chiefs |
|  |  | 90. Monitor forest reserves to prevent illegal logging a |  |  | Forest Reserves |  |  |  |  |  |  |  | 20,000.00 | - |  | 50,000.00 |  | - | Forestry Commission | Chiefs, CA |
| Focus Area: Mineral Extraction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Management | 91. Facilitate the implementation of community mining |  |  | Selected communities |  |  |  |  |  |  |  | 10,000.00 | 30,000.00 |  | 100,000.00 |  | - | Minerals Commission | CA, NGOs, CSO, Minerals Commission |
|  |  | 92. Organise sensitization programme on illegal mining, deforestation and land reclamation |  |  | Selected communities |  |  |  |  |  |  |  | - | 22,000.00 |  | 50,000.00 |  | - | Minerals Commission | CA, NGOs, CSO, Minerals Commission |
| Focus Area: Water Resources Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Management | 93. Enforcement of development control on water bodies |  |  | Municipal wide |  |  |  |  |  |  |  | 10,000.00 | - |  | 60,000.00 |  | - | Forestry Commission | CA, NGOs, CSO, Minerals Commission |
| Focus Area: Environmental Pollution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Management | 94. Enforce environmental laws and regulations to prevent noise pollution |  |  | Municipal Wide |  |  |  |  |  |  |  | 2,000.00 | - |  | 40,000.00 |  | - | Forestry Commission | CA, NGOs, CSO |
|  |  | 95. Promote the use of LPG as alternative sources of energy by households |  |  | Municipal wide |  |  |  |  |  |  |  | 2,000.00 | - |  | 32,000.00 |  | - | Forestry Commission | NADMO |
| Focus Area: Deforestation, Desertification and Soil Erosion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Management | 96. Planting of 100,000 tress across the municipality |  |  | Municipal wide |  |  |  |  |  |  |  | 100,000.00 | - |  | 100,000.00 |  | - | Forestry Communities | NADMO |
|  |  | 97. Establishment of forest plantations in degraded forest land through Modified Taungya and industrial plantation |  |  | Anhwiaso, Aboduabo |  |  |  |  |  |  |  | 10,000.00 | - |  | 70,000.00 |  | - | Forestry Commission | CA |
|  |  | 98. Support the implementation youth in afforestation programme |  |  | Municipal wide |  |  |  |  |  |  |  | - | - |  | 20,000.00 |  | - | Forestry Commission | CA |
| Focus Area: Climate Variability and Change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation & Mgt | 99. Train farmers on climate smart agriculture technologies |  |  | Municipal Wide |  |  |  |  |  |  |  | 5,000.00 | - |  | - |  | - | Forestry Commission | CA, NGOs, CSO |
| Environmental Management | Natural Resource Conservation & Mgt | 100. Organize community durbar on climate change in 10 Communities |  |  | Selected towns |  |  |  |  |  |  |  | 2,000.00 | - |  | - |  | - | Forestry Commission | CA, NGOs, CSO Mineral Commission |
| Focus Area: Disaster Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Disaster Prevention and management | 101. Formation of Disaster Risk Reduction clubs in 20 schools |  |  | Selected Schools |  |  |  |  |  |  |  | 2,000.00 | - |  | 5,000.00 |  | - | CA | NADMO |
|  |  | 102. Organise community sensitisation on hazards of fire |  |  | Selected Towns |  |  |  |  |  |  |  | 3,000.00 | - |  | 3,000.00 |  | - | NADMO | GNFS, CA |
| Focus Area: Transportation: Air, Rail, Water and Road |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | Urban roads and transport services | 103. Reshape 100km of feeder roads and building of culvert |  |  | Municipal Wide |  |  |  |  |  |  |  | 300,000.00 | 100,000.00 |  | - |  | - | Works | CA |
|  | Urban roads and transport services/Road Safety | 104. Sensitization on Road Safety policy for drivers and user |  |  | Municipal Wide |  |  |  |  |  |  |  | 10,000.00 | 5,000.00 |  | - |  | - | Works | CA POLICE NRSC NCCE |
| Focus Area: Information Communication Technology Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | ICT | 105. Organise ICT training for the youth |  |  | Bibiani |  |  |  |  |  |  |  | 5,000.00 | 5,000.00 |  | - |  | - | CA | Telcos, MA, NGOs |
|  |  | 106. Construction of ICT Centre |  |  | Kwamekrom |  |  |  |  |  |  |  | 500,000.00 | - |  | - |  | - | CA | MA |
| Focus Area: Human Settlements Development and Housing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | Spatial Planning | 107. Continue the street naming and property addressing |  |  | Asawinso,Humjibre |  |  |  |  |  |  |  | 50,000.00 | - |  | 100,000.00 |  | - | Physical Planning | CA, TA, SPC |
|  |  | 108. Extension of electricity in 4 communities in the Municipality |  |  | Selected |  |  |  |  |  |  |  | 300,000.00 | - |  | - |  | - | Works | CA, TA, SPC |
|  |  | 109. Preparation of Local Plans |  |  | Chirano Anhwiaso |  |  |  |  |  |  |  | 200,000.00 | 70,000.00 |  | - |  | - | Physical Planning | CA, TA, SPC |
|  |  | 110. Landscaping and Gardening |  |  | Bibiani |  |  |  |  |  |  |  | 5,000.00 | - |  | - |  | - | Physical Planning | CA, TA, SPC |
|  |  | 111. Undertake building inspections to ensure compliance with the national building code |  |  | Municipal Wide |  |  |  |  |  |  |  | - | 20,000.00 |  | - |  | - | Physical Planning | CA, TA, SPC |
| Focus Area: Drainage and Flood Control |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | Public Works, Rural Housing and Water Management | 112. Construction of culvert |  |  | 2 Selected Towns |  |  |  |  |  |  |  | 40,000.00 | - |  | - |  | - | NADMO | CA |
| DEVELOPMENT DIMENSION 4: GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Local Governance and Decentralisation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | General Administration | 113. Organize Statutory meetings (Management Meetings, Sub-Committee, Executive Committee & General Assembly Meetings, SAT Meetings etc) |  |  | Bibiani |  |  |  |  |  |  |  | 100,000.00 | 100,000.00 |  | - |  | - | CA | MLGDRD |
|  |  | 114. Maintenance of office equipment |  |  | Bibiani |  |  |  |  |  |  |  | 20,000.00 | 30,000.00 |  | - |  | - | CA | MLGDRD |
|  |  | 115. Construction of Assembly Guest House |  |  | Bibiani |  |  |  |  |  |  |  | 450,000.00 | - |  | - |  | - | CA | MLGDRD |
|  |  | 116. Maintenance of Assembly Vehicles |  |  | Bibiani |  |  |  |  |  |  |  | 30,000.00 | 20,000.00 |  | - |  | - | CA | MLGDRD |
|  |  | 117. Renovation of Staff Quarters |  |  | Bibiani |  |  |  |  |  |  |  | 50,000.00 | 50,000.00 |  | - |  | - | CA | MLGDRD |
|  |  | 118. Procurement of Office Equipment/logistics (6-No servers, 6-No laptops, UPS & Networking Equipment) |  |  | Bibiani |  |  |  |  |  |  |  | 50,000.00 | - |  | - |  | - | CA | MLGDRD |
| Management and Administration | General Administration | 119. Support to Self Help Projects |  |  | Municipal Wide |  |  |  |  |  |  |  | 200,000.00 | - |  | - |  | - | CA | MLGDRD |
|  |  | 120. Support the sub-structures in the Municipality |  |  | Zonal Councils |  |  |  |  |  |  |  | 30,000.00 | - |  | - |  | - | CA | MLGDRD |
|  |  | 121. Repair of street lights and purchase of electric pole |  |  | Municipal wide |  |  |  |  |  |  |  | 50,000.00 | 50,000.00 |  | - |  | - | CA | MLGDRD |
|  |  | 122. Support Decentralized Dept and WNRCC |  |  | Bibiani |  |  |  |  |  |  |  | 50,000.00 | - |  | - |  | - | CA | MLGDRD |
|  |  | 123. Implement Capacity building plan/Staff development |  |  | Bibiani |  |  |  |  |  |  |  | 50,000.00 | 10,000.00 |  | - |  | - | HR Dept. | MLGDRD |
|  |  | 124. Provision for official day celebrations |  |  | Zonal council Capitals |  |  |  |  |  |  |  | 50,000.00 | - |  | - |  | - | CA | MLGDRD |
|  |  | 125. Internal Management of organisation (Utility, fuel, call credit, Hotel Accommodation, NALAG Dues etc) |  |  | Bibiani |  |  |  |  |  |  |  | 50,000.00 | 50,000.00 |  | - |  | - | CA | MLGDRD |
| Management and Administration | Planning, Budgeting, Monitoring & Evaluation | 126. Organize 4 quarterly MPCU meetings |  |  | Bibiani |  |  |  |  |  |  |  | 30,000.00 | 10,000.00 |  | - |  | - | CA | CA |
|  |  | 127. Provision for preparation of 2024 composite budget and fee-fixing resolution |  |  | Bibiani |  |  |  |  |  |  |  | 25,000.00 | - |  | - |  | - | Budget Unit | CA |
|  |  | 128. Conduct of monthly market readings at Sefwi Bekwai and Bibiani |  |  | Bibiani & Bekwai |  |  |  |  |  |  |  | 5,000.00 | - |  | - |  | - | Statistical Service Dept | CA |
| Focus Area: Public Accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Planning, Budgeting, Monitoring & Evaluation | 129. Organise Social Accountability Fora ie. Town Hall meeting, Meet the Press & Social Audit |  |  | Bibiani & Bekwai |  |  |  |  |  |  |  | 40,000.00 | 10,000,00 |  | - |  | - | CA | CA |
| Focus Area: Human Security and Public Safety |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | General Administration | 130. Support for Security operations & MUSEC activities |  |  | Bibiani |  |  |  |  |  |  |  | 20,000,00 | 10,000.00 |  | - |  | - | CA | MLGDRD |
| Focus Area: Corruption and Economic Crimes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | General Administration | 131. Support Anti- Corruption Agencies /Implement NACAP |  |  | Municipal wide |  |  |  |  |  |  |  | 10,000.00 | - |  | - |  | - | CA | CHRAJ, Audit Service, NGOs |
| DEVELOPMENT DIMENSION 5: EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19 RECOVERY PLAN) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Hydro meteorological |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Public Health Services and management | 132. Organize community education programme on hydro metrological disaster |  |  | Selected Communities |  |  |  |  |  |  |  | 2,000.00 | - |  | - |  | - | NADMO | CA |
| Focus Area: Biological |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Public Health Services and management | 133. Organise sensitisation and education programmes on Covid-19 and enforcement of safety protocols |  |  | Municipal wide |  |  |  |  |  |  |  | 20,000.00 | 10,000.00 |  | - |  | - | GHS | CA |
|  |  | 134. Procurement of Covid -19 personal protective equipment eg. Veronica buckets, Nose Masks, thermometer guns etc. |  |  | Bibiani |  |  |  |  |  |  |  | 100,000.00 | - |  | - |  | - | GHS | CA |
|  |  | 135. Support Municipal Public Health Emergency Management Committee &Municipal Public Health Emergency Rapid Response Team activities |  |  | Bibiani |  |  |  |  |  |  |  | 20,000.00 | - |  | - |  | - | GHS | CA |
| Focus Area: Anthropogenic |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Public Health Services and management | 136. Organise disaster mitigation public awareness programmes |  | Selected communities |  |  |  |  |  |  |  |  | 5,000.00 | 2,000.00 | - |  |  | - | NADMO | CA |
| Relief Assistance and Victim Welfare |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Disaster Prevention and management | 137. Support disaster victims with relief items |  | Municipal wide |  |  |  |  |  |  |  |  | 100,000.00 | - | - |  |  | - | NADMO | CA |
| DEVELOPMENT DIMENSION 6: IMPLEMENTATION, COORDINATION, MONITORING AND EVALUATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Planning, Budgeting, Monitoring and evaluation | 138. Organise site meetings/ sod-cutting and project commissioning |  |  | Project Communities |  |  |  |  |  |  |  | 50,000.00 | 20,000.00 |  | - |  | - | CA | MLGDRD |
|  |  | 139. Conduct PM&E of programmes and projects |  |  | Selected Towns |  |  |  |  |  |  |  | 50,000.00 | - |  | - |  | - | CA | MLGDRD |
|  |  | 140. Organise annual APR preparation sessions for Departmental Heads |  |  | Bibiani |  |  |  |  |  |  |  | - | 10,000.00 |  | - |  | - | CA | MLGDRD |
|  |  | 141. Monitor 2022 budget implementation and participate in 2023 Composite Budget hearings |  |  | Bibiani |  |  |  |  |  |  |  | 15,000 | - |  | - |  | - | CA | MLGDRD |
|  |  | 142. Undertake mid-year review of 2022 Action Plan and Programme Based Budget |  |  | Bibiani |  |  |  |  |  |  |  | 5,000.00 | - |  | - |  | - | CA | MLGDRD |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  |  | 8,036,000.00 | 2,938,000.00 |  | 2,471,000.00 | 13,445,000.00 |  |  |  |

##### Table 5.4 Annual Action Plan for 2025

| DEVELOPMENT DIMENSION: ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme (PBB) | Sub- Programme (PBB) |  | Broad Activities | Location | Time Frame |  |  |  |  |  | Cost |  |  |  |  | Programme Status |  | Implementing Institution |  |
|  |  |  |  |  | Q1 |  | Q2 | Q3 |  | Q4 | GoG (GH¢) |  | IGF (GH¢) |  | Others (GH¢) | New | Ongoing | Lead | Collaborating |
| DEVELOPMENT DIMENSION 1: ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Private Sector Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Trade, Industry and Tourism | 1. Training and provision of start-up kits for 60 people in Gari processing, bee keeping, Soap making, Baking &confessionary |  | Municipal wide |  |  |  |  |  |  | 20,000.00 |  | 20,000.00 |  | 10,000.00 |  | - | BAC | CA, (Mensin Gold, Chirano Kenros, Care International) |
|  |  | 2. Provide apprenticeship and start -ups for 30 youth to in carpentry, Masonry, Auto-Mechanics, Welding& Fabrication |  | Municipal wide |  |  |  |  |  |  | 20,000.00 |  | 40,000.00 |  | 10,000.00 |  | - | BAC | CA, Mining Companies, RTF |
|  |  | 3. Organise management training for 120 SMEs and Entrepreneurs |  | Municipal wide |  |  |  |  |  |  | 30,000.00 |  | 40,000.00 |  | 20,000.00 |  | - | BAC | CA |
|  |  | 4. Support Agriculture value chain Actors & SMEs with Revolving Funds |  | Municipal wide |  |  |  |  |  |  | 20,000.00 |  | - |  | 600,000.00 |  | - | BAC | EU, Sefwiman Rural Bank |
|  |  | 5. Partner with financial institutions to provide loans to SMEs |  | Municipal wide |  |  |  |  |  |  | 20,000.00 |  | 10,000.00 |  | - |  | - | BAC | Financial Institutions, Economic groups |
| Focus Area: Focus Area: Strong and Resilient Economy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Finance | 6. Revenue sensitization and rateable property data collection |  | Municipal Wide |  |  |  |  |  |  |  |  | 15,000.00 |  | - |  | - | Finance | CA |
|  |  | 7. Support training of Municipal Revenue Collectors on digital revenue mobilisation strategies |  | Municipal Wide |  |  |  |  |  |  | 23,000.00 |  | 20,000.00 |  | - |  | - | Finance Dept | CA |
| Focus Area: Agriculture and Rural Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Agricultural Services and Management | 8. Implement government flagship programmes in Agric ie MAG, PFJ, DCACT, PERD |  | Municipal wide |  |  |  |  |  |  | - |  | 20,000.00 |  | 100,000.00 |  | - | MDA | CA, Farmers, Financial Institutions |
|  |  | 9. Organize District Farmers Day Celebrations |  | Asawinso |  |  |  |  |  |  | 50,000.00 |  | 30,000.00 |  | 20,000.00 |  | - | MDA | CA, Farmers, Financial Institutions |
|  |  | 10. Training of AEAs, DDOs and farmers on crops and animals |  | Bibiani |  |  |  |  |  |  | - |  | - |  | 25,000.00 |  | - | MDA | CA, Farmers, Financial Institutions |
|  |  | 11. Organise Sensitisation for the youth to go into Agriculture |  | Municipal Wide |  |  |  |  |  |  | - |  | 5,000.00 |  | 30,000.00 |  | - | MDA | NCCE, ISD |
|  |  | 12. Supply of subsidized fertilizers, improved seedlings, animal breeds and other inputs to farmers |  | Municipal wide |  |  |  |  |  |  | - |  | - |  | 50,000.00 |  | - | MDA | CA, MoFA & Farmers, |
|  |  | 13. Provision of veterinary and Extension services to farmers |  | Municipal wide |  |  |  |  |  |  | - |  | - |  | 10,000.00 |  | - | MDA | CA, Farmers, Financial Institutions |
|  |  | 14. Support farmers with Agriculture equipment such as Tillers and tractors |  | Municipal Wide |  |  |  |  |  |  | - |  | - |  | 20,0000.00 |  | - | MDA | CA, Farmers |
|  |  | 15. Organise bi-monthly technical review and stakeholder meetings |  | Bibiani |  |  |  |  |  |  | - |  | - |  | 24,000.00 |  | - | MDA | CA, Farmers |
|  |  | 16. Conduct monthly data collection on yield studies and market surveying |  | Municipal Wide |  |  |  |  |  |  | - |  | - |  | 15,000.00 |  | - | MDA | CA, Farmers |
|  |  | 17. Organise monthly field demonstration on crop and animal production |  | Municipal Wide |  |  |  |  |  |  | - |  | - |  | 15,000.00 |  | - | MDA | CA, Farmers |
|  |  | 18. Support MDA and staff attending Region planning sessions, workshops, seminars and conferences |  | Municipal Wide |  |  |  |  |  |  | - |  | - |  | 30,000.00 |  | - | MDA | CA, Farmers |
|  |  | 19. Support the procurement of extension materials and Covid 19 PPEs |  | Municipal Wide |  |  |  |  |  |  | - |  | 9,000.00 |  | 60,000.00 |  | - | MDA | CA, Farmers |
|  |  | 20. Support MDA running and maintenance of official vehicles, motor bikes and office equipment |  | Municipal Wide |  |  |  |  |  |  | - |  | - |  | 17,000.00 |  | - | MDA | CA |
| Focus Area: Tourism and Creative Arts Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Trade, Industry and Tourism | 21. Project independence day celebration |  | Municipal wide |  |  |  |  |  |  | - |  | 50,000.00 |  | 50,000.00 |  | - | CA | MLGDRD |
|  |  | 22. Support LED activities and holding of business seminars on local economic growth |  | Municipal Wide |  |  |  |  |  |  | - |  | 65,000.00 |  | 35,000.00 |  | - | BAC | BAC |
| DEVELOPMENT DIMENSION 2: SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Education and Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Service Delivery Social Service Delivery | Education, Youth & Sports and Library services Education, Youth & Sports and Library services | 23. Construction of 1No. K.G Block with Ancillary Facilities |  | Mframakrom |  |  |  |  |  |  | 250,000.00 |  | - |  | - |  | - | GES | CA |
|  |  | 24. Construction of 2 No.3-Units Classroom Block with Ancillary Facilities |  | Mpesiem, Manse |  |  |  |  |  |  | 380,000.00 |  | - |  | 380.000.00 |  | - | GES | CA |
|  |  | 25. Construction of 1No. 6-Unit Classroom Block with Office and Store |  | Donkorkrom,Kyenkyenase |  |  |  |  |  |  | 600.000.00 |  | - |  | - |  | - | GES | CA |
|  |  | 26. Rehabilitation of Schools |  | Wenchi, Nkatieso |  |  |  |  |  |  | 200.000.00 |  | - |  | - |  | - | GES | CA |
|  |  | 27. Construction of Dinning Hall for Sefwi Bekwai SHS |  | Sefwi Bekwai |  |  |  |  |  |  | 800,000.00 |  | - |  | - |  | - | GES | CA |
|  |  | 28. Organize best teacher awards |  | Bibiani |  |  |  |  |  |  | - |  | 50,000.00 |  | 50,000.00 |  | - | GES | CA, Private Sector, CSOs |
|  |  | 29. STMIE for 30 student from selected schools |  | Municipal wide |  |  |  |  |  |  | - |  | - |  | 35,000.00 |  | - | GES | CA |
|  |  | 30. Mock exams for BECE candidates |  | Municipal wide |  |  |  |  |  |  | 200,000.00 |  | - |  | - |  | - | GES | CA |
|  |  | 31. Support My 1st Day at school |  | Selected Schools |  |  |  |  |  |  | 5,000.00 |  | - |  | - |  | - | GES | CA |
|  |  | 32. Organize Inter-schools’ sports and athletic competition |  | Municipal Wide |  |  |  |  |  |  | - |  | 45.000.00 |  | 10,000.00 |  | - | GES | CA |
|  |  | 33. Organise capacity building for Teachers |  | Bibiani |  |  |  |  |  |  | 10,000.00 |  | 20,000.00 |  | 20,000.00 |  | - | GES | CA |
|  |  | 34. Supply of 1000 Mono Desk & 1000 Dual Desk for schools |  | Selected Schools |  |  |  |  |  |  | 100,000.00 |  | 40,000.00 |  | - |  | - | GES | CA |
| Focus Area: Health and Health Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Service Delivery | Public Health Services and Management | 35. Construction of 1No. CHPS Compound |  | Afaamu |  |  |  |  |  |  | 350,000.00 |  | - |  | - |  | - | GHS | CA |
|  |  | 36. Procurement of 5 delivery beds for CHPS compounds |  | Municipal wide |  |  |  |  |  |  | 65,000.00 |  | - |  | - |  | - | GHS | CA |
|  |  | 37. Procurement of 5 delivery sets for CHPS compounds |  | Municipal wide |  |  |  |  |  |  | 40,000.00 |  | - |  | - |  | - | GHS | CA |
|  |  | 38. Support malaria control activities |  | Municipal wide |  |  |  |  |  |  | - |  | 30,000.00 |  | - |  | - | GHS | CA, Private Sector, NGOs |
|  |  | 39. Support for HIV/Aids control activities |  | 10 Towns/ 1 FM Stations |  |  |  |  |  |  | - |  | 30,000.00 |  | - |  | - | GHS | CA, CSOs |
|  |  | 40. Intensify education to reduce stigmatisation |  | Municipal wide |  |  |  |  |  |  | 8,000.00 |  | - |  | - |  | - | GHS | CA |
|  |  | 41. Intensify behavioural change strategies, especially for high risks groups for HIV/AIDS and TB |  | Municipal wide |  |  |  |  |  |  | 8,000.00 |  | 10,000.00 |  | - |  | - | GHS | CA |
|  |  | 42. Support for National immunization campaigns and Neglected Tropical Disease Control Programme |  | Municipal wide |  |  |  |  |  |  | 20,000.00 |  | 10,000.00 |  | - |  | - | GHS | CA |
|  |  | 43. Public Health Emergency Management Committee (PHEMC) |  | Municipal wide |  |  |  |  |  |  | 20,000.00 |  | 30,000.00 |  | - |  | - | GHS | CA |
|  |  | 44. Municipal Health Committee Meetings |  | Municipality |  |  |  |  |  |  | - |  | 10,000.00 |  | 10,000.00 |  | - | GHS | CA |
|  |  | 45. Management of Public Health emergencies i e. disease outbreak, etc |  | Municipal wide |  |  |  |  |  |  | 250,000.00 |  | - |  | - |  | - | GHS | CA |
|  | Hygiene | 46. Provide public education on solid waste management in 40 communities |  | Municipal wide |  |  |  |  |  |  | 15,000.00 |  | 25,000.00 |  | 2000.00 |  | - | MEHO | CA |
|  |  | 47. Promote public health education and hygiene in 32 basic schools |  | Municipal wide |  |  |  |  |  |  | 20,000.00 |  | 20,000.00 |  | 2,000.00 |  | - | MEHO/GHS | MA |
|  |  | 48. Training and screening of 800 food vendor |  | Municipal wide |  |  |  |  |  |  | 38,000.00 |  | 20,000.00 |  | - |  | - | MEHO/GHS | CA |
| Focus Area: Food and Nutrition Security |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Service Delivery | Public Health Services and Management | 49. Promote nutritionally sensitive and cost effective diet through education and sensitization in 10 communities |  | Municipal wide |  |  |  |  |  |  | 10,000.00 |  | 2000.00 |  | 2,000.00 |  | - | GHS | CA, Private Sector, |
|  |  | 50. Promote the production of diversified, nutrient-rich food and consumption of nutrition foods |  | Municipal wide |  |  |  |  |  |  | 10,000.00 |  | 22,000.00 |  | 2000,00 |  | - | GHS | CA |
|  |  | 51. Sensitisation to reduce infant and adult malnutrition |  | Municipal wide |  |  |  |  |  |  | 10,000.00 |  | 35,000.00 |  | 2000.00 |  | - | GHS | CA |
| Focus Area: Population Management and Migration for Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Public Health Services and management | 52. Organise sensitisation programme on Teenage pregnancy on radio |  | Bibiani |  |  |  |  |  |  | 10,000.00 |  | 22,000.00 |  | - |  | - | SWCD | CA UNICEF |
| Focus Area: Reducing Poverty and Inequality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Services | 53. Monitor and coordinate Livelihood Empowerment Against Poverty (LEAP) programme |  | Municipal Wide |  |  |  |  |  |  | 4,000.00 |  | 20,000.00 |  | - |  | - | SW&CD | CA |
|  |  | 54. Coordinate activities of School Feeding Programme |  | Beneficiary schools |  |  |  |  |  |  | 10,000.00 |  | 20,000.00 |  | - |  | - | SW&CD | CA |
|  |  | 55. Provision of Medical Support to the 100 vulnerable patient |  | Municipal Wide |  |  |  |  |  |  | 50,000.00 |  | 50,000.00 |  | - |  | - | SWCD | CA |
|  |  | 56. Support 400 Vulnerable people to get NHIS Cards |  | Municipal Wide |  |  |  |  |  |  | 15,000.00 |  | 15,000.00 |  | - |  | - | SWCD | CA |
| Focus Area: Water and Environmental Sanitation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | Public Works, Rural Housing and Water Management | 66. Construction of 5No. Mechanized boreholes |  | Adamukrom, Surano-A, Donkorkrom, Alata, Naama, Nsuoakyi,, Anyinase |  |  |  |  |  |  | 160,000.00 |  | 40,000.00 |  | - |  | - | Works Dept. | CA, CWSA |
|  |  | 67. Formation and training of WATSANS members in 7 communities |  | Selected Towns |  |  |  |  |  |  | 10,000.00 |  | 10,000.00 |  | - |  | - | EHU | CA |
|  |  | 68. Construction of 1No. 12 seater Toilet Facility (Support households to construct improved household toilet facilities) Technical & Material |  | Awaso-Asempanaye |  |  |  |  |  |  | 350,000.00 |  | - |  | - |  | - | EHU | CA |
|  |  | 69. Maintenance of 10 No. Borehole |  | 10 communities |  |  |  |  |  |  | 40,000.00 |  | - |  | - |  | - | Works Dept. | CA |
| Social Services Delivery | Environmental Health and Sanitation Services | 70. Procure 5No. refuse containers and sanitary tools |  | Selected Towns |  |  |  |  |  |  | 70,000.00 |  | - |  | - |  | - | EHU | CA |
|  |  | 71. Conduct screening of food vendors |  | Municipal Wide |  |  |  |  |  |  | 10,000.00 |  | 15,000.00 |  | - |  | - | EHU | CA |
|  |  | 72. Conduct environmental health /hygiene education in 40 communities |  | Municipal Wide |  |  |  |  |  |  | 2,000.00 |  | 10,000.00 |  | - |  | - | EHU | GES, NGOs |
|  |  | 73. Pest and vector control |  | Bibiani |  |  |  |  |  |  | 10,000.00 |  | 10,000.00 |  | - |  | - | EHSU | CA |
|  |  | 74. Solid and liquid waste management, (Fumigation, manage wasteland fills Contract with Zoomlion) |  | Municipal Wide |  |  |  |  |  |  | 300,000.00 |  | - |  | - |  | - | EHSU | CA, Zoomlion |
|  |  | 75. Construction of Toilet Facility |  | Bibiani |  |  |  |  |  |  | - |  | 400,000.00 |  | - |  | - | EHU | CA |
|  |  | 76. Promote household toilet construction (CLTS) |  | 10 Communities |  |  |  |  |  |  | - |  | 20,000.00 |  | - |  | - | EHU | CA |
| Focus Area: Child Protection and Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Services | 77. Formation of Community Child Protection Committees in 10 Child labour endemic communities and train them on child labour issues |  | Selected Towns |  |  |  |  |  |  | 10,000.00 |  | 22,000.00 |  | 10,000.00 |  | - | SW&CD | CA NGOs |
|  |  | 78. Organize sensitization programmes on child labour |  | Bibiani |  |  |  |  |  |  | 10,000.00 |  | 20,000.00 |  | 20,000.00 |  | - | SW&CD | CA, NGOs |
|  |  | 79. Remediation support for children |  | Bibiani |  |  |  |  |  |  | 10,000.00 |  | 20,000.00 |  | 20,000.00 |  | - | SWCD | CA |
| Focus Area: Gender Equality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 80. Organise sensitization programme on Persistent negative discriminatory socio-cultural, traditional beliefs and customary practices against women |  | Bibiani |  |  |  |  |  |  | 5,000.00 |  | 20,000.00 |  | 5,000.00 |  | - | SW&CD | CA, NGOs |
|  |  | 81. Provide educational support to 10 female students pursuing science at the Tertiary level |  | Municipal wide |  |  |  |  |  |  | 30,000.00 |  | 20,000.00 |  | - |  | - | SW&CD | CA |
| Focus Area: Sports and Recreation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education, youth &sports and library services | 82. Organise community Football gala |  | Bibiani |  |  |  |  |  |  | 20,000.00 |  | 20,000.00 |  | - |  | - | CA | Community members |
| Focus Area: Youth Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education, youth &sports and library services | 83. Organise capacity building workshops for the youth to orient them on the need to venture into entrepreneurship |  | Bibiani |  |  |  |  |  |  | 5,000.00 |  | 35,000.00 |  | - |  | - | BAC | CA, Private Sector, NABCO |
| Focus Area: Social Protection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Welfare and Community Services | 84. Organise radio programme on child right and child protection issue |  | Bibiani |  |  |  |  |  |  | 2,000.00 |  | 10,000.00 |  | 5,000.00 |  | - | SW& CD | CA, UNICEF |
| Focus Area: Disability-Inclusive Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Welfare and Community Services | 85. Provide medical /assistive device to PWDs |  | Municipal wide |  |  |  |  |  |  | 10,000.00 |  | 10,000.00 |  | - |  | - | SW& CD | CA, PWDs |
|  |  | 86. Organise Advocacy & awareness creation on the rights & responsibilities of PWDs |  | Bibiani |  |  |  |  |  |  | 12,000.00 |  | 15,000.00 |  | - |  | - | SW& CD | CA, PWDs |
|  |  | 87. Provide educational/apprenticeship support to PWDs |  | Municipal wide |  |  |  |  |  |  | 10,000.00 |  | 35,000.00 |  | - |  | - | SW& CD | CA, PWDs |
|  |  | 88. Procure items such as fridges, Tricycles, start-ups etc, to support PWDs to enter into income generation activities |  | Municipal wide |  |  |  |  |  |  | 60,000.00 |  | 30,000.00 |  | - |  | - | SW& CD | CA, PWDs |
|  |  | 89. Strengthening organisation of person with Disability |  | Bibiani |  |  |  |  |  |  | 18,000.00 |  | 20,000.00 |  | - |  | - | SW& CD | CA, PWDs |
| Focus Area: Employment and Decent Work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Welfare and Community Services | 90. Support government flagship programmes such as NABCO &YEA |  | Bibiani |  |  |  |  |  |  | 20,000.00 |  | - |  | 20,000.00 |  | - | NABCO, YEA | CA |
| DEVELOPMENT DIMENSION 3: ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Protected Areas |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Management | 91. Facilitate alternative livelihoods including eco-tourism support schemes for fringe communities along protected areas |  | Chine, Anhwiaso, Aboduabo, Asawinso |  |  |  |  |  |  | 4,000.00 |  | 60,000.00 |  | 10,000.00 |  | - | Forestry Commission | CA, NGOs, CSO, Chiefs |
|  |  | 92. Monitor forest reserves to prevent illegal logging a |  | All Forest Reserves |  |  |  |  |  |  | 20,000.00 |  | 25,000.00 |  | 60,000.00 |  | - | Forestry Commission | Chiefs, CA |
| Focus Area: Mineral Extraction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Management | 93. Facilitate the implementation of community mining |  | Selected communities |  |  |  |  |  |  | 10,000.00 |  | - |  | 60,000.00 |  | - | Minerals Commission | CA, NGOs, CSO, Chiefs Minerals Commission |
|  |  | 94. Organise sensitization programme on illegal mining, deforestation and land reclamation |  | Selected communities |  |  |  |  |  |  | 5,000.00 |  | 4,000.00 |  | 20,000.00 |  | - | Minerals Commission | CA, NGOs, CSO, Chiefs Minerals Commission |
| Focus Area: Water Resources Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Management | 95. Enforcement of development control on water bodies |  | Municipal wide |  |  |  |  |  |  | 10,000.00 |  | - |  | 30,000.00 |  | - | Forestry Commission | CA, NGOs, CSO, Chiefs, Minerals Commission |
| Focus Area: Environmental Pollution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Management | 96. Enforce environmental laws and regulations to prevent noise pollution |  | Municipal Wide |  |  |  |  |  |  | 7,000.00 |  | - |  | 23,000.00 |  | - | Forestry Commission | CA, NGOs, CSO, MWST, |
|  |  | 97. Promote the use of LPG as alternative sources of energy by households |  | Municipal wide |  |  |  |  |  |  | 2,000.00 |  | - |  | 5,000.00 |  | - | NADMO | FC |
| Focus Area: Deforestation, Desertification and Soil Erosion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Management | 98. Planting of 100,000 trees across the municipality |  | Municipal wide |  |  |  |  |  |  | 100,000.00 |  | - |  | 50,000.00 |  | - | Forestry Communities | NADMO |
|  |  | 99. Establishment of forest plantation s in degraded forest land through Modified Taungya and industrial plantation |  | Anhwiaso, Aboduabo |  |  |  |  |  |  | 10,000.00 |  | - |  | 54,000.00 |  | - | Forestry Commission | CA |
|  |  | 100. Support the implement youth in afforestation programme |  | Municipal wide |  |  |  |  |  |  | - |  | - |  | 70,000.00 |  | - | Forestry Commission | CA |
| Focus Area: Climate Variability and Change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation & Mgt | 101. Train farmers on climate smart agriculture technologies |  | Municipal Wide |  |  |  |  |  |  | 5,000.00 |  | - |  | 40,000.00 |  | - | Forestry Commission | CA, NGOs, CSO, CWSA |
| Environmental Management | Natural Resource Conservation & Mgt | 102. Organize community durbar on climate change in 10 Communities |  | Selected towns |  |  |  |  |  |  | 2,000.00 |  | - |  | 35,000.00 |  | - | Forestry Commission | CA, NGOs, CSO,Mineral Commission |
| Focus Area: Disaster Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Disaster Prevention and management | 103. Formation of Disaster Risk Reduction clubs in 20 schools |  | Selected Schools |  |  |  |  |  |  | 2,000.00 |  | - |  | 5,000.00 |  | - | CA | NADMO, CSOs |
|  |  | 104. Organise community sensitisation on hazards of fire |  | Selected Towns |  |  |  |  |  |  | 3,000.00 |  | - |  | 13,000.00 |  | - | NADMO | GNFS, CA |
|  |  | 105. Establishment of fire station |  | Sefwi Bekwai |  |  |  |  |  |  | 200,000.00 |  | - |  | - |  | - | NADMO | GNSF, CA |
| Focus Area: Transportation: Air, Rail, Water and Road |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | Urban roads and transport services | 106. Reshape 100km of feeder roads and building of culvert |  | Municipal Wide |  |  |  |  |  |  | 300,000.00 |  | 100,000.00 |  | - |  | - | Works | CA |
|  | Urban roads and transport services | 107. Sensitization on Road Safety policy for drivers and user |  | Municipal Wide |  |  |  |  |  |  | 10,000.00 |  | 5,000.00 |  | 5,000.00 |  | - | Works | CA GPS NRSC NCCE |
| Focus Area: Information Communication Technology Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | ICT | 108. Organise ICT training for the youth |  | Bibiani |  |  |  |  |  |  | 5,000.00 |  | 5,000.00 |  | 10,000.00 |  | - | CA | CA, NGOs |
| Focus Area: Human Settlements Development and Housing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | Spatial Planning | 109. Continue the street naming and property addressing |  | Afamu Tanoso/ Praso |  |  |  |  |  |  | 50,000.00 |  | - |  | 100,000.00 |  | - | Physical Planning | CA, Chiefs, SPC |
|  |  | 110. Extension of electricity in 8 communities in the Municipality |  | Selected Communities |  |  |  |  |  |  | 300,000.00 |  | - |  | - |  | - | Physical Planning | CA, Chiefs, SPC |
|  |  | 111. Preparation of local plans |  | Awaso Atronsu |  |  |  |  |  |  | 200,000.00 |  | - |  | - |  | - | Physical Planning | CA, Chiefs, SPC |
|  |  | 112. Landscaping and Gardening |  | Bibiani |  |  |  |  |  |  | 5,000.00 |  | - |  | 5,000.00 |  | - | Physical Planning | CA, , SPC |
|  |  | 113. Undertake building inspections to ensure compliance with the national building code |  | Municipal Wide |  |  |  |  |  |  |  |  | 20,000.00 |  | 10,000.00 |  | - | Physical Planning | CA, Chief, SPC |
| Focus Area: Drainage and Flood Control |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | Public Works, Rural Housing and Water Management | 114. Desilting and reconstruction of drains |  |  |  |  |  |  |  |  | 20,000.00 |  | 10,000.00 |  | 10,000.00 |  | - | EHU | CA |
| DEVELOPMENT DIMENSION 4: GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Local Governance and Decentralisation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | General Administration | 115. Organize Statutory meetings (Management Meetings, Sub-Committee, Executive Committee & General Assembly Meetings, SAT Meetings etc) |  | Bibiani |  |  |  |  |  |  | - |  | 200,000.00 |  | - |  | - | CA | MLGDRD |
|  |  | 116. Maintenance of office equipment |  | Bibiani |  |  |  |  |  |  | 20,000.00 |  | 30,000.00 |  | 20,000.00 |  | - | CA | MLGDRD |
|  |  | 117. Construction of Assembly Guest House |  | Bibiani |  |  |  |  |  |  | 450,000.00 |  | - |  | - |  | - | CA | MLGDRD |
|  |  | 118. Maintenance of Assembly Vehicles |  | Bibiani |  |  |  |  |  |  | 30,000.00 |  | 20,000.00 |  | - |  | - | CA | MLGDRD |
|  |  | 119. Renovation of Staff Quarters |  | Bibiani |  |  |  |  |  |  | 50,000.00 |  | 50,000.00 |  | - |  | - | CA | MLGDRD |
|  |  | 120. Procurement of Office Equipment/ logistics (6-No servers, 6-No laptops, UPS & Networking Equipment) |  | Bibiani |  |  |  |  |  |  | 50,000.00 |  | - |  | 15,000.00 |  | - | CA | MLGDRD |
| Management and Administration | General Administration | 121. Support to Self Help Projects |  | Municipal Wide |  |  |  |  |  |  | 200,000.00 |  | - |  | - |  | - | CA | MLGDRD |
|  |  | 122. Support the sub-structures in the Municipality/Construction of 1 No. Zonal Council Office |  | Zonal Councils |  |  |  |  |  |  | 300,000.00 |  | - |  | - |  | - | CA | MLGDRD |
|  |  | 123. Repair of street lights and purchase of electric pole |  | Municipal wide |  |  |  |  |  |  | 50,000.00 |  | 50,000.00 |  | - |  | - | CA | MLGDRD |
|  |  | 124. Implement Capacity building plan/Staff development |  | Bibiani |  |  |  |  |  |  | 50,000.00 |  | 10,000.00 |  | - |  | - | HR Dept. | MLGDRD |
|  |  | 125. Provision for official day celebrations |  | Zonal council Capitals |  |  |  |  |  |  | 50,000.00 |  |  |  | - |  | - | CA | MLGDRD |
|  |  | 126. Internal Management of organisation (Utility, fuel, call credit, Hotel Accommodation, NALAG Dues etc) |  | Bibiani |  |  |  |  |  |  | 50,000.00 |  | 50,000.00 |  | - |  | - | CA | MLGDRD |
| Management and Administration | Planning, Budgeting, Monitoring & Evaluation | 127. Organize 4 Quarterly MPCU meetings |  | Bibiani |  |  |  |  |  |  | 100,000.00 |  | 10,000.00 |  | 40,000.00 |  | - | CA | MLGDRD |
|  |  | 128. Provision for preparation of 2023 composite budget and fee-fixing resolution |  | Bibiani |  |  |  |  |  |  | 25,000.00 |  | - |  | - |  | - | Budget Unit | MLGDRD |
|  |  | 129. Conduct of monthly market readings at Sefwi Bekwai and Bibiani |  | Bibiani & Bekwai |  |  |  |  |  |  | 5,000.00 |  | - |  | - |  | - | Statistical Service Dept | CA |
| Focus Area: Public Accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Planning, Budgeting, Monitoring & Evaluation | 130. Organise Social Accountability Fora ie. Town Hall meeting, Meet the Press & Social Audit |  | Bibiani & Bekwai |  |  |  |  |  |  | 40,000.00 |  | 10,000,00 |  | - |  | - | CA | MLGDRD |
| Focus Area: Human Security and Public Safety |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | General Administration | 131. Support for Security operations & MUSEC activities |  | Bibiani |  |  |  |  |  |  | 20,000,00 |  | 10,000.00 |  | - |  | - | CA | RCC, MLGDRD |
| Focus Area: Corruption and Economic Crimes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | General Administration | 132. Support Anti- Corruption Agencies /Implement NACAP |  | Municipal wide |  |  |  |  |  |  | 10,000.00 |  | - |  | - |  | - | CA | CHRAJ, Audit Service, NCCE,NGOs |
| DEVELOPMENT DIMENSION 5: EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19 RECOVERY PLAN) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Hydro meteorological |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Public Health Services and management | 133. Organize community education programme on hydro metrological disaster |  | Selected Communities |  |  |  |  |  |  | 2,000.00 |  | - |  | - |  | - | NADMO | CA |
|  |  | Dredging and widening of stream channels |  | Bekwai & Bibiani |  |  |  |  |  |  | 40,000.00 |  | - |  | - |  | - | Works Dept | CA |
| Focus Area: Biological |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Public Health Services and management | 134. Organise sensitisation and education programmes on Covid-19 and enforcement of safety protocols |  | Municipal wide |  |  |  |  |  |  | 20,000.00 |  | 10,000.00 |  | - |  | - | GHS | CA |
|  |  | 135. Procurement of Covid -19 personal protective equipment eg. Veronica buckets, Nose Masks, thermometer guns etc. |  | Bibiani |  |  |  |  |  |  | 100,000.00 |  | - |  | - |  | - | GHS | CA |
|  |  | 136. Support Municipal Public Health Emergency Management Committee &Municipal Public Health Emergency Rapid Response Team activities |  | Bibiani |  |  |  |  |  |  | 20,000.00 |  | - |  | - |  | - | GHS | CA |
|  |  | 137. Vaccination against public health emergencies such as Covid-19 |  | Municipal wide |  |  |  |  |  |  | 10,000.00 |  | - |  | - |  | - | GHS | CA |
| Focus Area: Anthropogenic |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Public Health Services and management | 138. Organise disaster mitigation public awareness programmes |  | Selected communities |  |  |  |  |  |  |  | 5,000.00 |  | 2,000.00 | - |  | - | GHS/ NADMO | CA |
| Relief Assistance and Victim Welfare |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Disaster Prevention and management | 139. Support disaster victims with relief items |  | Municipal wide |  |  |  |  |  |  |  | 100,000.00 |  | - | - |  | - | NADMO | CA |
| DEVELOPMENT DIMENSION 6: IMPLEMENTATION, COORDINATION, MONITORING AND EVALUATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Planning, Budgeting, Monitoring and evaluation | 140. Organise site meetings/ sod-cutting and project commissioning |  | Project Communities |  |  |  |  |  |  | 50,000.00 |  | 20,000.00 |  | - |  | - | CA | RCC, MLGDRD |
|  |  | 141. Conduct PM&E of programmes and projects |  | Selected Towns |  |  |  |  |  |  | 50,000.00 |  | - |  | - |  |  | CA | RCC, MLGDRD |
|  |  | 142. Organise annual APR preparation sessions for Departmental Heads |  | Bibiani |  |  |  |  |  |  | - |  | 10,000.00 |  | - |  |  | CA | RCC, MLGDRD |
|  |  | 143. Monitor 2022 budget implementation and participate in 2023 Composite Budget hearings |  | Bibiani |  |  |  |  |  |  | 15,000 |  | - |  | - |  |  | CA | RCC, MLGDRD |
|  |  | 144. Undertake mid-year review of 2022 Action Plan and Programme Based Budget |  | Bibiani |  |  |  |  |  |  | 5,000.00 |  | - |  | - |  |  | CA | RCC, MLGDRD |
| Total |  |  |  |  |  |  |  |  |  |  | 7,243,000.00 |  | 1,458,000.00 |  | 2,033,000.00 | 10,734,000.00 |  |  |  |

# CHAPTER SIX

# MONITORING AND EVALUATION ARRANGEMENTS

## 6.1 Introduction

This chapter outlines the 2022-2025 DMTDP the stakeholder’s analysis of the Assembly, the Monitoring and Evaluation conditions and capacities of the Service in addition to indicators and targets. Again, this chapter indicates Monitoring and Evaluation Matrix, calendar, budget, data collection, collation and analysis in the Service. It also provides information on M&E report and findings, dissemination, participatory monitoring and evaluation processes among others.

## 6.2 Stakeholders Analysis

The initial task in Monitoring and Evaluation was the identification of various stakeholders of the Bibiani Anhwiaso Bekwai Municipal Assembly. These are individuals, institutions and groups of people who have interest in the implementation, monitoring and evaluation of the 2022-2025 MTDP.

This is relevant in the sense that, the identification and participation of these stakeholders will lead to ownership, sustained capacity building, dissemination and demand for Monitoring and Evaluation results. In doing this, all stakeholders were identified and analysed with a critical look at their background information and their various roles, responsibilities and needs.

Table 6.1 outlines a list of key stakeholders who have interest in the implementation of the Plan at various levels. It is expected that all the stakeholders identified, will contribute to the successful implementation of this plan.

##### Table 6.1: Stakeholder Analysis

| S/N | Stakeholders | Classifications | Information needs/interest/responsibility | Involvement in M&E Activities | Impacts |
| --- | --- | --- | --- | --- | --- |
| 1 | Ministries, Departments and Agencies (MDAs) | Primary/ Secondary | Practical changes occurring in their respective sub-sectors | - Data collection and analysis - Preparation of progress reports - Formulation of policies for projects and programmes - Provision of technical backstopping | High |
| 2 | LGSC | Primary | General Management and Control of the Service | - Assist in monitoring government policies plans and programmes of MMDAs, RCCs and LGSS - Advice the Service on findings of their monitoring exercise | Medium |
| 3 | Ministry of Finance | Primary | Policy formulation and capacity building | Technical Backstopping | Medium |
| 4 | NDPC | Primary | Policy formulation, guidelines and capacity building | M&E Plan preparation, evaluations and result disseminations | High |
| 5 | DACF-RFG Secretariat | Primary | Financial Resources and guidelines | M&E seminars, Meetings, supervision and reporting of M&E results | Low |
| 6 | ILGS | Secondary | Provide Training for Local Government Functionaries | Provide M&E capacity building to MMDAs | Medium |
| 7 | Member of Parliament | Primary | Law-making, common fund for Programmes and projects, advocacy for development initiate Programme and projects and support the vulnerable in the constituency | M&E Seminars and Meetings, supervision, evaluations, project inspection and reporting on M&E results | Low |
| 8 | RCCs/ RPCUs | Primary | Coordination, harmonization, monitoring and evaluation of activities of MMDAs & MDAs | - Assist in monitoring of government policies - Coordinate activities of MMDAs plans and programmes of MMDAs - Advice the Service on findings of their monitoring exercise | High |
| 9 | Municipal Assembly | Primary | - Resources should be available for implementation - Extent of community participation in plan implementation | - Monitor and evaluate DMTDP - Participatory M&E - Data collection, analysis data and report to appropriate offices - Dissemination of M&E information - 6 Ensure proper utilization of Funds | High |
| 10 | Zonal Councils and unit committees | Secondary | - Status of implementation of Government policies and DMTDPs - Level of support provided to the sub- structure | - Mobilize community people for assessments - Provide inputs to monitor the implementation of plans and programmes | High |
| 11 | Development Partners | Secondary | Ensure quality, effective and efficient delivery of service | - Provide funds and capacity building to MMDAs and the Service - Provide, funding, logistics and technical support for M&E - Implement projects and programmes in line with government policies | Medium |
| 10 | Traditional Authorities | Secondary | - Ensure Participatory Monitoring and Evaluation - Provide land for development projects. | - Ensure proper utilization of funds - Mobilize both human and capital resources for development at the local level - Dissemination of M&E information to local people | High |
| 11 | Service providers | Primary & Secondary | Provide consultancy, works/infrastructure services | - Provision of training and capacity building services - Involvement in data collection and analysis | High |
| 12 | Other MMDAs | Secondary | Guidelines and advisory services | Data collection, M&E results reporting and dissemination | Low |
| 13 | Political Parties | Secondary | Act as pressure groups, evaluate the performance of government and mobilize people for political and development activities | M&E seminars and meetings, supervision, project inspection, evaluation, M&E reporting and dissemination | Low |
| 14 | CSOs NGOs CBOs | Secondary | Practical changes occurring in their respective jurisdictions/communities | - Advocate, initiate and support development plan, programmes & projects and undertake M&E exercise - Dissemination of M&E reports - Provision of logistics and equipment - Build capacity for M&E | Medium |
| 15 | Other Decentralized Departments | Secondary | Responsible for implementation of government policies at the local level, provision of social, economic, security, legal and other services such as adult education | Data collection, evaluation, M&E reporting and dissemination | Low |
| 16 | Media | Secondary | Status of implementation of development programmes and projects | - Demand transparency and accountability - Communicate information to the public and obtain feedback | Medium |

Source: MPCU, 2021

## 6.3 Monitoring of Development Programmes/Projects

It is important to institute measures to keep track of the Implementation and Management of Community/Urban/Zonal Council and the Municipal Assembly initiatives. This is to ensure that activities are implemented on time and with the required level of efficiency.

In view of the above, a monitoring and evaluation plan has been  prepared in accordance with the guidelines provided by the National Development Planning Commission to provide the framework to monitor and evaluate the plan for the period 2022-2025 to the government’s Agenda for Growth, Jobs, Prosperity and Equal Opportunity for All.

The objectives of the monitoring and evaluation of the plan include the following:

- To ascertain whether or not activities are on track and take pragmatic measures where possible.

- Identify successful interventions for replication in other areas of the Municipality.

- Obtain periodic data for further planning.

- Promote co-ordination and balance in service provision and utilization.

- Motivate and strengthen the capacity of the various actors such as government departments/agencies, NGOs, CBOs, FBOs and the private sector in the collection and utilization of data to improve on service delivery.

## 6.4 Development indicators and Targets

An indicator is a quantitative or qualitative factor or variable that provides a simple and reliable basis for assessing achievement, change or performance. Indicators are essential component of M&E Plan as they guide in accessing and measuring progress. It is a unit of information measured over time that can help show changes in a specific condition.

##### Table 6.2 Monitoring Matrix – Performance of District Core Indicators

| Goal 1: Build a prosperous country |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Indicators |  | Indicator Definition | Indicator Type | Baseline 2021 | Targets |  |  |  | Disaggregation | Monitoring Frequency | Responsibility |
|  |  |  |  |  | 2022 | 2023 | 2024 | 2025 |  |  |  |
| Programme 1: Economic Development |  |  |  |  |  |  |  |  |  |  |  |
| Sub-Programme 1: Agriculture Services and Management |  |  |  |  |  |  |  |  |  |  |  |
| 1. Total output in agriculture production (Metric Tons) |  | Total quantity of selected crops, livestock and poultry and fisheries produced in the district in a given year | Output |  |  |  |  |  | Maize – 21,248 Rice milled – 13,631 Cassava –184,752 Cocoyam – 110,008 Plantain – 225,788 Cocoa – 266 Cattle – 46,064 Sheep – 46,323 Pig – 7,561 Poultry – 230,275 | Quarterly | MDA/ Cocoa Health and Extension Division (CHED) |
| - Maize |  |  |  | 14,513 | 15,964 | 17,560 | 19,316 | 21,248 |  |  |  |
| - Rice Milled |  |  |  | 9,310 | 10,241 | 11,265 | 12,392 | 13,631 |  |  |  |
| - Cassava |  |  |  | 126,188 | 138,807 | 152,688 | 167,957 | 184,752 |  |  |  |
| - Cocoyam |  |  |  | 75,138 | 82,651 | 90,916 | 100,007 | 110,008 |  |  |  |
| - Plantain |  |  |  | 154,216 | 169,638 | 186,6012 | 205,261 | 225,788 |  |  |  |
| - Cocoa |  |  |  | NA | 200 | 220 | 242 | 266 |  |  |  |
| - Cattle |  |  |  | 31,463 | 34,609 | 38,070 | 41,877 | 46,064 |  |  |  |
| - Sheep |  |  |  | 31,639 | 34,802 | 38,283 | 42,112 | 46,323 |  |  |  |
| - Pig |  |  |  | 5,164 | 5,680 | 6,248 | 6,873 | 7,561 |  |  |  |
| - Poultry |  |  |  | 157,281 | 173,009 | 190,310 | 209,341 | 230,275 |  |  |  |
| 2. Average productivity of selected crops |  | Output per hectare of selected crops (mt/ha) | Output |  |  |  |  |  | Maize – 19 Rice Milled – 23 Cassava – 20 Cocoyam – 12 Plantain – 12 Cocoa - 17 | Quarterly | MDA/ CHED |
| - Maize |  |  |  | 13 | 14 | 16 | 17 | 19 |  |  |  |
| - Rice Milled |  |  |  | 16 | 18 | 19 | 21 | 23 |  |  |  |
| - Cassava |  |  |  | 14 | 15 | 17 | 19 | 20 |  |  |  |
| - Cocoyam |  |  |  | 8 | 9 | 10 | 11 | 12 |  |  |  |
| - Plantain |  |  |  | 7 | 8 | 8 | 9 | 10 |  |  |  |
| vi Cocoa |  |  |  | N/A | 13 | 14 | 16 | 17 |  |  |  |
| 3. Number of new industries established |  | Count of new establishments within the district for purposes of producing goods and services | Output |  |  |  |  |  | Agriculture – 16 Industry – 23 Service - 89 | Quarterly | MPCU |
| i. Agriculture |  |  |  | 11 | 12 | 13 | 15 | 16 |  |  |  |
| ii. Industry |  |  |  | 16 | 18 | 19 | 21 | 23 |  |  |  |
| iii. Service |  |  |  | 61 | 67 | 74 | 81 | 89 |  |  |  |
| 4. Number of jobs created under agriculture |  | Count of formal sector jobs created per annum | Outcome |  |  |  |  |  | Agriculture – 16 Industry – 48 Service - 31 | Quarterly | MDA, BAC, Mining Companies |
| i. Agriculture |  |  |  | 11 | 12 | 13 | 15 | 16 |  |  |  |
| ii. Industry |  |  |  | 33 | 36 | 39 | 43 | 48 |  |  |  |
| iii. Service |  |  |  | 21 | 23 | 25 | 28 | 31 |  |  |  |
| 5. Percentage change in IGF Growth |  | Difference of current year IGF over the previous year expressed as a percentage | Outcome | 710,889.90 | 25% | 35% | 40% | 50% | N/A | Quarterly | Finance/ MPCU |
| Goal 2: Create Opportunities for all Ghanaians |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  | Indicator Definition | Indicator Type | Baseline 2021 | Targets |  |  |  | Disaggregation | Monitoring Frequency | Responsibility |
|  |  |  |  |  | 2022 | 2023 | 2024 | 2025 |  |  |  |
| Programme 2: Social Services Delivery |  |  |  |  |  |  |  |  |  |  |  |
| Sub-Programme I: Education, youth & sport and Library services |  |  |  |  |  |  |  |  |  |  |  |
| 6. Net enrolment ratio |  | Indicator Definition | Indicator Type |  |  |  |  |  |  |  |  |
| KG | Total | Net enrolment ratio is the number of boys and girls of school going age of a particular level of education (KG, Primary /JHS) that are enrolled in that school expressed as a percentage of the total population in that age group | Outcome | 87.7 | 88.4 | 90.2 | 92.4 | 94.4 | KG total : 94.4% Male : 96.4% Female : 94.4% Primary total : 95.6% Male : 96.1% Female : 96.2% JHS total : 96.4% Male : 96.6% Female : 95.7% | Quarterly | GES |
|  | Male |  |  | 89.1 | 90.0 | 92.3 | 94.2 | 96.4 |  |  |  |
|  | Female |  |  | 86.3 | 87.3 | 88.4 | 90.2 | 94.4 |  |  |  |
| Primary | Total |  |  | 89.7 | 90.3 | 92.2 | 94.6 | 95.6 |  |  |  |
|  | Male |  |  | 90.0 | 92.3 | 93.4 | 94.6 | 96.1 |  |  |  |
|  | Female |  |  | 89.4 | 90.4 | 92.5 | 94.7 | 96.2 |  |  |  |
| JHS | Total |  |  | 89.4 | 90.3 | 91.7 | 94.2 | 96.4 |  |  |  |
|  | Male |  |  | 89.6 | 90.4 | 92.3 | 94.4 | 96.6 |  |  |  |
|  | Female |  |  | 89.2 | 90.2 | 92.6 | 94.4 | 95.7 |  |  |  |
| 7. Gender Parity Index |  | Total number of girls at all levels as a ratio of total number of boys at all levels | Outcome |  |  |  |  |  |  |  |  |
| Kindergarten |  |  |  | 1.02 | 1 | 1 | 1 | 1 | Kindergarten : 1 Primary : 1 JHS : 1 SHS -:1 | Quarterly | GES |
| Primary |  |  |  | 1.02 | 1 | 1 | 1 | 1 |  |  |  |
| JHS |  |  |  | 1.05 | 1 | 1 | 1 | 1 |  |  |  |
| SHS |  |  |  | 0.9 | 1 | 1 | 1 | 1 |  |  |  |
| 8. Completion rate |  |  |  |  |  |  |  |  |  |  |  |
| Kindergarten |  |  |  | 89.4 | 92.7 | 94.6 | 96.5 | 98.4 | Kindergarten : 98.4% Primary : 84.5% JHS : 100% SHS : 100% | Quarterly | GES |
| Primary |  | Ratio of the total number of pupils enrolled in the last grade of a given level of education regardless of age expressed as a % of the total pop. of the theoretical entrance age to the last grade of that level of education | Outcome | 66.4 | 70.4 | 75.6 | 80.4 | 84.5 |  |  |  |
| JHS |  |  |  | 92.9 | 94.5 | 96.8 | 98.2 | 100 |  |  |  |
| SHS |  |  |  | 94.1 | 96.6 | 98.3 | 99.4 | 100 |  |  |  |
| 9. Pass Rate |  | Count of final exams takers who passed a particular exam over a total count of final exam takers in that same exams expressed as a percentage | Outcome | N/A | 90% | 95% | 100% | 100% | JHS : 100% SHS : 100% | Annually | GES |
| JHS |  |  |  | N/A | 90% | 95% | 100% | 100% |  |  |  |
| SHS |  |  |  |  |  |  |  |  |  |  |  |
| Sub-Programme II: Public Health Services and Management |  |  |  |  |  |  |  |  |  |  |  |
| 10. Proportion of health facilities that are functional |  | Measure the number of health facilities that are registered and in operation for purposes of providing health care services to the general public expressed as a percentage of completed health facilities | Outcome |  |  |  |  |  |  |  |  |
| i. CHPS Compound |  |  |  | 37 | 40 | 42 | 44 | 45 | CHPS Compound : 37 Clinic : 10 Health Centre : 6 Hospital : 9 | Quarterly | GHS / MPCU |
| ii. Clinic |  |  |  | 5 | 7 | 9 | 10 | 10 |  |  |  |
| iii. Health Centre |  |  |  | 3 | 5 | 6 | 6 | 6 |  |  |  |
| iv. Hospital |  |  |  | 8 | 8 | 9 | 9 | 9 |  |  |  |
| 11. Proportion of population with valid NHIS card |  | The population with valid NHIS card expressed as a percentage of total district population | Outcome |  |  |  |  |  |  |  |  |
| i. Total |  |  |  | 79,542 | 10% | 11% | 12% | 15% | Total : 15% Male : 7% Female : 7.5% Indigents : 0.9% Informal : 5.8% Aged : 0.9% Under 18 yrs. : 6.2% Pregnant women: 1.4% | Quarterly | NHIS |
| Male |  |  |  | 38,180 | 5% | 5.3% | 5.8% | 7% |  |  |  |
| Female |  |  |  | 41,362 | 5% | 5.7% | 6.2% | 7.5% |  |  |  |
| ii. Indigents |  |  |  | 4,987 | 0.3% | 0.4% | 0.5% | 0.9% |  |  |  |
| iii. Informal |  |  |  | 7,000 | 4% | 4.5% | 5% | 5.8% |  |  |  |
| iv. Aged |  |  |  | 7,365 | 0.3% | 0.4% | 0.5% | 0.9% |  |  |  |
| v. Under 18 years |  |  |  | 655 | 5.3% | 5.5% | 5.7% | 6.2% |  |  |  |
| vi. Pregnant women |  |  |  | 8,318 | 0.7% | 0.8% | 0.9% | 1.4% |  |  |  |
| 12. Percentage of communities with access to basic drinking water services |  |  |  |  |  |  |  |  |  |  |  |
| i. District |  | Share of the district population with access to basic drinking water services expressed as a percentage of total district population | Outcome | 90 | 92 | 95 | 97 | 100 | District : 100% Urban : 100% Rural : 94% | Quarterly | Central Administration/Planning Unit |
| ii. Urban |  |  |  | 95 | 97 | 98 | 99 | 100 |  |  |  |
| iii. Rural |  |  |  | 85 | 87 | 88 | 90 | 94 |  |  |  |
| 13. Proportion of population with access to improved sanitation services |  |  |  |  |  |  |  |  |  |  |  |
| i. District |  | Share of population with access to basic sanitation services including ventilated improved pit latrines, flush toilets to sewer systems, septic tanks or pit latrine expressed as a percentage of total population | Outcome | 90 | 93 | 95 | 97 | 99 | District :99% Urban : 100% Rural : 92% | Quarterly | MEHU |
| ii. Urban |  |  |  | 90 | 94 | 96 | 98 | 100 |  |  |  |
| iii. Rural |  |  |  | 85 | 87 | 88 | 90 | 92 |  |  |  |
| 14. Number of Births and Deaths Registered |  |  |  |  |  |  |  |  |  |  |  |
| i. Birth |  | Count of births and deaths registered in the district in a particular year | Output | 423 | 430 | 438 | 446 | 454 | Total Births : 454 Children below 18: 280 Youth between 18-35: 111 Adult above 35: 63 Total Deaths – 0 Children below 18: 0 Youth between 18-35: 0 Adult above 35: 0 | Quarterly | Birth and Death Registry |
| Children below 18 |  |  |  | 261 | 266 | 270 | 275 | 280 |  |  |  |
| Youth between – 18-35 |  |  |  | 103 | 105 | 107 | 109 | 111 |  |  |  |
| Adult - above 35 |  |  |  | 59 | 60 | 61 | 62 | 63 |  |  |  |
| ii. Death |  |  |  | 4 | 0 | 0 | 0 | 0 |  |  |  |
| Children below 18 |  |  |  | 1 | 0 | 0 | 0 | 0 |  |  |  |
| Youth between – 18-35 |  |  |  | 1 | 0 | 0 | 0 | 0 |  |  |  |
| Adult - above 35 |  |  |  | 2 | 0 | 0 | 0 | 0 |  |  |  |
| 15. Total number of recorded cases of child trafficking and abuse |  |  |  |  |  |  |  |  |  |  |  |
| Child Trafficking |  | Count of recorded cases of child trafficking and child abuse cases in the district | Output | N/A | 0 | 0 | 0 | 0 | Child Trafficking : 0 Male : 0 Female : 0 Child Abuse : 4 Male : 0 Female : 1 | Quarterly | SWCD / GPS |
| - Male |  |  |  | N/A | 0 | 0 | 0 | 0 |  |  |  |
| - Female |  |  |  | N/A | 0 | 0 | 0 | 0 |  |  |  |
| Child Abuse |  |  |  | 12 | 10 | 8 | 6 | 4 |  |  |  |
| - Male |  |  |  | 3 | 2 | 1 | 0 | 0 |  |  |  |
| - Female |  |  |  | 9 | 7 | 5 | 3 | 1 |  |  |  |
| 16. Maternal mortality ratio (institutional |  | Maternal deaths recorded per 100,000 live births in the district | Outcome | 73.4 | 70 | 68 | 65 | 60 | N/A | Quarterly | GHS |
| 17. Malaria case fatality (institutional) |  |  |  |  |  |  |  |  |  |  |  |
| i. District |  | Total malaria deaths expressed as a percentage of total malaria admissions in health facilities | Outcome | 3.1 | 2.8 | 2.5 | 2.2 | 2.0 | District : 2.0 Under 5 – 1.0 Women between 15-49 years : 0.2 | Quarterly | GHS |
| ii. Under five (5) years |  |  |  | 2.5 | 2.2 | 2.0 | 1.6 | 1.0 |  |  |  |
| iii. Women between 15-49 years |  |  |  | 0.6 | 0.5 | 0.4 | 0.3 | 0.2 |  |  |  |
| 18. Prevalence of Malnutrition |  |  |  |  |  |  |  |  |  |  |  |
| i. Wasting |  | Proportion of children 0-59 months whose height-for-age, weight-for-age, weight-for-height is less than two standard deviations from the median of the reference population group | Output | N/A | 5% | 4% | 3% | 2% | Wasting : 2% Underweight : 3% Stunting : 2% Overweight – 2% | Quarterly | GHS |
| ii. Underweight |  |  |  | N/A | 5% | 4% | 3% | 2% |  |  |  |
| iii. Stunting |  |  |  | N/A | 5% | 4% | 3% | 2% |  |  |  |
| iv. Overweight |  |  |  | N/A | 5% | 4% | 3% | 2% |  |  |  |
| Goal 3: Safeguard the Natural Environment and ensure a Resilient, Built Environment |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  | Indicator Definition | Indicator Type | Baseline 2021 | Targets |  |  |  | Disaggregation | Monitoring Frequency | Responsibility |
|  |  |  |  |  | 2022 | 2023 | 2024 | 2025 |  |  |  |
| Programme I: Infrastructure Delivery and Management |  |  |  |  |  |  |  |  |  |  |  |
| Sub-Programme: Urban Roads and Transport Services |  |  |  |  |  |  |  |  |  |  |  |
| 19. Percentage of road network in good condition |  |  |  |  |  |  |  |  |  |  |  |
| i. Total |  | The total km of classified road network in good condition expressed as percentage of total road network | Outcome | 81% | 85% | 87% | 90% | 95% | Total : 95% Urban :98% Feeder : 80% | Quarterly | MWE |
| ii. Urban |  |  |  | 92% | 95% | 96% | 97% | 98% |  |  |  |
| iii. Feeder |  |  |  | 67% | 70% | 72% | 75% | 80% |  |  |  |
| 20. Percentage of communities covered by electricity |  |  |  |  |  |  |  |  |  |  |  |
| i. District |  | The number of communities in the district connected to the national grid divided by total number of communities in the district expressed as a percentage | Outcome | 94% | 95% | 95% | 100% | 100% | District : 100% Rural : 95% Urban : 100% | Quarterly | MWE / ECG |
| ii. Rural |  |  |  | 82% | 85% | 87% | 90% | 95% |  |  |  |
| iii. Urban |  |  |  | 96% | 92% | 95% | 97% | 100% |  |  |  |
| GOAL 4: Maintain a Stable, United and Safe Society |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  | Indicator Definition | Indicator Type | Baseline 2021 | Targets |  |  |  | Disaggregation | Monitoring Frequency | Responsibility |
|  |  |  |  |  | 2022 | 2023 | 2024 | 2025 |  |  |  |
| PROGRAMME: Management and Administration |  |  |  |  |  |  |  |  |  |  |  |
| Sub-Programme I: Legislative Oversight |  |  |  |  |  |  |  |  |  |  |  |
| 21. Reported cases of crime |  |  |  |  |  |  |  |  |  |  |  |
| i. Rape |  | Count of reported cases of major crimes including rape, armed robbery, defilement and murder recorded by Ghana police in a given year | Output | 3 | 1 | 0 | 0 | 0 | Rape : 0 Armed Robbery : 0 Defilement : 1 Murder : 0 | Quarterly | GPS |
| ii. Armed Robbery |  |  |  | 5 | 3 | 2 | 1 | 0 |  |  |  |
| iii. Defilement |  |  |  | 9 | 7 | 5 | 3 | 1 |  |  |  |
| iv. Murder |  |  |  | 1 | 0 | 0 | 0 | 0 |  |  |  |
| GOAL 5: Mainstream emergency planning and preparedness into Ghana’s development planning agenda at all levels to respond to potential internal and external threats (including COVID-19) |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  | Indicator Definition | Indicator Type | Baseline 2021 | Targets |  |  |  | Disaggregation | Monitoring Frequency | Responsibility |
|  |  |  |  |  | 2022 | 2023 | 2024 | 2025 |  |  |  |
| PROGRAMME: Environmental Management |  |  |  |  |  |  |  |  |  |  |  |
| SUB-PROGRAMME I: Disaster Prevention and Management |  |  |  |  |  |  |  |  |  |  |  |
| 22. Number of communities affected by disaster |  |  |  |  |  |  |  |  |  |  |  |
| i. Urban |  | Count of communities in a district recording disaster cases including floods, bushfires etc | Output | 1 | 1 | 0 | 0 | 0 | Urban : 0 Rural : 2 | Quarterly | NADMO |
| ii. Rural |  |  |  | 13 | 10 | 7 | 5 | 2 |  |  |  |
| 23. Proportion of population who have tested positive for covid-19 |  |  |  |  |  |  |  |  |  |  |  |
| i. District |  | Count of covid-19 cases confirmed as a percentage of district population | Outcome | N/A | 0 | 0 | 0 | 0 | District : 0 Male : 0 Female : 0 |  |  |
| ii. Male |  |  |  | N/A | 0 | 0 | 0 | 0 |  |  |  |
| iii. Female |  |  |  | N/A | 0 | 0 | 0 | 0 |  |  |  |
| GOAL 6: Improve delivery of development outcomes at all levels |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  | Indicator Definition | Indicator Type | Baseline 2021 | Targets |  |  |  | Disaggregation | Monitoring Frequency | Responsibility |
|  |  |  |  |  | 2022 | 2023 | 2024 | 2025 |  |  |  |
| PROGRAMME: Management and Administration |  |  |  |  |  |  |  |  |  |  |  |
| Sub-Programme I: Planning, Budgeting, Monitoring and Evaluation |  |  |  |  |  |  |  |  |  |  |  |
| 24. Percentage of Annual Action Plan implemented |  | Count of activities implemented in the district divided by the total number of planned activities in a given year expressed as a percentage | Outcome | 92.6% | 94% | 95% | 95% | 97% | N/A | Quarterly | MPCU |

Source: MPCU, 2021

##### Table 6.3 Monitoring Matrix – Performance of District Specific Indicators

| GOAL 1: Promote fiscal decentralization process and increase economic growth and job creation |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Indicators | Indicator Definition |  | Indicator Type | Baseline 2021 | Targets |  |  |  | Disaggregation | Monitoring Frequency | Responsibility |
|  |  |  |  |  | 2022 | 2023 | 2024 | 2025 |  |  |  |
| PROGRAMME : Economic Development Sub-Programme I: Trade, Tourism and Industrial Development |  |  |  |  |  |  |  |  |  |  |  |
| 1. No. of People provided with start-up capital |  | Total number of people provided start up kids | Output | N/A | 10 | 15 | 17 | 20 | Male: 10 Female:10 | Quarterly | BAC |
| 2. No. of Business development trainings Organized |  | Count business trained Programmes organized | Output | N/A | 5 | 7 | 8 | 10 | N/A | Quarterly | BAC |
| Sub-Programme II : Agricultural Services and Management |  |  |  |  |  |  |  |  |  |  |  |
| 3. Number of farmers who received extension service |  | Count of extension services rendered | Output | 3,160 | 3,300 | 3,500 | 3,700 | 4,000 | Males: 2,860 Females : 1,140 | Quarterly | MDA |
| 4. Percentage of arable land under cultivation |  | Number of acreage cultivated in a given year | Outcome | 75% | 78% | 80% | 82% | 85% | N/A | Quarterly | MDA |
| GOAL 2: Enhance and sustain social development interventions |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  | Indicator Definition | Indicator Type | Baseline 2021 | Targets |  |  |  | Disaggregation | Monitoring Frequency | Responsibility |
|  |  |  |  |  | 2022 | 2023 | 2024 | 2025 |  |  |  |
| PROGRAMME: Social Services Delivery Sub-Programme I: Education, youth & sports and Library services |  |  |  |  |  |  |  |  |  |  |  |
| 5. Number of educational facilities that are easily accessible to children PWDS |  | Count of schools that are disability friendly | Output | N/A | 5 | 6 | 7 | 8 | N/A | Quarterly | GES |
| Sub-Programme II: Public Health Services and management |  |  |  |  |  |  |  |  |  |  |  |
| 6. Under-five (5) mortality ratio |  | Number of deaths of under 5 years expressed as a percentage of district population of under 5 in a given year | Outcome | N/A | 0.3% | 0.2% | 0.1% | 0% | Male : 0% Female : 0% | Quarterly | GHS |
| 7. Proportion of births attended by skilled health personnel |  | Number of births attended by skilled staff expressed as a percentage of district births in a given year | Outcome | N/A | 45% | 50% | 55% | 60% | Male: 90% Female: 95% | Quarterly | GHS |
| 8. Infants mortality ratio |  | Number of infants deaths expressed as a percentage of district infants population | Outcome | N/A | 0.4% | 0.3% | 0.2% | 0.1% | Male : 0.1% Female : 0.1% | Quarterly | GHS |
| 9. Stillbirth Rate |  | Number of still birth expressed as a percentage of district population | Outcome | N/A | 0.2% | 0.2% | 0.1% | 0.01% | Male : 0.01% Female : 0.01% | Quarterly | GHS |
| 10. Proportion of children immunized (Penta 3) |  | Number of children immunized expressed as a percentage to district population of children | Outcome | N/A | 65% | 70% | 80% | 90% | Male : 45% Female : 45% | Quarterly | GHS |
| 11. Prevalence of Anaemia |  | Count of children and women who are anaemic in the district | Outcome | N/A | 10% | 8% | 6% | 5% | -Children under 5 ; 3% -Women of reproductive age (15-49 years) : 2% | Quarterly | GHS |
| 12. Exclusive breastfeeding rate |  | Number of exclusive breastfeeding children expressed as district population of children | Outcome | N/A | 80% | 85% | 90% | 95% | Male: 90% Female: 95% | Quarterly | GHS |
| 13. Proportion of severely malnourished children supported by complementary feeding centres |  | Number of severely malnourished children expressed as a percentage of district population of children | Outcome | N/A | 10% | 8% | 6% | 5% | Male : 2% Female : 3% | Quarterly | GHS |
| SUB-PROGRAMME III: Social Welfare And Community Services |  |  |  |  |  |  |  |  |  |  |  |
| 14. Proportion of children (5-17) engaged in hazardous work |  | Number of children engaged in hazardous work expressed as a percentage of district population of children | Outcome | N/A | 15% | 10% | 6% | 4% | Male : 2% Female : 2% | Quarterly | SWCD |
| 15. Percentage of children engaged in child labour |  | Number of children engaged in child labour expressed as a percentage of district population of children | Outcome | N/A | 10% | 8% | 6% | 4% | Male : 2% Female : 2% | Quarterly | SWCD |
| 16. Number of children placed in alternative family-based care |  | Count of children in alternative family-based care in the district | Output | N/A | 25 | 15 | 10 | 5 | Male : 2 Female : 3 | Quarterly | SWCD |
| 17. Number of residential homes for children closed down |  | Count of residential homes for children closed down in the district | Output | N/A | 5 | 4 | 3 | 2 | N/A | Quarterly | SWCD |
| 18. Proportion of child labourers rescued or withdrawn and supported |  | Number of rescued child labours expressed as a percentage of district population of children | Outcome | N/A | 10 | 12 | 15 | 20 | Males : 13 Female : 7 | Quarterly | SWCD |
| 19. Percentage of children with disability accessing the disability fund |  | Number of children accessing disability fund expressed as a percentage of district population of children | Outcome | N/A | 5% | 7% | 10% | 15% | Males : 10% Female : 5% | Quarterly | SWCD |
| 20. Proportion of women aged 20-24 years who were married or in a union before age 15 |  | Number of women aged 20-24 who married before age 15 expressed as a percentage to district population of women aged 20-24 | Outcome | N/A | 5% | 6% | 7% | 8% | N/A | Quarterly | SWCD |
| GOAL 3: Protect the natural environment and promote sustainable human settlement |  |  |  |  |  |  |  |  |  |  |  |
| PROGRAMME: Environmental Management SUB-PROGRAMME I: Natural Resource Conservation And Management |  |  |  |  |  |  |  |  |  |  |  |
| 21. Hectors of degraded forest rehabilitated |  | Portions of rehabilitated forest | Outcome | 34 | 40 | 45 | 50 | 55 | N/A | Quarterly | FC |
| 22. Number of sensitizations of the general public on management and protection of forests |  | Hectors of forest areas protected | Outcome | 46 | 50 | 56 | 60 | 65 | N/A | Quarterly | FC |
| 23. Embark on enrichment tree planting Programme |  | Count of trees planted | Output | 20,000 | 25,000 | 30,000 | 35,000 | 40,000 | N/A | Quarterly | FC/BABMA/ |
| Sub-Programme II: Disaster Prevention And Management |  |  |  |  |  |  |  |  |  |  |  |
| 24. Number of communities affected by disasters |  |  |  |  |  |  |  |  |  |  |  |
| i. Bush/domestic fires |  | Count of disasters in communities | Output | 12 | 0 | 0 | 0 | 0 | Bush/domestic fires : 0 Floods : 0 Rainstorm : 0 | Quarterly | NADMO |
| ii. Floods |  |  |  | 1 | 0 | 0 | 0 | 0 |  |  |  |
| iii. Rainstorm |  |  |  | 3 | 0 | 0 | 0 | 0 |  |  |  |
| PROGRAMME : Infrastructure development and Management Sub-Programme I: Spatial Planning |  |  |  |  |  |  |  |  |  |  |  |
| 25. Proportion of Building permits applications approved |  | Number of building permits issued expressed as a percentage of total applications received | Outcome | 55 | 70% | 80% | 90% | 100% | N/A | Quarterly | PPD |
| 26. Number of communities with local plans |  | Count of communities with local plans in the district | Output | 6 | 7 | 8 | 9 | 10 | N/A | Quarterly | PPD |
| GOAL 4: Promote Administrative and Political Decentralization |  |  |  |  |  |  |  |  |  |  |  |
| PROGRAMME: Management and Administration Sub-Programme I : General Administration |  |  |  |  |  |  |  |  |  |  |  |
| 27. No. of Public hearings organized |  | Count of public hearing organized | Output | 2 | 4 | 4 | 4 | 4 | - | Quarterly | CA |
| 28. Number of MCE’s visit to communities |  | Count of communities visited by MCE | Output | 60 | 70 | 80 | 90 | 100 | - | Quarterly | CA |
| 29. No. of Town hall meetings organized |  | Count of Town hall meetings organized | Output | 4 | 4 | 4 | 4 | 4 | - | Quarterly | CA |
| GOAL 5: Mainstream emergency response activities into District development planning |  |  |  |  |  |  |  |  |  |  |  |
| PROGRAMME: Sub-Programme I: |  |  |  |  |  |  |  |  |  |  |  |
| 30. No. of sensitizations programmes organized on covid-19 and other related pandemics |  | Count of sensitizations of covid-19 | Output | 13 | 15 | 15 | 15 | 15 | N/A | Quarterly | GHS, CA |
| 31. Percentage of population affected by covid-19 and other pandemics |  | Number of people infected by covid -19 expressed as a percentage to the total population of the district | Outcome | 0.12 | 0.1 | 0.1 | 0 | 0 | Male: 0% Female: 0% |  |  |
| GOAL 6: Improve percentage implementation of development programmes |  |  |  |  |  |  |  |  |  |  |  |
| PROGRAMME: Management and Administration Sub-Programme: Planning, Budgeting, Monitoring and Evaluation |  |  |  |  |  |  |  |  |  |  |  |
| 32. No. of Participatory M & E's organized |  | Count of M and E's organized | Output | 4 | 4 | 4 | 4 | 4 | - | Quarterly | MPCU |
| 33. No. of budget hearing meetings organized |  | Count of number meeting organized | Output | 2 | 4 | 4 | 4 | 4 | N/A | Quarterly | MBA |
| 34. No. of fees fixing meeting organized |  | Count of number meeting organized | Output | 1 | 4 | 4 | 4 | 4 | N/A | Quarterly | MBA |
| 35. Percentage of M&E budget released |  | Amount release for M&E expressed as a percentage of total amount budgeted for M&E in a year | Outcome | 86% | 90% | 92% | 95% | 100% | N/A | Quarterly | Finance |

Source: MPCU, 2021

## 6.5 Evaluation Arrangements

Evaluation is the systematic and objective assessment of an on-going or completed project, programme or policy, its design, implementation and results in relation to specified evaluation criteria (OECD, 2002). The principal aim of the planned evaluation is to improve decision-making, resource allocation and accountability. The criteria for the evaluation on planned projects and programme will be five cardinal points of; relevance, effectiveness, efficiency, impact and sustainability. These five criteria will provide a normative framework in determining the merit or worth of any planned intervention for 2022-2025 MTDP and thus also serve as basis upon which evaluation judgements will be made.

Four main types of evaluation would be conducted which are:-

1. Ex-ante evaluations would be conducted before the start of any Programme and Project to determine the feasibility of the intervention by using Feasibility Studies, Technical Appraisal among others.

2. The Municipal Planning Coordinating Unit would be conducting quarterly and mid-term evaluation (half-way – 2023) into the implementation of all planned intervention to weigh their performance and first output of implementation, as well as proposals for possible modifications where necessary.

3. Terminal evaluation would also be carried out at the completion of an intervention to assess achievement(s) made under the implementation of the intervention.

4. Finally, some years after the implementation of an intervention, Post evaluation would be conducted to assess the impacts on the citizenry. The evaluation framework or matrix is presented in table 39. The matrix is a table of the evaluation work plan.

## 6.6. Participatory Monitoring and Evaluation Arrangements

Participatory Monitoring and Evaluation could be explained as a process where primary stakeholders actively participate in tracking progress towards the achievement of self-selected or jointly agreed results to draw actionable conclusions. There shall be quarterly meeting to evaluate the performance of the MTDP. The monitoring team shall also conduct periodic project site inspection with contractors, consultants, beneficiary communities and other stakeholders. The monitoring report would be disseminated to the public and other stakeholders at workshops and fora. Special interest will be focused on the view and contribution of Assembly members, the traditional authorities in the municipal, NGOs/CBOs using focus group discussions and Community Score Cards.

6.6.1 Need for PM&E

It is essential that, the communities in the municipality be actively involved in the decision making that directly affects their lives. In view of this, the MPCU will adopt a multi-stakeholder participatory approach to monitoring and evaluation of projects earmarked for implementation. These would be essential to the development of the municipal based on the following factors;

- Ensures effective implementation of the activities and Programmes in the MTDP

- Offers a sense of ownership of Programmes and activities from the community members

- Enhances community participation and boost the self-confidence of community members.

6.6.2 Methods to be used

The Participatory Rural Appraisal approach will be adopted to enhance the Participatory Monitoring and Evaluation. It is important that, project managers, MPCU members collaborate with the local community members in order to ascertain the required information for the monitoring and evaluation purposes of the MTDP.

Information for monitoring and evaluation of activities in the various communities will be acquired through a participatory approach. The following methods or steps will be adopted to enhance the participation of community members in the monitoring and evaluation of activities.

- Empower the various unit committees in the various electoral areas to actively participate in the process

- Using of maps for information gathering

- Transect Walk to identify and gather information

- Multi-stakeholder  Analysis

These methods would promote the compilation of information and improve monitoring and evaluation activities of projects and Programmes. A summary of evaluation framework for data collection based on selected criteria for conducting project evaluations for the 2022-2025 MTDP is outlined in table 6.4

##### Table 6.4 Summary of Evaluation Matrix

| Evaluation Criteria | Evaluation Questions |  | Data Needed | Data Sources | Data collection Methods |
| --- | --- | --- | --- | --- | --- |
|  | Main Questions | Sub-Questions |  |  |  |
| Relevance | Are the goal and objectives of the projects / Programme relevant? | 1. Is the activity/project objective in line with beneficiary requirements? 2. Does the intervention comply with development policy and planning of the government? 3. Does the strategies outlined or implemented corresponds with cross-cutting and vulnerability issues such as gender and HIV/AIDs among others | Project /Programme impact assessment reports | Project beneficiaries, MPCU reports and community members | Questionnaire administration, interview guide, project closure meeting, project site reports |
| Efficiency | Was the project /Programme completed on time? | 1. Was the project implemented within the scheduled timeframe 2. Was the project implemented within the specified budget and costs? | Project implementation plans, Quarterly Progress Reports | Project consultants Reports, Contractors, MPCU minutes and reports | Questionnaire administration and Interview guides, Discussions with MPCU members, cost-benefits analysis |
| Effectiveness | Has the project/ Programme well implemented? | 1. To what extent have the objectives of the interventions been achieved in accordance with targets? 2. To what extent is the target group reached? 3. To what extent will the objectives of the intervention be achieved? 4. To extend has vulnerability and marginalized activities implemented | Projects progress reports | Project managers, Contractors, Planning officer, Engineers and Project Beneficiaries | Questionnaire administration and Interview guides, Project impacts Assessment |
| Impacts | What benefits have you received from the implementation of the project / Programme | 1. What has happened as a result of the Programme or project/activities in your community? 2. What real difference has the activity made to the beneficiary communities 3. How many people have been affected including the marginalized and excluded | Social Impact Assessment reports, Beneficiary impact assessment reports | Project consultants reports from Contractors, MPCU, Beneficiary communities | Questionnaire administration and Interview guides, community engagements, Economic and impacts Assessments reports |
| Sustainability | What is the lifespan of the project? | 1. To what extent will activities, results and effects be expected to continue after implementation 2. To what extent does the interventions reflected on the lives of the people taking into consideration economic and social factors 3. How long will the project last taking into consideration technical and social factors | Impact Assessment reports, Annual Progress Reports | Project consultants Contractors, MPCU Beneficiary communities | Questionnaire administration, Interview guides, community fora, Economic Environmental Impacts Assessments, |

Source: MPCU, 2021

# CHAPTER SEVEN

# COMMUNICATION STRATEGY

## 7.1 Introduction

This chapter encapsulate the communication strategy to be implemented by the Assembly as reporting/dissemination of the right information on the status of implementation of the formulated development programmes, projects and activities to stakeholders at the local, regional and national levels respectively at the right time plays crucial role in the successful execution of the 2022-2025 DMTDP.

This is because the various stakeholders can only play their roles and responsibilities well towards the implementation of the plan when they are adequately informed. Dissemination of these reports with stakeholders would improve accountability of the Municipal Assembly contributing to the enhancement of local governance and decentralisation in Ghana. It will boost stakeholder commitment to support development interventions that emerge from the Monitoring and Evaluation exercise

## 7.2 Strategies

The strategies the Bibiani-Anhwiaso-Bekwai Municipality has adopted to communicate or disseminate information on the status of implementation of the plan within the plan period 2022-2025 include:

Quarterly, mid-term and end of year M&E exercises will be conducted after which Quarterly, mid –year and annual progress reports will be compiled on the status of implementation on the development programmes/projects whiles both hard and soft copies of the main plan will be distributed to NDPC, RCC, Development Partners and other MDAs.

At the local level, copies of the progress reports will be distributed to P.M, MA sub-committees especially F&A, Works and Economic Planning sub-committees, local NGOs, Decentralized Departments etc. and copies kept at the MPCU Secretariat for reference. At the regional and national levels, copies of the reports will be sent to RCC, MLGRD, and NDPC.

Quarterly, mid-year and annual review meetings will also be held to brief DPCU members and other stakeholders and the progress reports. General dialogue will be promoted and feedbacks on performance of the district will be received through mid-year composite and end of year reviews meetings, reports from area councils, unit committees, opinion leaders, public complaint unit of the Assembly, General Assembly meetings and the Development Communication Committee that will be formed.

However, a more detailed communication strategy that provides a more visual and easier understanding of how the information on the implementation of the plan will be sent to stockholders and feedback mechanisms has been provided in Table 7.1. The matrix also shows how the strategy can be used to mobilise funds for the district.

Furthermore, the strategy is meant to showcase the results of the programmes and projects in the plan which are supposed to transform the living conditions of the people. By disseminating the results or impacts of the plan to relevant stakeholders and providing feedbacks, they would be encouraged to provide the necessary resources for the district to implement the plan. This will help the vigorous resource mobilisation drive set out in the revenue mobilisation action plan in Table 6.2.

##### Table 7.1 2022 – 2025 DMTDP Communication Strategy Matrix

| S/NO | STRATEGY | INDICATOR | FREQUENCY | STAKEHOLDER | ROLE | LEVEL/ IMPROVEMENT |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Conduct M&E exercises on the implementation of the development programmes/ projects in the plan | M&E exercises conducted regularly | - Quarterly - Half-yearly - Annually | MPCU, CSOs, NDPC, MLGRD, WRCC, MP, Local Communities, MoF, Donors, District Sub-Structures/ Assembly Members | - Give Policy direction - Give M&E guideline - Provide feedback on M&E results - Participate in M&E exercises - Release of funds - Coordination and harmonization - Facilitate M&E activities | - Provision of logistics for M&E activities - Field visits for M&E exercises - Capacity building on M&E - Awareness creation - Participatory M&E - M&E data collection |
| 2 | Prepare progress reports | Progress reports timely prepared | - Quarterly - Half-yearly - Annually | MPCU, NGOs, NDPC, MLGRD, WRCC, Donors, District sub-structures | - Data collection - Provide Guidelines - Preparation of M&E reports - Provision of logistics | - Data collection - Provision of resources - M &E reports writing |
| 3 | Conduct review meetings on DMTDP | Review meetings held regularly and timely | - Quarterly - Half-yearly - Annually - Others | MPCU, CSOs, NDPC, MLGRD, WRCC, MP, Local Communities, MoF, Donors, District Sub-Structures, TAs, Private Sector, Assembly members, other departments, etc | - Provision of logistics - Technical assistance - Participation of review meetings | - M&E seminars and meetings - Organization of review meetings - Provision of logistics for review meetings - Funding of review meetings |
| 4 | Submission of progress reports | Progress reports submitted timely and regularly | - Quarterly - Half-yearly - Annually - Others | MPCU, DA, NDPC, MLGRD, WRCC, CSOs, Donors, District Sub-Structures, Other Departments, subcommittees, RPCU | - Submission of M&E results and reports - M&E results dissemination - M&E seminars - M&E results publication | - M&E seminars and meetings - Organization of review meetings - Provision of logistics for review meetings - Funding of review meetings |
| 5 | Create awareness on the roles and expectations of stakeholders in the plan implementation | Adequate awareness created among stakeholders | Throughout the plan period | MPCU, DA, NDPC, MLGRD, WRCC, CSOs, Donors, District Sub-Structures, Other departments, sub-committees, Local communities, media, Political parties, etc. | - Organize public education/ seminars - Organize community durbars - Organize public hearings - Stakeholder consultations - Organize general assembly meetings | - Organize public education/ seminars - Organize community durbars - Organize public hearings - Stakeholder consultations - Organize general Assembly meetings |
| 6 | Promote dialogue and feedback mechanisms | dialogue and feedback mechanisms promoted/ created | Throughout the plan period | MPCU, NGOs, NDPC, MLGRD, WRCC, Donors, District Sub-Structures, Media, Other MDAs, DA, TA, Local Communities, etc. | - Composite review meetings - Dissemination of reports - Provision of feedback mechanisms | - Dialogue sessions - Feedback process |

All the strategies outlined in the matrix are really geared towards identifying the relevant stakeholders, their roles/ responsibilities, the various level of involvement in the various activities relating the communication strategy set out for the 2022– 2025 DMTDP for the BABMA

Furthermore, the strategy is meant to showcase the results of the programmes and projects in the plan which are supposed to transform the living conditions of the people. By disseminating the results or impacts of the plan to relevant stakeholders and providing feedbacks, they would be encouraged to provide the necessary resources for the district to implement the plan. This will help the vigorous resource mobilisation drive set out in the revenue mobilisation action plan in Table 7.1.

## 7.3 Approaches/Channels for Communication

The methodologies outlined below will focus on group and individual approaches or organizational through interaction, information dissemination, training, management development programmes, team building and survey feedback techniques. The approaches to be used to achieve the above-objectives are:

- Newspapers/ Newsletter Publications

- Local Dailies

- Local Government Information Digest

- Broadcast media, TV and radio, public service announcements and phone-ins;

- Workshops/Seminars

- Focus Group Discussions

- Consultative Meetings

- Town Hall Meetings

- Meet the press series

- Briefing of RCCs and General Assembly during meetings

- District Website Updating (www.babma.gov.gh)

The Communication channels envisaged are:

7.3.1 The use of Discussion Programmes

- Electronic Media: Radio (selected FM stations in the Municipality)

- Print Media: Selected Newspaper for publication of Articles

- Using Information Services Division

7.3.2 The Use of Interpreters   and sign language

As much as possible sign language   professionals and interpreters would be used at public for such as town Hall meetings, meet the press series etc to take care of the vulnerable groups such as the deaf and local language interpreter.

# LIST OF APPENDICES

## Appendix I – Report on Final Public Hearing

REPORT ON PUBLIC HEARING HELD ON THURSDAY, 14TH OCTOBER 2021 AT THE BIBIANI METHODIST CHURCH

1.0 INTRODUCTION

In accordance with section 88 of the local governance act, 2016 act 936, which requires MMDAS to conduct a public hearing on the MTDP, the Bibiani Anhwiaso Bekwai Municipal Assembly carried out a public hearing at the Bibiani Methodist Church on the 14th October 2021. 'The program started at 10:00 with an opening prayer by Hon. Mathew Obiri Assembly member for Subri Electoral Area

2.0 INTRODUCTION OF DIGNITARIES

The dignitaries present were introduced by Evans Opoku Afriyie, among the dignitaries were;

Hon. Alfred Amoah - Municipal Chief Executive

Mr. S.M Abdul-Rahman - Municipal Coordinating Director.

Nana Bonya Atipimhene of Sefwi Bekwai Traditional Area

Nana Agyarko Komeh II -Chief of Chirano

Nana Asa Ababio - Chief of Sorano

SOME IDENTIFIABLE GROUPS PRESENT WERE;

Assembly Members, Area Council Members, Unit Committee Members, Members of Sub Committees of the Assembly, Representative of Political Parties, Heads of Decentralized Departments. Representatives of NGOs, FBOs, And CBOs, Women's Group's Leaders, Youth Groups Leaders, Leaders Of Political Parties, Traditional Authorities, Leaders Of Various Associations (Hair Dressers, Dress Makers, Mechanics, Traders etc.), DPCU Members, PWDs representative and opinion leaders from the various Communities.

3.0 CHAIRMAN OPENING REMARKS

The Chairman for the occasion Nana Ogyeahohuo Gyebi who doubles as the President of National House of Chief was represented by Nana Bonya III the Atipimhene of Sefwi Bekwai. In his opening remarks he thanked participants for their presence and encouraged them to pay attention and listen to the presentation and also tasked participant to ask relevant questions and make contribution to help make a good plan for the Bibiani Anhwiaso Bekwai Municipality. He further expressed joy about participatory planning approach adopted by the municipal assembly in executing its mandate.

4.0 WELCOME ADRRESS BY HON. ALFRED AMOAH THE MUNICIPAL CHIEF EXECUTIVE,

The MCE welcomed members for coming and thanked them for honouring the invitation by the Municipal Assembly. He spoke on participatory planning and enhancing the bottom up approach to planning as the new trend of participatory planning. He explained that unlike before where authorities could plan for the people, now the people are supposed to take a lead role in the planning process and that is exactly why all these stakeholders have been invited to participate in the preparation of the MTDP 2022-2025. He made an appeal to the participants and Nananom to ensure that the most pressing issues and challenges facing them in their communities are present in the plan. Finally he drew members' attention to the fact that the deadly Covid-19 pandemic is still with us and we should adhere to the protocols to help curb the disease.

5.0 THE PURPOSE OF THE GATHERING BY MR. S.M ABDUL-RAHMAN

MUNICIPAL COORDINATING DIRECTOR

The Municipal Coordinating Director took members through the purpose of the gathering and how important this gathering is to the development of the Municipality within the next 4 years.

He stated this is a follow up after the community needs assessment and a platform for

Stakeholders to make inputs to the plan. He congratulated the Municipal Planning Officer and his team for the good work done so far.

6.0 PRESENTATION ON STATUS OF THE PREPARATION OF THE 2022-2025 DMTDP

Mr. Aggrey Louis, the Municipal Planning Officer took the members present through the needs assessment by outlining all the prioritized needs of the communities within the Bibiani Anhwiaso Bekwai municipal Assembly. Among the issues noted were;

- Construction of Educational infrastructure

- Construction of Health infrastructure

- Improving Roads/Drainage Systems

- Provision of Refuse Containers

7.0 INPUTS, CONCERNS, SUGGESIONS, QUESTIONS FROM THE GENERAL PUBLIC.

After then detailed presentation by Mr. Aggrey Louis the municipal planning officer, ample time of about 2 hours was allowed for questioning, clarifications and inputs from the members present. The following were the questions asked and suggestions made with their corresponding response from the Municipal Assembly.

1. Mr. Robert Osei Kofi who is the community liaison officer for the MENSIN Gold Bibiani Limited entreated the Assembly to use more of pictorial representations in the presentation to give more understanding of the processes and the projects spoken about. Secondly he spoke on the rate of lawlessness in the principal streets of Bibiani and entreated city authorities to look at that with all the seriousness it requires. He stated the activities of tricycles and trading activities on the principal streets as examples. Lastly he recommended for a new labour office for the labour office since the current state of the labour office is below standard.

2. Miss. Hannah Aidoo a representative of the PWD's thanked the MCE and the Assembly for the construction of an office for the PWD's. She further asked about when the building is going to be officially handed over to the PWD's. She also suggested that

refresher causes and educational seminars to be periodically organized for teachers within the Bibiani Anhwiaso Bekwai Municipality to help refresh their teaching skills.

3. Hon. Adam Smith the Assembly Member for the Hwenampori electoral area stated that there's a school building they have presented to the Assembly previously which needs attention so he asked the MPO to factor it as critical and urgent the school facility is need of the community. Also he expressed concerns about the poor state of the office of the Ghana water company. He further suggested to the Assembly to consider constructing a new office for the Ghana water company or renovating the office to a befitting standard.

4. Hon. Collins Berchie the Assembly man for Bassengele suggested that since the communities are the final beneficiaries of development projects, the Assemblymen should be privy to certain contract details to enable them to check and also track the work of the contractors. He expressed that Assemblymen are to have oversight responsibilities over projects within their electoral areas but without the contract details it becomes difficult to comment on the work of the contractors also the contractor don't give them the necessary hearing since they (the Assemblymen) are not properly introduced to the contractors as stakeholders of the project. Secondly he entreated the Assembly to make sure projects started are completed before new once are started to make sure the scarce financial resources are no spreader too wide to take projects to various stages without completion.

He stated that there are two toilet facilities within his community at various stages of completion which have all stalled. Lastly he asked when the Fahiakobo School is scheduled for opening.

5.  Hon. Samuel Kwagyire the Assembly member for Bibiani Newtown. Asked about the plans in place to support the traders in the municipality financially. Also he stated that the footbridge behind the municipal assembly has broken and needed critical attention. He also asked about when the GNPC funded toilet facility will be completed and be in use. Again the Hon. Member asked about the water shortage that has been hitting the municipal capital in recent times.

6. The hon. Assembly member for Adupri stated that the building been used as a CHPS compound has issues which they have to relocate so he pleaded with the Assembly to put things in place to build a CHPS compound at Adupri to help them solve the pertainingg issues.

7. A member present raised issue with growing nature of young/ underage ridding tricycles in town and the number of tricycle related accidents in town should be checked also

8. The chairman of the Sefwi Bekwai pragyia association recommended that there should be an association of pragyia riders which should be compulsory for all. This will help hold their leadership responsible and help keep track of all the riders and their activities.

These among others were the issues raised by the people who were present at the public hearing after which the opportunity was given to the traditional authorities from the three traditional councils to also present the issues and their observations with respect to their traditional areas.

The chief of Chirano Nana Agyarko Komeh II raise issues about;

- The lack of infrastructural development of Chirano SHS.

- He also spoke on the need to upgrade the Chirano clinic to a polyclinic to enable the health facility serve the people of Chirano and surrounding communities to the maximum.

- Again he appealed to the MCE that the crime rate of Chirano is on the ascendency so a police station at Chirano will be in order to check the increasing crime rate within the Chirano area.

- Lastly he appealed to the MCE to work on the construction of Chirano roads to give the vicinity a facelift.

The representative of the Omanhene of Sefwi Anhwiaso Nana Bonya on behalf of the Omanhene made the following request.

- He spoke on the bad nature of the refuse disposal sites within the Sefwi Anhwiaso, Bekwai and Chirano Traditional areas. He pleaded with the assembly as a matter of urgency to work on getting a final refuse disposal site for the municipality.

- Also he reported on the massive encroachment activities on the Bekwai market land. He entreated the assembly to do everything within their means to protect the land for future use.

- He spoke on the potholes between the Bekwai and Ashiam stretch as an accident prone area which needs urgent attention to prevent accidents from occurring on the stretch of road.

- He lastly urged the municipal to speed up the work on Surano CHPS compound to completion.

The representative of the Tanoso traditional area also raised the following issues for the necessary attention.

- The road Leading to Tanoso school is  inaccessible and need to be looked at

- Secondly, the road from Tanoso junction to Adupri is also in a bad state and need urgent attention.

- He also suggested that it's about time the traditional authorities are involved in the revenue mobilization ie property rate collection.

After the time for members to ask questions and make suggestions the MCE, the Municipal Coordinating Director, the Municipal Planning Officer and other departmental heads took time to respond to the questions and issues raised. Among the noted once included the following;

- On the issue of the lawlessness in the Municipal capital and the activities of the tricycle, the Coordinating Director stated that the Assembly will collaborate with the Municipal Police Commander of MITTD to regulate their activities within the Municipality especially on market days and also to decongest the principal streets.

- On the issue of the office of the People with Disability and also the GNPC funded toilet facility at New Town, it was explained that there are a few things that need to be in place to give room for the commissioning and handing over the projects to its users. The Municipal Chief Executive assured members that the necessary steps will be taken to speed up the works to hand over the projects.

- The Municipal Coordinating Director took note of the issues raised on the labour and the Ghana water offices and stated that management will take another look at those issues for consideration.

- On the issue of introducing contractors to the Assemblymen and other relevant stakeholders, it was stated that a community entry meeting between the contractors and key stakeholders before the commencement of projects are held to introduce the contractor to the key stakeholders and also discuss contract details before project commencement. He entreated citizens to take key interest in projects and support monitor visits to assure value money on project materials and works.

- On the issue of support for petty traders the Municipal Planning officer stated that the EU Grant Support Project funds are still available and interested groups should apply to the Sefwiman rural bank for consideration and possible award of loans at cheaper market rates.

- On the issue of the water shortage in Bibiani the MCE took time to explain factors that are contributing to the water shortage in the capital. Among them were the issues

Pictures of Public Hearing

| Type of Infrastructure/ Assets | Type of maintenance | Schedule of Maintenance (start date – end date) | Estimated cost of maintenance | Location | Responsibility |
| --- | --- | --- | --- | --- | --- |
| Residential Accommodation | Renovation & Furnishing | 2021 – 2024 | 325,000.00 | Bibiani | Works/procurement |
| Office Accommodation | Renovation &Furnishing | 2021 – 2024 | 750,000.00 | Bibiani | Works/procurement |
| Official Vehicles | Servicing and routine maintenance | 2021 – 2024 | 667,112.00 | Bibiani | Transport/Procurement |
| Office Equipment | Servicing and routine maintenance | 2021 – 2024 | 440,692.00 | Bibiani | Procurement/ MIS |
| Street Lights | Change of electric bulbs, general repairs | 2021 – 2024 | 630,000.00 | Municipal wide | ECG, Works |
| Boreholes | Routine servicing and maintenance | 2021 – 2024 | 420,000.00 | Municipal wide | Works |
| Maintenance of fire tender | Routine Servicing and maintenance | 2021-2024 | 100,000.00 | Bibiani | Fire Service |
| Feeder Roads | Rehabilitation, reshaping, construction and re-construction of bridges | 2021 – 2024 | 1,238,700.00 | Municipal wide | Works & feeder roads |
| School buildings | Renovation | 2021 – 2024 | 839,356.00 | Municipal wide | Works/Education |
| CHPs Compounds | Renovation | 2021 – 2024 | 320,000.00 | Municipal wide | Health/Works |
| Markets | Rehabilitation & Renovation | 2021 – 2024 | 400,000.00 | Bibiani, Bekwai and Awaso | Works |
| Solid and Liquid waste management | Routine maintenance | 2021 – 2024 | 1,640,000.00 | Municipal wide | Env. Health Unit |
| TOTAL |  |  | 7,770,860.00 |  |  |

## Appendix II - Assets Maintenance Plan (2022 – 2025)

## Appendix III - Climate Change Mitigation and Vulnerability Analysis

| S/N |  | Communities likely to be affected by disasters | Type of Risks | Population | Number of people likely to be affected | Key infrastructure likely to be affected | Water channels/Rivers /Steams | Identified Safe Havens | Measures to prevent identified disaster |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  | Awaso | Flood | 4,200 | 155 | Farm land/ Houses | Awa river | Roman Catholic church | Desilt choke gutters and clean-up exercise |
| 2 |  | Subiri habitat | Flood | 2,500 | 120 | Farm land/ Houses | Subiri river | JHS | Desilt choke gutters and clean-up exercise |
| 3 |  | Kofikrom | Flood | 600 | 120 | House | Soro river | School | Desilt choke gutters and clean-up exercise |
| 4 |  | Surano A | Flood | 2,200 | 80 | Farm land/ Houses | Soro river | School | Desilt choke gutters and clean-up exercise |
| 5 |  | Safokye | Flood | 300 | 50 | Farm land/ Houses | Soro river | School | Desilt choke gutters and clean-up exercise |
| 6 |  | Afamu | Flood | 2,000 | 50 | Farm land/ Houses | Chira river | School | Desilt choke gutters and clean-up exercise |
| 7 | Alata |  | Flood | 450 | 100 | Farm land/ Houses | Soro river | Chief Palace | Desilt choke gutters and clean-up exercise |
| 8 | Bekwai Axile Weigh |  | Flood | 6,300 | 500 | Farm land/ Houses | Addei river | DC School | Desilt choke gutters and clean-up exercise |
| 9 | Old town Bibiani |  | Flood | 6,400 | 450 | Farm land/ Houses | Amponsa river | Old Methodist Church | Desilt choke gutters and clean-up exercise |
| 10 | Hwenapori |  | Flood | 3,200 | 200 | House | Mensin river | School | Desilt choke gutters and clean-up exercise |
| 11 | Attakrom |  | Flood | 8,200 | 150 | Farm land/ Houses | Hohorosabra river | Victory Preparatory | Desilt choke gutters and clean-up exercise |
| 12 | Natwikumye |  | Flood | 7,500 | 420 | Farm land/ Houses | Hohorosabra river | C.A.C | Desilt choke gutters and clean-up exercise |
| 13 | Jee Akurase behind administration |  | Flood/Rain storm | 2,100 | 150 | Farm land/ Houses | Mensin | Municipal Administration | Desilt choke gutters and clean-up exercise |
| 14 | Pataboso Nkwanta |  | Flood | 1,800 | 60 | Farm land/ Houses | Korsan | Market | Desilt choke gutters and clean-up exercise |
| 15 | Subiri-nkwanta |  | Flood | 4,800 | 120 | House | Subiri | Primary and JHS School | Desilt choke gutters and clean-up exercise |
| 16 | Dominibo 1 |  | Flood | 950 | 40 | House | Afaasue | School | Desilt choke gutters and clean-up exercise |
| 17 | Dominibo 2 |  | Flood/Rain storm | 2,000 | 80 | Farm land/ Houses | Afaasue | School | Desilt choke gutters and clean-up exercise |
| 18 | Ankramuano |  | Flood | 5,000 | 150 | House | Ankobra | School | Desilt choke gutters and clean-up exercise |
| 19 | Anhwiaso |  | Flood | 6,000 | 200 | House | Auwa,Ankobra | Market | Desilt choke gutters and clean-up exercise |
| 20 | Bekwai-Nsuoakyi |  | Flood | 4,500 | 550 | Farm land/ Houses | Anoku | Korsa & Partner School | Desilt choke gutters and clean-up exercise |
| 21 | Asawinso A |  | Flood | 3,000 | 180 | House | Ankobra | School | Desilt choke gutters and clean-up exercise |
| 22 | Chira |  | Flood | 320 | 120 | House | Chira river | School | Desilt choke gutters and clean-up exercise |
| 23 | Abesinsuom |  | Flood | 430 | 46 | House | Mensin river | Roman Catholic church | Desilt choke gutters and clean-up exercise |
| 24 | Aboduabo |  | Flood/Rain storm | 416 | 206 | House | Mmanawo | Roman Catholic church | Desilt choke gutters and clean-up exercise |
| 25 | Mepesiem |  | Flood | 210 | 65 | House | Ankobra | Methodist Church | Desilt choke gutters and clean-up exercise |
| 26 | Wenchi |  | Flood | 2,800 | 100 | House | Chine | Methodist Church | Desilt choke gutters and clean-up exercise |
| 27 | Kunkumso |  | Flood | 4,100 | 180 | House | Gyantoo river | Roman Catholic church | Desilt choke gutters and clean-up exercise |
| 28 | Breman |  | Flood | 650 | 200 | Farm land/ Houses | Ankobra | Roman Catholic church | Desilt choke gutters and clean-up exercise |
| 29 | Abokyikrom |  | Flood | 284 | 41 | House | Nyoboso river | School | Desilt choke gutters and clean-up exercise |
| 30 | Nsuontam |  | Flood | 1,140 | 480 | House | Mensin river | School | Desilt choke gutters and clean-up exercise |
| 31 | Oforikrom Bibiani |  | Flood | 2,840 | 1100 | House | Hohorosabra river | School | Desilt choke gutters and clean-up exercise |
| 32 | Chine |  | Flood/Rain storm | 1,020 | 80 | Farm land/ Houses | Chine | Roman Catholic church | Desilt choke gutters and clean-up exercise |
| 33 | Praga |  | Flood | 4,850 | 2000 | House | Hohorosabra river | School | Desilt choke gutters and clean-up exercise |
| 34 | Mframakrom |  | Flood | 300 | 50 | Farm land/ Houses | Asuwa | School | Desilt choke gutters and clean-up exercise |
| 35 | Pataboso |  | Flood | 1,600 | 85 | Farm land/ Houses | Chine | Roman Catholic church | Desilt choke gutters and clean-up exercise |
| 36 | Etwebo |  | Flood | 2,150 | 180 | Farm | Etwebo | Roman Catholic church | Desilt choke gutters and clean-up exercise |