REPUBLIC OF GHANA

BIBIANI –ANWHIASO –BEKWAI MUNICIPAL ASSEMBLY

WESTERN-NORTH REGION

APPROVED 2024 COMPOSITE ANNUAL ACTION PLAN

# BIBIANI -ANHWIASO-BEKWAI MUNICIPAL ASSEMBLY

# 1.0 INTRODUCTION

The 2024 Annual Action Plan of the Bibiani-Anhwiaso-Bekwai Municipal Assembly outlines the activities which the Municipal Assembly has planned to implement for the year 2024 in collaboration and support of the Central Government, Donors, NGOs, CSOs and the  communities They are programmes and projects earmarked in the 2022-2025 DMTDP that are in line the Medium-Term National Development Policy Framework (MTNDPF 2022-2025) christened “An Agenda for Jobs: Creating Prosperity and Equal Opportunity for All II” and also in consonance with the Long Term National Development Policy Framework “a just, free, and prosperous nation with high levels of national income and broad-based social development’’ and the Medium-Term National Development Policy Framework, 2022-2025, with six main goals: build a prosperous society; create equal opportunities for all;  safeguard the natural  environment and ensure a resilient built environment; Maintain a stable, united and safe society; Mainstream Emergency Response Activities into District Development Planning and Improve percentage implementation of Development Programme.

The projected 2024 population based on the 2021 PHC with a growth rate of 2.9% stand at 183,239 with 90,332 males and 92,907 females.

1.1 DATE OF ESTABLISHMENT

The Bibiani-Anhwiaso-Bekwai Municipal Assembly was established in 1988 by the Local Government (Bibiani-Anhwiaso-Bekwai Municipal Assembly) (Establishment) Instrument, L.I 1387 under the then Local Government Law, 1988 PNDCL 207. The district was elevated into a Municipal status in 2018 and inaugurated on Thursday, 15th March, 2018 with LI 2284. Bibiani is the Municipal capital of the Bibiani Anhwiaso Bekwai Municipal.

1.2 VISION

The vision of the Assembly is to be an efficient and effective municipality with continuous enhanced living standards of its people.

1.3 MISSION STATEMENT

The Municipal Assembly exists ‘to facilitate the overall development of the municipality by effectively formulating and implementing plans and programmesof the Assembly, Ministries, Departments, Agencies and Non-Governmental Organisations to improve the quality of life of the people in the district.

1.4 LOCATION AND SIZE

The municipality is in the north-western part of the Western Region of Ghana and between latitude 6o N, 3o N and longitude 2o W, 3o W. It is bordered to the North by the Atwima Mponua District in the Ashanti Region, South by the Wassa Amenfi West in the Western Region, West by the Sefwi Wiawso Municipal Assembly in the Western North Region and East by the Upper Denkyira West and Amannsie West in the Ashanti Region respectively. The municipality has a total land area of 873 km square.

Table 1 below provides a summary of the plan under various Development Dimensions

| THEMATIC AREAS | ECONOMIC DEVELOPMENT | SOCIAL DEVELOPMENT | ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENTS | GOVERNANCE, CORRUPTION AND ACCOUNTABILITY | Emergency Planning & Response (Including Covid-19) | Implementation, Coordinating, Monitoring & Evaluation |
| --- | --- | --- | --- | --- | --- | --- |
| GOAL | Build a prosperous society | Create equal opportunity for all | Ensure resilient built environment while safeguarding the natural environment | Maintain a stable, safe and united society | Mainstream Emergency Response Activities into district development Planning | Improve percentage implementation of development programme |
| SECTORS | Trade, Agriculture, Markets, Tourism, Private Sector Development | Education, Health, Child development & Protection, HIV/AIDS, Persons with Disability, Portable Water, Women Empowerment & Gender | Transportation, Energy, Waste & Sanitation, ICT, Human Settlement & Dev’t Planning, Natural Resource. | Revenue Mobilization, Local Governance, Security | Health care, disaster prevention and pandemics | Development planning, Budgeting, and local governance |
| TOTAL NO. OF PROGRAMS AND PROJECTS | 39 | 64 | 29 | 18 | 6 | 8 |
| LEAD IMPLEMENTING AGENCY | BAC, MOFA, DWD / Central Administration | SWCD, GHS, GES, DWD, ILO, TA/ Central Administration | MEHU, DWD, TCPD, FSD, GES/ Central Administration | NADMO, GNFS/ Central Administration | GHS, NADMO and Central Administration | Central Administration |

Composite Annual Action Plan for 2024

| Programme (PBB) | Sub- Programme (PBB) | Broad Activities | Location | Time Frame |  |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Q1 |  | Q2 | Q3 | Q4 | GoG (GH¢) | IGF (GH¢) | Others (GH¢) | New | On-going | Lead | Collaborating |
| DEVELOPMENT DIMENSION 1: ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Strong and Resilient Economy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Finance | 1. Train revenue collectors and key staff on revenue collection strategies | Bibiani |  |  |  |  |  | - | 15,000.00 | 5,000.00 |  | - | Finance | CA, GIZ |
| Management | Finance | 2. Undertake data collection to update the list of ratable properties and businesses to enhance revenue mobilization | Municipal Wide |  |  |  |  |  | - | 30,000.00 | - |  | - | Finance Dept./ | CA |
| Focus Area: Private Sector Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Trade, Industry and Tourism | 3. Organize quarterly LED platform meetings / business forum to improve business growth | Bibiani |  |  |  |  |  | - | 36,000.00 | - |  | - | BAC | CA |
|  |  | 4. Organize basic skills training in soap making 70 unemployed women and youth | Municipality-Wide |  |  |  |  |  | 20,000.00 | 30,000.00 | - |  | - | BAC | CA, Donors |
|  |  | 5. Organize monthly business counselling sections and follow-ups for 160 SMEs | Bibiani |  |  |  |  |  | 20,000.00 | 30,000.00 | 10,000.00 |  | - | BAC | CA |
|  |  | 6. Facilitate access to credit facilities by 60 SMEs from the financial institutions | Municipality wide |  |  |  |  |  | 30,000.00 | - | - |  | - | BAC | CA |
|  |  | 7. Conduct monthly monitoring exercise for 120 CAPBUSS loan beneficiaries to assess the recovery rate | Bibiani & Bekwai |  |  |  |  |  | - | - | 24,000.00 |  | - | BAC | Sefwiman Rural Bank |
|  |  | 8. Organize basic management training for 152 SMEs and business associations in entrepreneurship | Bibiani |  |  |  |  |  | 20,000.00 | 20,000.00 | 10,000.00 |  | - | BAC | CA, RTF, Donors |
|  |  | 9. Construction of 20 No. Market stalls at Wenchi | Wenchi |  |  |  |  |  | 200,000.00 | - | - |  | - | Works | CA |
| Focus Area: Agriculture and Rural Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 21Economic Development | Agricultural Services and Management | 10. Organize District Farmers Day Celebrations | Selected Community |  |  |  |  |  | 70,000.00 | - | - |  | - | MDA | CA |
|  |  | 11. Disseminate Extension Information through 15 AEAs fortnightly home and farm visits including Vet AEAs | Municipality- wide |  |  |  |  |  | 10,800.00 | - | - |  | - | MDA | CA |
|  |  | 12. Conduct monitoring, MDA and Municipal Assembly officers | Municipality- wide |  |  |  |  |  | 8,000.00 | - | - |  | - | MDA | CA |
|  |  | 13. Train 10 pig farmers (male, female & youth) on feed formulation | Municipal Wide |  |  |  |  |  | 2,000.00 |  | - |  | - | MDA | CA |
|  |  | 14. Train 15 farmers (male, female, and youth on IMO technology | Bibiani |  |  |  |  |  | 2,495.00 | - | - |  | - | MDA | CA |
|  |  | 15. Follow up visit to 30 rice farmers PWD, Aged and Youth by MDA, MIS. | Municipality- wide |  |  |  |  |  | 1,800.00 | - | - |  | - | MDA | CA |
|  |  | 16. Train 15 farmers (male, female, and youth) on climate smart Agriculture | Municipality- wide |  |  |  |  |  | 3,000.00 | - | - |  | - | MDA | CA |
|  |  | 17. Train 60 farmers (women PWD, youth) in post-harvest management of cereal crops | Municipality- wide |  |  |  |  |  | 6,000.00 | - | - |  | - | MDA | CA |
|  |  | 18. Organize monitoring visits by MDA and MAQ visits | Municipality- wide |  |  |  |  |  | 4,560.00 | - | - |  | - | MDA | CA |
|  |  | 19. Sensitize and Train 20 farmers (women, PWD, youth) on the use of local food ingredients and Nutrition | Municipality- wide |  |  |  |  |  | 5,000.00 | - | - |  | - | MDA | CA |
|  |  | 20. Support for Planting for Food and Jobs (PFJs) &Planting for Export and Rural Development (PERD) and another agricultural programme. | Municipality- wide |  |  |  |  |  | 56,000.00 | - | - |  | - | MDA | CA |
|  |  | 21. Attend Regional meetings, workshops, seminars, and conference with other stakeholder’s engagements by MDA, MACs, driver and other staff | Municipality- wide |  |  |  |  |  | 6,000.00 | - | - |  |  | MDA | CA |
|  |  | 22. Facilitate the signing of MOUs between 10-member Rice FBO and market women | Bibiani |  |  |  |  |  | 1,000.00 | - | - |  | - | MDA | CA |
|  |  | 23. Sensitization of 100 livestock farmers (male, female, PWD, Youth) on vaccination of Pets against Rabies and PPR by December 31st 2023 | Municipality- wide |  |  |  |  |  | 2,500.00 | - | - |  |  | MDA | CA |
|  |  | 24. Train 60 female farmers on feeding from the 4-star food groups | Municipality- wide |  |  |  |  |  | 3,857.00 | - | - |  |  | MDA | CA |
|  |  | 25. Organize 2 technical Review Meeting by the MIS officer | Bibiani & Bekwai |  |  |  |  |  | 2,400.00 | - | - |  |  | MDA | CA |
|  |  | 26. Train 10 fish farmers (male, female & youth) on good aquaculture practices | Municipality- wide |  |  |  |  |  | 2,000.00 | - | - |  |  | MDA | CA |
|  |  | 27. Train 20 female farmers, PWD and youth on food safety and environmental hygiene | Municipality- wide |  |  |  |  |  | 2,000.00 | - | - |  |  | MDA | CA |
|  |  | 28.Internal Management of organization (utility bills, electricity, water, office supplies, internet bundles) | Municipality- wide |  |  |  |  |  | 4,800.00 | - | - |  |  | MDA | CA |
|  |  | 29.Train 15 farmers and 10, Agro, inputs dealers (women, PWD, youth) illegal chemicals and potential health effects of pesticides | Municipality- wide |  |  |  |  |  | 2,300.00 | - | - |  | - | MDA | CA |
| Economic Development | Agricultural Services and Management | 30. Train 25 Female Farmers, PWD, youth) on alternative source of livelihoods power zone preparation | Municipality- wide |  |  |  |  |  | 2,000.00 | - | - |  | - | MDA | CA |
| Economic Development | Agricultural Services and Management | 31.Runing and maintenance of 12 official Motorbikes for MAOs and AEAs (insurance, roadworthy and fuel allowance) | Bibiani |  |  |  |  |  | 1, 860.00 | - | - |  |  | MDA | CA |
| Economic Development | Agricultural Services and Management | 32. Quarterly Runing and Maintenance of official vehicle (insurance, roadworthy, purchase of safety guard) | Bibiani |  |  |  |  |  | 6,000.00 | - | - |  |  | MDA | CA |
| Economic Development | Agricultural Services and Management | 33. Repairs and maintenance of office and MDA premises – painting, leakages, toilet facilities, pipelines, and water systems | Municipality- wide |  |  |  |  |  | 21,000.00 | - | - |  |  | MDA | CA |
| Economic Development | Agricultural Services and Management | 34. Train 10 female farmers and youth in snail rearing as an alternative source of livelihoods | Bibiani |  |  |  |  |  | 2,375.00 | - | - |  | - | MDA | CA |
| Economic Development | Agricultural Services and Management | 35. Train 20 female FBO members on the dynamics of group formation and records / data collection | Humijibre |  |  |  |  |  | 3,200.00 | - | - |  | - | MDA | CA |
| Focus Area: Tourism and Creative Arts Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Trade, Industry and Tourism | 36. Promote the celebration of National Independence Day | Municipal wide |  |  |  |  |  | - | 20,000.00 | 50,000.00 |  | - | CA | MLGDRD |
|  |  | 37. Organize radio sensitizations to educate public on issues including marriage rites and puberty rights | Bibiani & Bekwai |  |  |  |  |  | - | 20, 000.00 | - |  | - | Dept. of Arts & Culture | CA |
| Economic Development | Economic Development | 38. Establishment of an Arts center to promote local Arts & Culture | Bibiani |  |  |  |  |  | - | 20,000.00 | - |  | - | Dept. of Arts & Culture | CA |
| Economic Development | Economic Development | 39. Organize 2024 Municipal Festival of Arts and Culture | Bibiani |  |  |  |  |  | - | 90,000.00 | - |  | - | Dept. of Arts & Culture | CA |
| DEVELOPMENT DIMENSION 2: SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Education and Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 40. Construction of 1 No. 6-Unit Classroom Block with office, Store, and 5-Seater WC toilet facility at Queens SHS | Anhwiaso |  |  |  |  |  | 791,920.30 | - | - |  | - | GES | Works |
|  |  | 41. STMIE for 30 students from selected schools | Municipal wide |  |  |  |  |  | - | 20,000.00 | 27,000.00 |  | - | GES | CA |
|  |  | 42. Construction of 1 No. 6-Unit classroom Block with office, store and changing room for girls | Nsuontam |  |  |  |  |  | 400,000.00 | - | - |  | - | GHS | Works |
|  |  | 43. Facilitate the Organization of mock exams for BECE candidates | Municipal wide |  |  |  |  |  | 153,000.00 | - | - |  | - | GES | CA |
|  |  | 44. Organize Inter-schools’ sports and athletic competition | Municipal Wide |  |  |  |  |  | - | 30,000.00 | - |  | - | GES | CA |
|  |  | 45. Organize capacity building for Teachers | Bibiani |  |  |  |  |  | 20,000.00 | - | 20,000.00 |  | - | GES | CA |
|  |  | 46. Supply of 1,000 Mono Desks for schools | Selected Schools |  |  |  |  |  | - | - | 82,916.25 |  | - | GES | CA |
|  |  | 47. Supply of 1,135 Dual Desk for schools | Selected Schools |  |  |  |  |  |  |  | 50,830.08 |  |  |  |  |
|  |  | 48. Supply of 500 No. Mono Desks for Queens and Chirano SHS | Queens & Chirano SHS |  |  |  |  |  | 154,425.00 | - | - |  | - | GES | LMC |
| Focus Area: Health and Health Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 49. Procurement of 8 delivery sets for CHPS Compounds | Debiso, Adupiri, Surano A’, Ntakam, Akaaso, Akaasu, Aboduabo & Kumkumso |  |  |  |  |  | 50,496.00 | - | - |  | - | GHS | CA |
|  |  | 50. Procurement of 5 delivery beds for CHPS compounds | Selected CHPS Zones |  |  |  |  |  | 50,000.00 | - | - |  | - | GHS | CA |
|  |  | 51. Support training in malaria case management | Municipal wide |  |  |  |  |  | 25,000.00 | 10,000.00 | - |  | - | GHS | CA, Private Sector, NGOs |
|  |  | 52. Support for national immunization campaigns and support for neglected tropical Disease control programme | Municipal wide |  |  |  |  |  | - | 30,000.00 | 30,000.00 |  | - | GHS | CA |
|  |  | 53. Intensify education to reduce stigmatization on HIV/AIDs and other diseases | Municipal wide |  |  |  |  |  | 16,000.00 | 20,000.00 | - |  | - | GHS | CA |
|  |  | 54. Intensify behavioral change strategies, especially for high risks groups for HIV/AIDS and TB | Municipal wide |  |  |  |  |  | 6,000.00 | 10,000.00 | - |  | - | GHS | CA |
|  |  | 55. Rehabilitation of malnourished children ward and support other Nutritional activities | Bibiani |  |  |  |  |  | 50,000.00 | - | - |  | - | GHS | CA |
|  |  | 56. Organize quarterly Municipal health Committee meetings | Bibiani |  |  |  |  |  | - | 35,000.00 | - |  | - | GHS | CA |
|  |  | 57. Support the management of Public Health emergencies i e. disease outbreak | Municipal wide |  |  |  |  |  | - | - | 250,000.00 |  | - | GHS | CA |
| Focus Area: Food and Nutrition Security |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Service Delivery | Public Health Services and Management | 58. Promote nutritionally sensitive and cost-effective diet through education and sensitization through radio and community visits | Municipal wide |  |  |  |  |  | 28,000.00 | 50,000.00 | 2,000.00 |  | - | GHS | CA, Private Sector, |
|  |  | 59. Promote the production of diversified, nutrient-rich food and consumption of nutrition foods | Municipal wide |  |  |  |  |  | - | 20,000.00 | 30,000.00 |  | - | GHS | CA |
|  |  | 60. Sensitization to reduce infant, adult malnutrition, and dietary non communicable diseases | Municipal wide |  |  |  |  |  | 15,000.00 | 30,000.00 | - |  | - | GHS | CA |
| Social Service Delivery | Public Health Services and Management | 61. Organize demonstrative training workshop for women on kitchen gardens and food basal in 5communities | Selected Communities |  |  |  |  |  | - | 20,000.00 | 30,000.00 |  | - | SWCD | CA |
| Focus Area: Population Management and Migration for Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Public Health Services and management | 62. Organize sensitization programme on teenage pregnancy on radio | Bibiani |  |  |  |  |  | - | 22,000.00 | - |  | - | SWCD | NCCE UNICEF |
| Social Services Delivery | Population Management | 63. Collaboration with Immigration service on migration data within the Municipality | Municipal Wide |  |  |  |  |  | 10,000.00 | 25,000.00 | - |  | - | Statistics Dept | CA GIS |
| Focus Area: Reducing Poverty and Inequality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Services | 64. Monitor and coordinate Livelihood Empowerment Against Poverty (LEAP) programme | Municipal Wide |  |  |  |  |  | - | - | 34,000.00 |  | - | SW&CD | CA |
|  |  | 65. Coordinate activities of School Feeding Programme | Beneficiary schools |  |  |  |  |  | 30,000.00 | 20,000.00 | - |  | - | SW&CD | CA |
|  |  | 66. Provision of Medical Support to the vulnerable | Municipal Wide |  |  |  |  |  | 70,000.00 | 30,000.00 | - |  | - | SWCD | CA |
|  |  | 67. Support 1,000 Vulnerable people to get NHIS Cards | Municipal Wide |  |  |  |  |  | 30,000.00 | 50,000.00 | 15,000.00 |  | - | SWCD | CA |
| Focus Area: Water and Environmental Sanitation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Environmental Health and Sanitation Services | 68. Procure 2 No motorbike for monitoring activities of sanitation service providers | Bibiani |  |  |  |  |  | 86,000.00 | - | - |  | - | EHU | CA |
|  |  | 69. Procure 5 No. refuse containers and sanitary tools | Municipal Wide |  |  |  |  |  | 70,000.00 | - | - |  | - | EHU | CA |
|  |  | 70. Conduct screening of 800 food vendors | Municipal Wide |  |  |  |  |  | 20,000.00 | 35,000.00 | - |  | - | EHU | CA |
|  |  | 71. Promote household toilet construction in 10 communities (CLTS) | Municipal Wide |  |  |  |  |  | 5,500.00 | 20,000.00 | - |  | - | EHU | CA |
|  |  | 72. Conduct environmental health /hygiene education in 40 communities | Municipal Wide |  |  |  |  |  | 32,000.00 | - | - |  | - | EHU | GES, NGOs |
|  |  | 73. Organize spraying to control Pests and vectors in the municipality | Bibiani |  |  |  |  |  | 30,000.00 | 20,000.00 | - |  | - | EHU | MA |
|  |  | 74. Solid and liquid waste management, (Fumigation, manage wasteland fills Contract with Zoomlion) | Municipal Wide |  |  |  |  |  | 300,000.00 | - | - |  | - | EHU | CA, Zoomlion |
|  |  | 75. Conduct quarterly Evaluation and Performance Review meetings with Environmental Health Zonal Heads | Bibiani |  |  |  |  |  | 20,000.00 | 25,000.00 | - |  | - | EHU | CA |
|  |  | 76. Conduct monthly monitoring of Sanitation service providers | Municipal Wide |  |  |  |  |  | 15,000.00 | 20,000.00 | - |  | - | EHU | CA |
|  |  | 77. Conduct quarterly meeting of Sanitation Service providers | Bibiani |  |  |  |  |  | 12,000.00 | 12,000.00 | - |  | - | EHU | CA |
|  |  | 78. Construction of Slaughter House in Lineso | Lineso |  |  |  |  |  | 400,000.00 | - | - |  | - | EHU | CA |
|  |  | 79. Procurement of 1 ambient meter for controlling public noise | Selected Communities |  |  |  |  |  | 15,000.00 | - | - |  | - | EHU | CA |
|  |  | 80. Construction and Mechanization of 1 No. Borehole at Bibiani New Town with overhead Tank and extension of pipelines to the Municipal Hospital Director’s Bungalow | Bibiani |  |  |  |  |  | 100,000.00 | - | - |  | - | Works | CA |
|  |  | 81. Provide public education on solid waste management | Municipal wide |  |  |  |  |  | 10,000.00 | 4000.00 | 4000.00 |  | - | EHU | CA |
|  |  | 82. Promote public health education and hygiene in basic schools | Municipal wide |  |  |  |  |  | 10,.000.00 | 40,000.00 | 5000.00 |  | - | EHU | CA |
|  |  | 83. Training of food vendors on safety and proper handling of food | Municipal wide |  |  |  |  |  | - | 20,000.00 | 15,000.00 |  |  | EHU | CA |
|  |  | 84. Construction and Mechanization of 7 No. Boreholes with overhead tanks | BISEC, Ntakam, Fawokabra, Anyinase, Asempaneye, Ohiampeneka, Degede & Mota yard |  |  |  |  |  | 393,306.90 | - | - |  | - | EHU | LMC |
| Focus Area: Child Protection and Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Services | 85. Monitoring and Formation of Girls Club in 10 selected Schools | Selected Schools |  |  |  |  |  | - | - | 10,000.00 |  | - | SW&CD | MCPC |
|  |  | 86. Coordination and training of Gender child Protection committees in 20 Communities | Selected communities |  |  |  |  |  | - | - | 20,000.00 |  | - | SW&CD | MCPC |
|  |  | 87. Remediation support for children |  |  |  |  |  |  | 10,000.00 | 20,000.00 | 20,000.00 |  | - | SWCD | CA |
| Focus Area: Gender Equality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Services | 88. Sensitization on Sexual and Gender based violence | Municipal wide |  |  |  |  |  | - | 7,000.00 | - |  | - | SW&CD | CA, NGOs |
|  |  | 89. Organize sensitization programme on Persistent negative discriminatory socio-cultural and customary practices against women | Bibiani |  |  |  |  |  | 25,000.00 | 10,000.00 | 5,000.00 |  | - | SW&CD | CA, NGOs |
|  |  | 90. Provide educational support to 10 female students pursuing science at the Tertiary level | Municipality- wide |  |  |  |  |  | 30,000.00 | 30,000.00 | - |  | - | CA | GES |
|  |  | 91. Organize basic skills training in poultry farming for 65 women cocoa farmers | Municipality- Wide |  |  |  |  |  | 25,000.00 | 10,000.00 | - |  | - | BAC | CA |
| Focus Area: Sports and Recreation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education, youth &sports and library services | 92. Organize community football galas | Bibiani |  |  |  |  |  | 40,000.00 | 20,000.00 | - |  | - | CA | Football Teams |
| Focus Area: Youth Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education, youth &sports and library services | 93. Organize skills training in alternative livelihoods for 80 youth in cocoa growing areas | Municipality- Wide |  |  |  |  |  | 25,000.00 | 10,000.00 | - |  | - | BAC | CA |
| Focus Area: Social Protection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Welfare and Community Services | 94. Coordination, Monitoring and Reporting of child related cases | Bibiani |  |  |  |  |  | - | 10,000.00 | 5,000.00 |  | - | SW& CD | CA, MCPC |
| Focus Area: Disability-Inclusive Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Welfare and Community Services | 95. Provide medical /assistive devices to PWDs | Municipal wide |  |  |  |  |  | 30,000.00 | 20,000.00 | - |  | - | SW& CD | CA |
|  |  | 96. Organize Advocacy & awareness creation on the rights & responsibilities of PWDs | Bibiani |  |  |  |  |  | 12,000.00 | 20,000.00 | - |  | - | SW& CD | CA |
|  |  | 97. Provide educational/ apprenticeship support to PWDs | Municipality-wide |  |  |  |  |  | 10,000.00 | 10,000.00 | - |  | - | SW& CD | CA |
|  |  | 98. Strengthening organization of Persons with Disability through capacity building | Bibiani |  |  |  |  |  | 18,000.00 | 20,000.00 | - |  | - | SW& CD | CA |
| DEVELOPMENT DIMENSION 3: ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Protected Areas |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Management | 99. Facilitate alternative livelihoods including eco-tourism support schemes for fringe communities along protected areas | 5 Selected Communities |  |  |  |  |  | 22,000.00 | 20,000.00 | 10,000.00 |  | - | Forestry Commission | CA, Care International |
|  |  | 100. Sensitization of communities to prevent illegal activities in forest reserves | Forest Reserves |  |  |  |  |  | 20,000.00 | 30,000.00 | - |  | - | Forestry Commission | Chiefs, CA |
| Focus Area: Mineral Extraction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Management | 101. Organize sensitization programme on illegal mining, deforestation, and land reclamation | Selected communities |  |  |  |  |  | 20,000.00 | 22,000.00 | - |  | - | Forestry Commission | CA, NGOs, CSO, Chiefs Minerals Commission |
| Infrastructure Maintenance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | Public works, rural housing and water management | 102. Rehabilitation of Bibiani Markets | Bibiani |  |  |  |  |  | 400,000.00 | - | - |  | - | Works | MLGDRD |
| Infrastructure Development and Management | Public works, rural housing and water management | 103. Renovation of National Ambulance Unit and Fire Tender station in Sefwi Bekwai | Sefwi Bekwai |  |  |  |  |  | 180,000.00 | - | - |  | - | Works | MLGDRD |
| Focus Area: Water Resources Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Management | 104. Enforcement of development control on water bodies | Municipal wide |  |  |  |  |  | 40,000.00 | 30,000.00 | - |  | - | Forestry Commission | CA, NGOs, CSO,Chiefs, Minerals Commission |
| Focus Area: Environmental Pollution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Management | 105. Enforce environmental laws and regulations to prevent noise pollution | Municipal Wide |  |  |  |  |  | 32,000.00 | - | - |  | - | EHU | CA, NGOs, CSO, MWST, |
|  |  | 106. Promote the use of LPG as alternative sources of energy by households | Municipal wide |  |  |  |  |  | 2,000.00 | - | 2,000.00 |  | - | NADMO | FC |
| Focus Area: Deforestation, Desertification and Soil Erosion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation and Management | 107. Support the planting of 360,000 assorted tree seedlings under the green Ghana Day programme | Municipal wide |  |  |  |  |  | 120,000.00 | - | - |  | - | Forestry Communities | NADMO |
|  |  | 108. Establishment of forest plantations in degraded forest land through Modified Taungya and industrial plantation | Anhwiaso, Aboduabo |  |  |  |  |  | 10,000.00 | - | - |  | - | Forestry Commission | CA |
| Environmental Management | Natural Resource Conservation and Mgt. | 109. Support the implementation of youth in afforestation programme | Municipal wide |  |  |  |  |  | - |  | 20,000.00 |  | - | Forestry Commission | CA |
| Focus Area: Climate Variability and Change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Natural Resource Conservation & Mgt | 110. Organize sensitization campaigns on climate change variability and adaptation in 30 communities in line with the Ghana Cocoa Forest REDD+ Programme | Selected communities |  |  |  |  |  | 12,000.00 |  | - |  | - | NADOM | CA NGO’s, FC |
| Environmental Management | Natural Resource Conservation & Mgt | 111. Undertake education on fire prevention and management in 30 communities in line with the Ghana Cocoa Forest REDD+ Programme | Selected towns |  |  |  |  |  | 2,000.00 | 20,000.00 | - |  | - | NADMO | CA, NGOs, CSO, Mineral Commission, FC |
| Focus Area: Disaster Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Disaster Prevention and management | 112. Formation of Disaster Risk Reduction clubs in 20 schools | Selected Schools |  |  |  |  |  | 2,000.00 | - | 5,000.00 |  | - | NADMO | GES |
|  |  | 113. Organize community sensitization on hazards of fire | Selected Towns |  |  |  |  |  | 3,000.00 | - | 3,000.00 |  | - | NADMO | GNFS, CA |
| Environmental Management | Disaster Prevention and management | 114. Sensitization of the public on the prevention and management of domestic and bush fires | Selected Communities |  |  |  |  |  | - | 2,000.00 | - |  | - | NADMO | GNFS |
| Environmental Management | Disaster Prevention and management | 115. Training of fuel stations, markets, and other public places on management of fire outbreaks | Selected Communities |  |  |  |  |  | - | 2,000.00 | - |  | - | NADMO | GNFS |
| Focus Area: Transportation: Road & Road Safety |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | Urban roads and transport services | 116. Spot Improvement of 13.2km Chirano-Atta Nyamekrom-Adiembra ‘C’- Bekwai Fedder Road – Phase I | Chirano-Atta Nyamekrom-Adiembra ‘C’- Bekwai |  |  |  |  |  | 120,000.00 | - | - |  | - | Works | CA |
|  |  | 117. Spot Improvement of 13.2km Chirano-Atta Nyamekrom-Adiembra ‘C’- Bekwai Fedder Road – Phase II | Chirano-Atta Nyamekrom-Adiembra ‘C’- Bekwai |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 118. De-silting of drains, patching of 3,200 potholes, and cutting of 2,400m grass | Municipality-wide |  |  |  |  |  | 420,000.00 | - | - |  | - | Works | CA, Urban Roads |
|  |  | 119. Grading of 14km Town Roads | Municipality-wide |  |  |  |  |  | 140,000.00 | - | - |  | - | Works | CA, Urban Roads |
|  |  | 120. Facilitate the management of vehicular traffic situation in the Municipal | Municipality-wide |  |  |  |  |  | 105,000.00 | - | - |  | - | Works | CA, RSC |
|  |  | 121. Installation of Street lights in Bibiani & Bekwai | Bibiani & Bekwai |  |  |  |  |  | 75,600.00 | - | - |  |  | Works | ECG |
|  |  | 122. Provision and installation of 270 Streetlights in Bibiani and Lineso | Bibiani & Lineso |  |  |  |  |  | 200,000.00 | - | - |  | - | Works | CA |
|  |  | 123. Provision and installation of 270 Streetlights in Sefwi Bekwai and Humijibre | Sefwi Bekwai & Humijibre |  |  |  |  |  | 200,000.00 | - | - |  | - | Works | CA |
|  |  | 124. Provision and installation of 260 Streetlights in Anhwiaso and Asawinso | Anhwiaso & Asawinso |  |  |  |  |  | 195,000.00 | - | - |  | - | Works | CA |
|  |  | 125. Provision and installation of 260 Streetlights in Awaso & Subri | Awaso & Subri |  |  |  |  |  | 195,000.00 | - | - |  | - | Works | CA |
|  |  | 126. Provision and installation of 260 Streetlights in Wenchi | Wenchi |  |  |  |  |  | 180,000.00 | - | - |  | - | Works | CA |
|  | Urban roads and transport services | 127. Sensitization on Road Safety policy for drivers and user | Municipal Wide |  |  |  |  |  | 10,000.00 | 5,000.00 | - |  | - | Works | CA, NRSC, NCCE |
| Focus Area: Information Communication Technology Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | ICT | 128. Organize ICT training for 150 youth | Municipal Wide |  |  |  |  |  | 5,000.00 | 15,000.00 | - |  |  | GES | CA, NGOs |
| Focus Area: Human Settlements Development and Housing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | Spatial Planning | 129. Continue the street naming and property addressing system | Anhwiaso, Chirano |  |  |  |  |  | 100,000.00 |  | 100,000.00 |  | - | Physical Planning | CA, TA .SPC |
|  |  | 130. Preparation and revision of 3 local settlement plans | Sefwi Bekwai, Chirano, Ampenkrom |  |  |  |  |  | 100,000.00 | - | - |  | - | Physical Planning | CA, TA, SPC |
|  |  | 131. Landscaping and Gardening of principal streets in Bibiani | Bibiani |  |  |  |  |  | 5,000.00 | 10,000.00 | - |  | - | Physical Planning | CA, TA , SPC |
|  |  | 132. Undertake building inspections to ensure compliance with the national building code | Municipal Wide |  |  |  |  |  | - | 20,000.00 | - |  | - | Physical Planning | CA, TA, SPC |
| Focus Area: Drainage and Flood Control |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development and Management | Public Works, Rural Housing and Water Management | 133. Construction of 6m Gee Akurase foot bridge | Gee Akurase |  |  |  |  |  | 500,000.00 | - | - |  | - | Works | CA |
| DEVELOPMENT DIMENSION 4: GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Local Governance and Decentralization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | General Administration | 134. Organize Statutory meetings (Management Meetings, Sub-Committee, Executive Committee & General Assembly Meetings, SAT Meetings etc) | Bibiani |  |  |  |  |  | - | 260,000.00 | - |  | - | CA | MLGDRD |
|  |  | 135. Maintenance of office equipment | Bibiani |  |  |  |  |  | 20,000.00 | 30,000.00 | - |  | - | CA | MLGDRD |
|  |  | 136. Rehabilitation and Furnishing of Assembly Hall | Bibiani |  |  |  |  |  | 1,300,000.00 | - | - |  | - | Works | MLGDRD |
|  |  | 137. Procurement of 100kva generator for the Assembly and other offices | Bibiani |  |  |  |  |  | 100,000.00 | - | - |  | - | Works | CA |
|  |  | 138. Maintenance of Assembly Vehicles/ General Equipment | Bibiani |  |  |  |  |  | 30,000.00 | 20,000.00 | - |  | - | CA | MLGDRD |
|  |  | 139. Renovation of selected Assembly Bungalows & Offices | Bibiani |  |  |  |  |  | 50,000.00 | 130,000.00 | - |  | - | Works | MLGDRD |
|  |  | 140. Procurement of Office Equipment /Logistics (6-No servers, 6-No laptops, UPS & Networking Equipment) | Bibiani |  |  |  |  |  | 50,000.00 | 20,000.00 | - |  | - | CA | MLGDRD |
|  |  | 141. Gazetting of Assembly’s Byelaws | Bibiani |  |  |  |  |  | 30,000.00 | - | - |  | - | CA | MLGDRD |
| Management and Administration | General Administration | 142. Support to Self Help Community Projects | Municipality- Wide |  |  |  |  |  | 200,000.00 | 100,000.00 | - |  | - | CA | MLGDRD |
|  |  | 143. Construction of Sefwi Bekwai Zonal Council Office | Sefwi Bekwai |  |  |  |  |  | 300,000.00 | - | - |  | - | CA | MLGDRD |
|  |  | 144. Support Decentralized Dept. and WNRCC | Bibiani |  |  |  |  |  | 50,000.00 | - | - |  |  | CA | MLGDRD |
|  |  | 145. Implement Capacity building plan/Staff development | Bibiani |  |  |  |  |  | 50,000.00 | 30,000.00 | - |  | - | HRM | MLGDRD |
|  |  | 146. Provision for official day celebrations | Selected Communities |  |  |  |  |  | 150,000.00 | - | - |  | - | CA | MLGDRD |
|  |  | 147. Internal Management of organization (Utility, fuel, call credit, Hotel Accommodation, NALAG Dues) | Bibiani |  |  |  |  |  | 100,000.00 | 100,000.00 | - |  | - | CA | MLGDRD |
| Focus Area: Public Accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Planning, Budgeting, Monitoring & Evaluation | 148. Organise Social Accountability Fora ie. 2 Town Hall meetings, Meet the Press & Social Audit | Bibiani & Bekwai |  |  |  |  |  | 40,000.00 | 10,000,00 | - |  | - | CA | MLGDRD |
| Focus Area: Human Security and Public Safety |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | General Administration | 149. Support for Security operations & MUSEC activities | Bibiani |  |  |  |  |  | 80,000,00 | 20,000.00 | - |  | - | CA | MLGDRD |
| Focus Area: Corruption and Economic Crimes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | General Administration | 150. Support Anti- Corruption Agencies /Implement NACAP | Municipal wide |  |  |  |  |  | 10,000.00 | 20,000.00 | - |  | - | CA | CHRAJ, Audit Service, NCCE, NGOs |
| DEVELOPMENT DIMENSION 5: EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19 RECOVERY PLAN) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Hydro meteorological |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Public Health Services and management | 151. Organize community education programme on hydro meteorological disaster | Selected Communities |  |  |  |  |  | 5,000.00 | 30,000.00 | - |  | - | NADMO | CA |
| Focus Area: Biological |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Public Health Services and management | 152. Organise sensitization and education programmes on Covid-19 and other pandemics and enforcement of safety protocols | Municipal wide |  |  |  |  |  | 20,000.00 | 10,000.00 | - |  | - | GHS | CA |
|  |  | 153. Support Municipal Public Health Emergency Management Committee & Municipal Public Health Emergency Rapid Response Team activities | Bibiani |  |  |  |  |  | 20,000.00 | 40,000.00 | - |  | - | GHS | CA |
|  |  | 154. Vaccination against public health emergencies such as Covid-19 and other pandemics | Municipality- wide |  |  |  |  |  | 10,000.00 | 10,000.00 | - |  | - | GHS | CA |
| Focus Area: Anthropogenic |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Public Health Services and management | 155. Organise 4 quarterly disaster mitigation and public awareness programmes | Selected communities |  |  |  |  |  | 5,000.00 | 12,000.00 | - |  | - | NADMO | CA |  |  |
| Relief Assistance and Victim Welfare |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Disaster Prevention and management | 156. Support 200 disaster victims with relief items | Municipal wide |  |  |  |  |  | 100,000.00 | - | - |  | - | NADMO | CA |  |  |
| DEVELOPMENT DIMENSION 6: IMPLEMENTATION, COORDINATION, MONITORING AND EVALUATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Planning, Budgeting, Monitoring & Evaluation | 157. Organize 4 Quarterly MPCU and budget committee meetings | Bibiani |  |  |  |  |  | 30,000.00 | 10,000.00 | - |  | - | CA | MLGDRD |
|  |  | 158. Preparation of 2025 composite Annual Action Plan and budget | Bibiani |  |  |  |  |  | 25,000.00 | - | - |  | - | CA | MLGDRD |
|  |  | 159. Conduct projects and programme evaluations and APR preparation sessions for HODs. | Selected Towns |  |  |  |  |  | 50,000.00 | 30,000.00 | - |  | - | CA | MLGDRD |
|  |  | 160. Dissemination of 2024 approved composite budget and Gazetting of fee-fixing | Bibiani |  |  |  |  |  | 15,000.00 | 10,000.00 | - |  | - | CA | MLGDRD |
|  |  | 161. Undertake consultative meetings and prepare 2025 Fee-Fixing Resolutions | Bibiani |  |  |  |  |  | 5,000.00 | 20,000.00 | - |  | - | CA | MLGDRD |
|  |  | 162. Undertake Mid-Year Review of the 2024 Composite Budget | Bibiani |  |  |  |  |  | 14,000.00 | - | - |  | - | CA | MLGDRD |
| Production and Utilization of Statistics |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Planning, Budgeting, Monitoring & Evaluation | 163. Conduct monthly market readings at Sefwi Bekwai and Bibiani | Bekwai & Bibiani |  |  |  |  |  | 5,000.00 | - | - |  | - | Statistics | CA |
| Management and Administration | Planning, Budgeting, Monitoring & Evaluation | 164. Build community register in 3 endemic communities of child labour using Ghana Child Labour Monitoring System | Selected Communities |  |  |  |  |  | 10,000.00 | - | - |  | - | Statistics | CA |
| Total |  |  |  |  |  |  |  |  | 9,150,372.00 | 1,480,000.00 | 1,577,000.00 | 12,207,372.00 |  |  |  |